## Read Me
Parakeet Rehab Tracker — Data Request
Two tabs: “Mark” and “Alt Vendor.” Work your own tab; the other is visible for insight. 182 active assets · prepared 6/13/26.
YOUR TAB
Mark | Your 159 in-house homes. Fill the AMBER cells (tier, actual start/end, final cost, HVAC/water heater/roof/siding, deposit, dates). John fills the magenta ISSUE # cells.
Alt Vendor (John) | The 23 Alternate-Vendor homes — all John’s. Fill every MAGENTA cell (ISSUE #, Rehab Tier, Alt Vendor name, dates, final cost, scope Y/N, deposit).
COLOR KEY (same on both tabs)
Amber | Mark fills
Magenta | John fills (every blank ISSUE # on both tabs; all rehab info on Alt Vendor homes)
Lavender | Melanie — start missing-title process
Light green | Auto-assumed completion = start + 45 days (overwrite if known)
Teal | Pre-filled by Claude from signed CAPEX/REHAB documents & invoices — verify.
GL # & ISSUE #
GL # = Rent Manager/accounting code for cost. ISSUE # = construction job/ClickUp number. Costs are actual (from invoices) where available, else estimate. Siding Deposit Y/N is for Mark to track; the old Deposit column is now Rehab Deposit Y/N.
TITLE WORKFLOW (new)
Title Status (col U) is pulled from Rent Manager; col V flags the action. 52 homes show “START missing-title (Melanie)”. Goal: when a rehab STARTS, Melanie begins missing-title work in parallel so title is IN HAND at completion and the home can be sold.
ROADMAP / FUTURE
• | Before & after photo links per home (planned).
• | Title status integration → ties rehab completion to a sellable, titled asset.
• | Cost tracking → pull final cost per home via the ISSUE # once all are filled.
• | Handoff Date — track how fast rehabs are assigned/turned (deferred).
• | Estimated budget vs final cost, permit/demo flags — tell us if you want them tracked.

## Mark
# | Community | Lot | RM Asset | Track | Vendor | Rehab Status | GL # | Rehab Tier | Alt Vendor Name | Target Start | Target End | Actual Start | Actual End | Base Cost w/ Deposit | HVAC Y/N | HVAC Cost | Water Heater Y/N | Water Heater Cost | Roof Y/N | Roof Cost | Siding Y/N | Siding Cost | Final Cost ($) | Siding Deposit Y/N | Rehab Deposit Y/N | Title Status (RM) | Title Action (Melanie) | Scope / Notes | Needs From | ISSUE #
1 | Applegate 399 Circle Dr Deland Fl 32724 | 208 | APPLE-208 Circle | Mark | Mark | Complete | 16630 | L2+ |  | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 20090.8 | Y | 7900 | N |  | Y | 1500 | Y | 4900 | 34390.8 | Y | Y | No Title | START missing-title (Melanie) | Bedroom ceiling, bath and drywall, bathroom needs full plumbing, Sub floor | Mark; Melanie
2 | Applegate 399 Circle Dr Deland Fl 32724 | 240 | APPLE-240 Circle | Mark | Mark | In Progress | 16793 | L2+ |  | 2026-08-04 | 2026-08-19 | 2026-06-22 | [6 empty] | Y |  | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
3 | Applegate 399 Circle Dr Deland Fl 32724 | 279 | APPLE-279 Circle | Mark | Mark | In Progress | 16795 | L3 |  | 2026-08-20 | 2026-09-04 | 2026-06-22 | [6 empty] | Y |  | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
4 | Applegate 399 Circle Dr Deland Fl 32724 | 335 | APPLE-335 Circle | Mark | Mark | Complete | 16629 | L1+ |  | 2026-06-15 | 2026-07-03 | 2026-06-10 | 2026-06-19 | 11618 | N |  | N |  | Y |  | Y | 4900 | 16518 | Y | Y |  | START missing-title (Melanie) | Cabinets replace / Repair | Mark; Melanie
5 | Applegate 399 Circle Dr Deland Fl 32724 | 396 | APPLE-396 Circle | Mark | Mark | In Progress | 16794 | L3 |  | 2026-09-05 | 2026-09-16 | 2026-06-22 | [6 empty] | Y |  | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
6 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 101 | ARD-101 | Mark | Mark | In Progress | 16801 | L2+ |  | 2026-07-06 | 2026-08-07 | [9 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | 101 = Level 2+ - Typical with some subfloor repair, cabinets can be repaired, some drywall. Needs siding and stairs. | Mark
7 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 106 | ARD-106 | Unmarked | Mark | NA | 16639 | To Be Assessed |  | NA | NA | [9 empty] | Y |  | 0 | N | N | Pending Transfer (MHTR) | In process — track |  | Mark
8 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 108 | ARD-108 | Mark | Mark | In Progress | 16802 | L3 |  | 2026-09-14 | 2026-08-07 | [9 empty] | Y |  | 0 | N | Y |  | START missing-title (Melanie) | 108 = Level 3 - Major sub floor and drywall repair. Plumbing issues in bathrooms and kitchen and cabinets. Needs siding. | Mark; Melanie
9 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 27 | ARD-27 | Mark | Mark | In Progress | 16798 | L1 |  | 2026-09-14 | 2026-08-07 | [9 empty] | N |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | Level 1 - Typical and needs siding. | Mark
10 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 46 | ARD-46 | Mark | Mark | In Progress | 16796 | L2 |  | 2026-09-14 | 2026-08-07 | [9 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | Level 2 - Drywall replacement, subfloors are decent, cabinet repair. Needs siding. | Mark
11 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 46A | ARD-46A | Mark | Mark | In Progress | 16797 | L3 |  | 2026-09-14 | 2026-08-07 | [9 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | 46A = Level 3 - Typical as well as cabinet replacement, subfloor replacement and some drywall repair and replacement. Also needs siding and stairs. | Mark
12 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 8 | ARD-8 | Mark | Mark | In Progress | 16800 | L2 |  | 2026-09-14 | 2026-08-07 | [9 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | 8 = Level 2 - Typical with subfloor repair, drywall and cabinet repair. Needs siding. | Mark
13 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 87 | ARD-87 | Mark | Mark | In Progress | 16803 | L1+ |  | 2026-09-14 | 2026-08-07 | [9 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | 87 = Level 1+ - Typical with minor sub floor repair. Needs siding. | Mark
171 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 26 | ARD-26 | Mark | Mark | In Progress | 16964 | L1 |  | 2026-09-14 | [10 empty] | Y |  | 0 |  |  |  |  | Level 1 - Typical and needs siding.
161 | Auburn Ridge 275 Carter Rd Auburn Ga 30011 | 122-A | ARD 122A | Mark | Mark | In Progress | 16909 | L2 |  | 2026-09-14 | [10 empty] | N |  | 0 | N |  |  |  | 122A Dplx = Level 2 - Typical interior but level 2 because it’s a duplex with some more space to it. There are some sub flooring repairs to be made, and some bathroom fixture replacement. No Siding
14 | Bay Oaks I 409 School Ave Panama City Fl 32401 | H4 | BOVIPO-H-4 | Mark | Mark | Not Started | 16592 | To Be Assessed |  | 2026-08-24 | 2026-08-21 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
| Bay Oaks II 420 N Kimbrel Ave Panama City Fl 32404 | 97 |  |  |  |  | 16965 |  |  | 2026-08-24 | [12 empty] | 0
15 | Bay Oaks II 420 N Kimbrel Ave Panama City Fl 32404 | 91 | BOVIIPO-91 | Mark | Mark | Not Started | 16591 | To Be Assessed |  | 2026-08-24 | 2026-08-21 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
| Bay Oaks I 409 School Ave Panama City Fl 32401 | C2 |  |  |  |  | 16978
16 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 16 | BELL-16 | Mark | Mark | Complete | 16628 | L1+ |  | 2026-04-01 | 2026-06-26 | 2026-04-02 | 2026-04-19 | 11606 | N |  | N |  |  |  | Y | 4900 | 16506 | Y | Y | Clear Title | Clear — in hand | Repair Cabinets ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16628), invoice 50125 $8,106.60. Base scope: cleanout, power wash exterior siding/skirting/stairs, broom-clean; level-based remodel of floors, walls, cabinets, kitchen/bath fixtures, ceilings, windows, electrical. Itemized detail image-only. Lot 16 also included in the Belle Haven siding bundle (Invoice 50118-2, GL 16628). | Mark
17 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 18 | BELL-18 | Mark | Mark | Complete | 16617 | L1+ |  | 2026-04-01 | 2026-06-26 | 2026-04-02 | 2026-04-19 | 17325 | N |  | N |  |  |  | Y | 4900 | 22225 | Y | Y | Clear Title | Clear — in hand | All New Sub Flooring, Cabinets S&P ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16617), invoice 50126 $13,824.97. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel (floors, walls, cabinets, fixtures, ceilings, windows, electrical, subfloor/drywall). Itemized detail image-only. | Mark
18 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 27 | BELL-27 | Mark | Mark | Complete | 16619 | L2 |  | 2026-04-01 | 2026-05-30 | 2026-05-01 | 2026-05-30 | 16032 | N |  | N |  |  |  | Y | 4900 | 20932 | Y | Y | Pending Transfer (Vector) | In process — track | Drywall, Cabinets S&P | Mark
19 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 21 | BELL-30A | Mark | Mark | Complete | 16626 | L1 |  | 2026-04-01 | 2026-06-26 | 2026-04-02 | 2026-04-19 | 10355 | N |  | N |  |  |  | Y | 4900 | 15255 | Y | Y | Clear Title | Clear — in hand | [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16626), invoice 50127 $6,855.00. Folder marked REFURB-COMPLETE. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Itemized detail image-only. | Mark
20 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 31 | BELL-31 | Mark | Mark | Complete | 16734 | L2 |  | 2026-04-01 | 2026-07-29 | 2026-05-01 | 2026-07-31 | 19697 | N |  | N |  |  |  | Y | 4900 | 24597 | Y | Y | Clear Title | Clear — in hand |  | Mark
21 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 33 | BELL-33 | Mark | Mark | Complete | 16618 | L2 |  | 2026-04-01 | 2026-06-26 | 2026-04-02 | 2026-05-17 | 16362 | N |  | N |  | Y |  | Y | 4900 | 21262 | Y | Y | Clear Title | Clear — in hand | Ceiling Demo , Cabinets S&P&R ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16618), final invoice $12,862.00 (two identical copies of the final invoice on file). Base scope: cleanout, power wash exterior siding/skirting/stairs, broom-clean; level-based interior remodel. Lot 33 ALSO had a separate TPO roof-over installation kickoff (issue 13728) to establish a waterproof monolithic seal, and is part of the Belle Haven siding bundle (Invoice 50118-2). | Mark | 13728 (roof-over)
22 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 36 | BELL-36 | Mark | Mark | On Hold | 16804 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 |  |  |  | N |  | N |  |  |  | Y |  | 0 | 0 | N | Clear Title | Clear — in hand | JC was testing to permit these are full gut remodels | Mark
23 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 41 | BELL-41 | Mark | Mark | Complete | 16625 | L2 |  | 2026-04-01 | 2026-07-29 |  |  | 12492 | N |  | N |  |  |  | Y | 4900 | 17392 | Y | Y | Clear Title | Clear — in hand | Cabinet S&P, Drywall | Mark
24 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 44 | BELL-44 | Mark | Mark | Complete | 16624 | L2 |  | 1900-01-03 02:24 | 2026-05-30 | 1900-01-04 | 2026-05-30 | 17011 | N |  | N |  |  |  | Y | 4900 | 21911 | Y | Y | Clear Title | Clear — in hand | Paint Cabinets, Vanity, 2 Sub Floor | Mark
25 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 44A | BELL-44A | Mark | Mark | On Hold | 16624 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | 1899-12-31 |  |  | N |  | N |  |  |  | Y |  | 0 | N | N |  | START missing-title (Melanie) | JC was testing to permit these are full gut remodels | Mark; Melanie
26 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 5 | BELL-5 | Mark | Mark | Complete | 16616 | L1+ |  | 2026-04-01 | 2026-06-26 | 2026-04-02 | 2026-05-17 | 12634 | N |  | N |  | Y | 4200 | Y | 4900 | 21734 | Y | Y | Clear Title | Clear — in hand | [CAPEX docs] High Pace Construction rehab under the All-Florida 59-home program (GL# 16616). Final invoice $13,334.00. Base program scope: trash/debris cleanout, power wash exterior siding/skirting/stairs, broom-clean and wipe all surfaces/cabinets/fixtures/appliances; home then assessed and remodeled to one of three levels covering floors, walls, cabinets, kitchen/bath fixtures, ceilings, windows, electrical outlets/fixtures and subfloor/drywall structural repair as needed. Itemized line detail image-only. | Mark
27 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 54 | BELL-54 | Mark | Mark | Complete | 16623 | L3+ |  | 2026-04-01 | 2026-05-30 | 1900-01-04 | 2026-05-30 | 27616 | N |  | N |  | Y | 6700 | Y | 4900 | 39216 | Y | Y | Clear Title | Clear — in hand | Full Gut Rehab | Mark
28 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 57 | BELL-57 | Mark | Mark | Complete | 16622 | L1+ |  | 2026-04-01 | 2026-06-26 | 2026-04-15 | 2026-05-17 | 10698 | N |  | N |  |  |  | Y | 4900 | 15598 | Y | Y | Clear Title | Clear — in hand | Vanity Replace ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16622), final invoice $7,198.00. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Part of Belle Haven siding bundle (Invoice 50118-2). Itemized detail image-only. | Mark
29 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 64 | BELL-64 | Mark | Mark | Complete | 16615 | L2+ |  | 2026-04-01 | 2026-05-30 | 2026-05-01 | 2026-05-30 | 11961 | N |  | N |  |  |  | Y | 4900 | 16861 | Y | Y | Clear Title | Clear — in hand |  | Mark
30 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 7 | BELL-7 | Mark | Mark | Complete | 16627 | L3 |  | 2026-04-01 | 2026-08-20 | 2026-07-01 | 2026-08-17 | 25146 | N |  | N |  | Y | 7500 | Y | 4900 | 37546 | Y | Y | Clear Title | Clear — in hand | Replacing Upper Cabinets & Ceiling. ADD ROOF | Mark
31 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 72 | BELL-72 | Mark | Mark | Complete | 16621 | L1 |  | 2026-04-01 | 2026-08-20 | 2026-07-01 | 2026-08-17 | 14096 | N |  | N |  | N |  | Y | 4900 | 18996 | Y | Y | Pending Transfer (Vector) | In process — track | Sub Flooring | Mark
32 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 73 | BELL-73 | Mark | Mark | Complete | 16735 | L3 |  | 2026-04-01 | 2026-08-20 | 2026-07-01 | 2026-08-17 | 23904 | N |  | N |  | Y | 6500 | Y | 4900 | 35304 | Y | Y | Pending Transfer (Vector) | In process — track | Sub Flooring Roof Repair | Mark
33 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 74 | BELL-74 | Mark | Mark | Complete | 16736 | L2+ |  | 2026-04-01 | 2026-07-29 | 2026-06-05 | 2026-07-31 | 19321 | N |  | N |  | Y | 6500 | Y | 4900 | 30721 | Y | Y | Clear Title | Clear — in hand | New Drywall needed throughout | Mark
34 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 78 | BELL-78 | Mark | Mark | Complete | 16620 | L1+ |  | 2026-04-01 | 2026-06-26 | 2026-04-02 | 2026-05-19 | 9489 | N |  | N |  |  |  | N |  | 9489 | N | Y | Clear Title | Clear — in hand | [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16620), invoice 50122 $5,988.50. Folder marked REFURB-COMPLETE. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Itemized detail image-only. | ISSUE #; Mark
35 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 86 | BELL-86 | Mark | Mark | Complete | 16614 | FULL DEMO |  | 2026-04-01 | 2026-06-26 | 2026-03-09 | 2026-04-08 | 5500 | N |  | N |  |  |  | N/A |  | 5500 | N/A | Y | Clear Title | Clear — in hand | Full Demo | ISSUE #; Mark
36 | Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 87 | BELL-87 | Mark | Mark | Complete | 16620 | FULL DEMO |  | 2026-04-01 | 2026-06-26 | 2026-03-09 | 2026-04-08 | 5500 | N |  | N |  |  |  | N/A |  | 5500 | N/A | Y | Clear Title | Clear — in hand | Full Demo | Mark
| Belle Haven 27554 US Hwy 19 N Clearwater Fl 33761 | 71 |  |  |  |  | 16554
37 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 12 | BRUN-12 | Mark | Mark | In Progress | 16806 | L2+ |  | 2026-09-14 | 2026-08-25 | [9 empty] | N |  | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
38 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 20 | BRUN-20 | Mark | Mark | In Progress | 16807 | L2+ |  | 2026-09-14 | 2026-07-31 | [9 empty] | Y |  | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
39 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 23 | BRUN-23 Rachel | Mark | Mark | In Progress | 16809 | L1+ |  | 2026-09-14 | 2026-07-31 | [9 empty] | N |  | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
40 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 28 | BRUN-28 | Unmarked | Mark | In Progress | 16808 | L2 |  | 2026-09-14 | 2026-07-31 | [9 empty] | Y |  | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
41 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 42 | BRUN-42 | Mark | Mark | In Progress | 16907 | L2+ |  | 2026-09-14 | 2026-07-31 | [9 empty] | Y |  | 0 | N | Y | Clear Title | Clear — in hand |  | ISSUE #; Mark
42 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 701 | BRUN-701 | Mark | Mark | In Progress | 16805 | L3 |  | 2026-09-14 | 2026-07-31 | [9 empty] | N |  | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
170 | Brunswick 221 Robarts Rd Brunswick Ga 31520 | 38 | BRUN-38 | Mark | Mark | In Progress | 16926 | L2+ |  | 2026-09-14 | 2026-07-31 | [9 empty] | Y |  | 0 | N | N
43 | Central 810 Peachtree St Cocoa Fl 32922 | C015 | CENT-C15 | Mark | Mark | Complete | 16612 | L2 |  | 2026-06-01 |  | 2026-06-01 | 2026-06-09 | 12374 | [6 empty] | N |  | 12374 | N/A | Y | No Title | START missing-title (Melanie) | Wall and Ceiling repair, Slider repair ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program, invoice 50146 $8,873.60. Base scope: cleanout, power wash exterior siding/skirting/stairs, broom-clean; level-based interior remodel (floors, walls, cabinets, fixtures, ceilings, windows, electrical). Itemized detail image-only. | Mark; Melanie
44 | Crystal Acres 2850 N Crede Ave Crystal River Fl 34428 | 1 | CA-1 | Mark | Mark | Cleaned | 16812 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
45 | Crystal Acres 2850 N Crede Ave Crystal River Fl 34428 | 25 | CA-25 | Mark | Mark | Cleaned | 16814 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
46 | Crystal Acres 2850 N Crede Ave Crystal River Fl 34428 | 34 | CA-34 | Mark | Mark | Cleaned | 16813 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y | Copy of Title (Our Name) | START missing-title (Melanie) |  | Mark; Melanie
47 | Crystal Acres 2850 N Crede Ave Crystal River Fl 34428 | 35 | CA-35 | Mark | Mark | Cleaned | 16573 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
48 | Crystal Acres 2850 N Crede Ave Crystal River Fl 34428 | 37 | CA-37 | Mark | Mark | Cleaned | 16810 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y | Copy of Title (Sellers Name) | START missing-title (Melanie) |  | Mark; Melanie
49 | Crystal Acres 2850 N Crede Ave Crystal River Fl 34428 | 49 | CA-49 | Mark | Mark | Cleaned | 16811 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
50 | Druid Oaks 4240 Hwy 17 Brunswick Ga 31525 | 57 | DO-57 | Mark | Mark | In Progress | 16815 | L2 |  | 2026-06-29 | 2026-07-31 | [9 empty] | Y |  | 0 | N | Y | FFT Sent to DMV | In process — track |  | Mark
| Druid Oaks 4240 Hwy 17 Brunswick Ga 31525 | 44 |  |  |  |  | 16966 | [15 empty] | 0
51 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 103 | FOX-103 | Siding | Alt | Complete | 16517 | NA |  | N/A |  | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N/A | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek refurb to rent-ready by Jams + Stark (base $9,000). Standard scope: pressure wash, skirting/window repair, carpet demo, paint, door/ceiling/wall repairs, cabinet/sink clean, new lights and smoke detectors, LVT throughout, professional clean. Folder marked COMPLETED. | Mark | 13072
52 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 121 | FOX-121 | Siding | Alt | Complete | 16525 | NA |  | 2026-07-20 | 2026-08-31 | 2026-09-07 |  |  | N |  | N |  | N |  | Y |  | 0 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek refurb to rent-ready by Jams + Stark (base $9,000). Standard scope: pressure wash, skirting/window repair, carpet demo, paint, door/ceiling/wall repairs, cabinet/sink clean, new lights and smoke detectors, LVT throughout, professional clean. Folder marked COMPLETED. | Mark | 13263
53 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 132 | FOX-132 | Mark | Mark | In Progress | 16821 | L2 |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [8 empty] | Y |  | 0 | N | Y | Sent to FTT | In process — track | L2 = Typical, some drywall and ceiling repair needed. Minor cabinet fixes. Unit Needs siding and stairs. | Mark
54 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 27 | FOX-27 | Siding | Alt | Complete | 16521 | NA |  | NA | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Refurb to rent-ready by Jams + Stark; base $9,000 + change order $4,700 = $13,700 total (per closeout). Base scope: pressure wash home and decks, repair/reform skirting and holes, repair side windows; interior carpet demo, prep/paint paneling/walls/trim, repair bedroom doors/holes/knobs, repair and paint ceiling holes, clean/repair bathroom sink, repair/replace countertop ends, clean cabinets; new light fixtures/bulbs and smoke detectors; LVT throughout; professional clean. Change Order #1: extensive demo (full home of furniture + shed + 3 extra dumpsters), 275 sq ft flooring/structural repair in guest & master bedrooms, repair holes behind wall coverings, bathroom wall + plumbing repairs, door replacement, general plumbing/leak repairs, new tub faucet and waterlines. | Mark | 13269
55 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 32 | FOX-32 | Siding | Alt | Complete | 16522 | NA |  | NA | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Standard Fox Creek refurb to rent-ready by Jams + Stark (base $9,000). Scope per template: pressure wash home/decks, repair skirting and side windows, carpet demo, prep/paint paneling/walls/trim, repair doors/holes/knobs, repair/paint ceiling holes, clean/repair bathroom sink and countertop ends, clean cabinets, new light fixtures/bulbs and smoke detectors, matching LVT throughout, professional clean. Folder marked COMPLETED. | Mark | 13257
56 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 35 | FOX-35 | Siding | Alt | Complete | 16549 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek refurb to rent-ready by Jams + Stark (base $9,000); kickoff notes exterior emphasis. Standard scope: pressure wash, skirting/window repair, carpet demo, paint, door/ceiling/wall repairs, cabinet/sink clean, new lights and smoke detectors, LVT throughout, professional clean. Folder marked COMPLETED. | Mark | 13271
57 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 38 | FOX-38 | Mark | Mark | Not Started | 16818 | NA |  | N/A |  | 2026-09-07 | [10 empty] | 0 | N | N/A | Sent to FTT | In process — track |  | Mark
58 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 39 | FOX-39 | Siding | Alt | Complete | 16544 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek refurb to rent-ready by Jams + Stark (base $9,000); kickoff cites exterior repair needs. Standard scope: pressure wash, skirting/window repair, carpet demo, paint, door/ceiling/wall repairs, cabinet/sink clean, new lights and smoke detectors, LVT throughout, professional clean. Folder marked COMPLETED. | Mark | 13273
59 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 4 | FOX-4 | Mark | Mark | Not Started | 16816 | NA |  | N/A |  | 2026-09-07 | [10 empty] | 0 | N | N/A | Sent to FTT | In process — track |  | Mark
60 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 42 | FOX-42 | Siding | Alt | Complete | 16523 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [10 empty] | 0 | N | N | Sent to FTT | In process — track |  | Mark
61 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 45 | FOX-45 | Siding | Alt | Complete | 16633 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Comprehensive interior/exterior refurb to rent-ready by Jams + Stark (billed $9,000, invoice 1229, WIP 16633). Exterior: pressure wash home and decks, repair skirting (bend back, patch holes), repair side windows. Interior: demo/remove carpet, prep and paint paneling/interior walls/trim, repair bedroom doors/holes/knobs, repair and paint ceiling holes, clean/repair bathroom sink, repair/replace countertop ends, clean cabinets. Electrical/safety: new light fixtures and bulbs, new smoke detectors. Finishes: matching LVT flooring throughout. Professional rent-ready cleaning. Roofing repairs not in estimate; no major plumbing/HVAC. | Mark | 13261
62 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 50 | FOX-50 | Mark | Mark | Not Started | 16823 | SOLD |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [10 empty] | 0 | N | N | Sent to FTT | In process — track |  | Mark
63 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 57 | FOX-57 | Mark | Mark | In Progress | 16825 | L2 |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [8 empty] | Y |  | 0 | N | Y | Sent to FTT | In process — track | L2 = Typical. Drywall and Ceiling need attention. Stairs also. Unit needs siding. | Mark
64 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 6 | FOX-6 | Siding | Alt | Complete | 16519 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [10 empty] | 0 | N | N | Sent to FTT | In process — track |  | Mark
65 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 60 | FOX-60 | Siding | Alt | Complete | 16545 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | N |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek rehab (Jams + Stark, base $9,000 per program). No standalone kickoff or invoice located in this pass; carried from prior tracker. Scope presumed standard Fox Creek refurb template (pressure wash, skirting/window repair, demo, paint, LVT, lighting, smoke detectors). | Mark | 13275
66 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 64 | FOX-64 | Mark | Mark | In Progress | 16819 | L2+ |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [8 empty] | Y |  | 0 | N | Y | Sent to FTT | In process — track | drainage issue under the home Typical. Needs more extensive cabinet and drywall repair, wet sub floor replacement. Unit needs siding | Mark
67 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 74 | FOX-74 | Siding | Alt | Complete | 16524 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek refurb to rent-ready by Jams + Stark (base $9,000). Standard scope: pressure wash, skirting/window repair, carpet demo, paint paneling/walls/trim, door/ceiling/wall repairs, cabinet/sink clean, new lights and smoke detectors, LVT throughout, professional clean. Folder marked COMPLETED. | Mark | 13277
68 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 82 | FOX-82 | Mark | Mark | In Progress | 16817 | L2 |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [8 empty] | Y |  | 0 | N | Y | Sent to FTT | In process — track | 82 - L2 = Typical and needs drywall and ceiling and cabinet repair. Unit needs siding | Mark
69 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 83 | FOX-83 | Mark | Mark | In Progress | 16824 | L2+ |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [8 empty] | Y |  | 0 | N | Y | Sent to FTT | In process — track | L2+ = Typical, and needs sub floor and drywall ceiling work. Unit needs siding. | Mark
70 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 88 | FOX-88 | Siding | Alt | Complete | 16550 | NA |  | 2026-08-31 | 2026-08-31 | 2026-09-07 |  | 9000 | N |  | N |  | N |  | Y |  | 9000 | N | N | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek refurb to rent-ready by Jams + Stark (billed $9,000, invoice 1223-2). Standard scope: pressure wash home/decks, repair skirting and side windows, carpet demo, prep/paint paneling/walls/trim, repair doors/holes/knobs, repair/paint ceiling holes, clean/repair bathroom sink and countertop ends, clean cabinets, new light fixtures/bulbs and smoke detectors, matching LVT throughout, professional clean. | Mark | 13471
71 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 9 | FOX-9 | Siding | Alt | Complete | 16520 | NA |  | NA |  | 2026-09-07 | [10 empty] | 0 | N | N/A | Sent to FTT | In process — track |  | Mark
72 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 90 | FOX-90 | Siding | Alt | Complete | 16527 | NA |  | NA |  | 2026-09-07 |  | 9000 | N |  | N |  | N |  | N |  | 9000 | N | N/A | Sent to FTT | In process — track | [CAPEX docs] Vendor: Jams + Stark LLC. Fox Creek rehab (Jams + Stark, base $9,000 per program). No standalone kickoff/invoice located this pass; carried from prior tracker. Scope presumed standard Fox Creek refurb template. | ISSUE #; Mark | 11634
73 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 94 | FOX-94 | Mark | Mark | Not Started | 16820 | NA |  | NA |  | 2026-09-07 | [10 empty] | 0 | N | N/A | Sent to FTT | In process — track |  | Mark
74 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 98 | FOX-98 | Mark | Mark | In Progress | 16822 | L3 |  | 2026-08-31 | 2026-08-31 | 2026-09-07 | [8 empty] | Y |  | 0 | N | Y | Sent to FTT | In process — track | L3 = Extensive interior demo and replacement in bathrooms and kitchen. Subfloor and drywall replacement. Not a full gut but close. Needs siding. | Mark
165 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 77 | FOX-77 | Mark | Mark | In Progress | 16927 |  |  | 2026-08-31 |  | 2026-09-07 | [8 empty] | Y |  | 0 | N | N
166 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 58 | FOX-58 | Mark | Mark | In Progress | 16928 |  |  | 2026-08-31 |  | 2026-09-07 | [8 empty] | Y |  | 0 | N | N
167 | Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 37 | FOX-37 | Mark | Mark | In Progress | 16929 |  |  | 2026-08-31 |  | 2026-09-07 | [8 empty] | Y |  | 0 | N | N
75 | Great Oak 4440 Yowell Rd Kissimmee Fl 34746 | AA | GO-AA | Unmarked | Mark | Not Started | 16826 |  |  | 2026-09-15 |  | 2026-09-07 | [10 empty] | 0 | N | N | No Title | START missing-title (Melanie) |  | Mark; Melanie
76 | Gulf Breeze 7530 Maryland Ave Hudson Fl 34667 | 12 | GULFPO-12 | Mark | Mark | Complete | 16827 | NA |  | NA | [12 empty] | 0 | N | N |  | START missing-title (Melanie) |  | Mark; Melanie
77 | Gulf Breeze 7530 Maryland Ave Hudson Fl 34667 | 20 | GULFPO-20 | Mark | Mark | Complete | 16589 | NA |  | NA | [12 empty] | 0 | N | MVD-LCKY 35 | Clear Title | Clear — in hand |  | Mark
78 | Gulf Breeze 7530 Maryland Ave Hudson Fl 34667 | 21 | GULFPO-21 | Mark | Mark | Complete | 16590 | NA |  | NA | [12 empty] | 0 | N | MVD SSH 284 |  | START missing-title (Melanie) |  | Mark; Melanie
79 | Gulf Breeze 7530 Maryland Ave Hudson Fl 34667 | 28 | GULFPO-28 | Mark | Mark | Complete | 16848 | To Be Assessed |  | NA | [12 empty] | 0 | N | N |  | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
| Gulf Breeze 7530 Maryland Ave Hudson Fl 34667 | 4 |  |  |  |  | 16979 | To Be Assessed
80 | Harbour 821 Peachtree St Cocoa Fl 32922 | B13 | HARB-B-13 | Unmarked | Mark | Not Started | 16828 |  |  | 2026-07-13 | 2026-07-31 | [11 empty] | 0 | N | N | No Title | START missing-title (Melanie) |  | Mark; Melanie
81 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 13 | HSMHC-13 | Mark | Mark | Cleaned | 16578 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
82 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 14 | HSMHC-14 | Mark | Mark | NA | 16577 | Full Gut Remodel |  | 2026-07-31 | 2026-09-15 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
83 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 18 | HSMHC-18 | Mark | Mark | Cleaned | 16898 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | N |  | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
84 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 19 | HSMHC-19 | Mark | Mark | Cleaned | 16580 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
85 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 20 | HSMHC-20 | Mark | Mark | Cleaned | 16576 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
86 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 8 | HSMHC-8 | Mark | Mark | Cleaned | 16579 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
87 | Hunter Springs 316 NE 2nd St Crystal River Fl 34429 | 9 | HSMHC-9 | Mark | Mark | Cleaned | 16581 | Full Gut Remodel |  | 2026-07-31 | 2026-08-31 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
88 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 15 | LWPO-15 | Mark | Mark | In Progress | 16849 | L2 |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | N |  | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
89 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 16 | LWPO-16 | Mark | Mark | In Progress | 16674 | L3 |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
90 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 19 | LWPO-19 | Mark | Mark | In Progress | 16588 | L2+ |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
91 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 29 | LWPO-29 | Mark | Mark | In Progress | 16582 | L1 |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
92 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 30 | LWPO-30 | Mark | Mark | In Progress | 16587 | L3 |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
93 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 32 | LWPO-32 | Mark | Mark | In Progress | 16586 | Full Gut Remodel |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | ISSUE #; Mark
94 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 40 | LWPO-40 | Mark | Mark | In Progress | 16585 | L3 |  | 2026-09-21 | 2026-10-23 | [11 empty] | 0 | N | Y | Copy of Title (Our Name) | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
95 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 55 | LWPO-55 | Mark | Mark | In Progress | 16584 | L3 |  | 2026-09-21 | 2026-08-31 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
96 | Lake Wales 705 N Scenic Hwy Lake Wales Fl 33853 | 60 | LWPO-60 | Mark | Mark | In Progress | 16583 | L2+ |  | 2026-09-21 | 2026-08-31 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | ISSUE #; Mark
97 | Lucky Clover 635 E Eau Gallie Blvd Melbourne Fl 32937 | 2 | LUCK-2 | Mark | Mark | Not Started | 16610 | L3+ |  | 2026-07-21 | 2026-08-03 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand | Full Get Remodel or Demo | Mark
98 | Lucky Clover 635 E Eau Gallie Blvd Melbourne Fl 32937 | 35 | LUCK-35 | Mark | Mark | Not Started | 16829 | To Be Assessed |  | 2026-08-31 | 2026-08-03 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
| Northgate 3304 3rd Ave Mims | 3304 3rd Ave |  |  |  |  | 16980
99 | Ocean Air 1311 Turnbull St New Smyrna Beach Fl 32168 | 13 | OCEAN-13 | Mark | Mark | Not Started | 16899 | NA |  | 2026-08-03 | 2026-08-28 | [11 empty] | 0 | N | N | Clear Title | Clear — in hand |  | ISSUE #; Mark
100 | Ocean Air 1311 Turnbull St New Smyrna Beach Fl 32168 | 71 | OCEANPO-71 | Mark | Mark | Not Started | 16831 | To Be Assessed |  | 2026-09-01 | 2026-08-28 | [11 empty] | 0 | N | N | Clear Title | Clear — in hand |  | Mark
101 | Ocean Air 1311 Turnbull St New Smyrna Beach Fl 32168 | 84 | OCEANPO-84 | Mark | Mark | Not Started | 16830 | To Be Assessed |  | 2026-09-01 | 2026-08-28 | [11 empty] | 0 | N | N |  | START missing-title (Melanie) |  | Mark; Melanie
160 | Ocean Air 1311 Turnbull St New Smyrna Beach Fl 32168 | 95 | Ocean - 95 | Mark | Mark | Not Started | 16908 | To Be Assessed |  | 2026-09-01 | [12 empty] | 0 | N | Y
102 | Palm Haven Estates 250 Nelle Ave Panama City Fl 32404 | 30 | PPH-30 | Mark | Mark | Not Started | 16900 | To Be Assessed |  | 2026-08-24 | 2026-07-21 | [11 empty] | 0 | N | Y | No Title | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
103 | Palm Haven Estates 250 Nelle Ave Panama City Fl 32404 | 4 | PPH-4 | Mark | Mark | Not Started | 16850 | NA |  | 2026-07-06 | 2026-07-21 | [11 empty] | 0 | N | N | Clear Title | Clear — in hand |  | Mark
104 | Palm Haven Estates 250 Nelle Ave Panama City Fl 32404 | 7 | PPH-7 | Mark | Mark | Not Started | 16851 | Full Gut Remodel |  | 2026-07-06 | 2026-07-21 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand | DEMO | Mark
105 | Palm Haven Estates 250 Nelle Ave Panama City Fl 32404 | K | PPH-K | Mark | Mark | Not Started | 16608 | NA |  | 2026-07-06 | 2026-07-21 | [11 empty] | 0 | N | N | Title Research | In process — track |  | Mark
106 | Palm Springs Estates 40110 US 19 N Tarpon Springs Fl 34689 | 2 | PSEPO-2 | Mark | Mark | Not Started | 16833 | To Be Assessed |  | 2026-07-22 | 2026-09-05 | [11 empty] | 0 | N | N | Clear Title | Clear — in hand |  | Mark
107 | Palm Springs Estates 40110 US 19 N Tarpon Springs Fl 34689 | 24 | PSEPO-24 | Mark | Mark | Not Started | 16832 | To Be Assessed |  | 2026-07-22 | 2026-09-05 | [11 empty] | 0 | N | N | Clear Title | Clear — in hand |  | Mark
108 | Palm Springs Estates 40110 US 19 N Tarpon Springs Fl 34689 | 7 | PSEPO-7 | Mark | Mark | Not Started | 16851 | To Be Assessed |  | 2026-07-22 | 2026-09-05 | [11 empty] | 0 | N | N |  | START missing-title (Melanie) |  | ISSUE #; Mark; Melanie
109 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 10 | PARK-10 | Mark | Mark | In Progress | 16837 | L2 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L2 = Typical plus some sub floor and wall repair / drywall replacement. Needs siding. | Mark
110 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 14 | PARK-14 | Mark | Mark | In Progress | 16844 | L1+ |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L1+ = Typical, but some floor demo from old work and sub repair. Needs new stairs and deck, needs siding. | Mark
111 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 39 | PARK-39 | Mark | Mark | In Progress | 16840 | L2 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L2 = Typical, needs some interior wall repair and floor repair structurally. Cabinets good, needs siding and stairs. | Mark
112 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 42 | PARK-42 | Mark | Mark | In Progress | 16845 | PLZ ADVISE |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [10 empty] | 0 | N | Y | Pending Transfer (MHTR) | In process — track | Looks like someone has been in here to work, however it is incomplete. Ceiling not painted, cabinets and flooring are not new or cleaned, paint is splattered on floor. Please advise what you want me doing here. If rehab this is a Level 1 | Mark
113 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 49 | PARK-49 | Mark | Mark | In Progress | 16839 | L1+ |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L1+ = Typical but needs new stairs and decks, some more extensive cabinet repair. Needs siding. | Mark
114 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 51 | PARK-51 | Mark | Mark | In Progress | 16842 | L1 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L1 = Typical, but needs some stair work. Needs siding. | Mark
115 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 60 | PARK-60 | Mark | Mark | In Progress | 16841 | PLZ ADVISE |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [10 empty] | 0 | N | Y | Pending Transfer (MHTR) | In process — track | Please advise same as lot 42. Would be level 1 | Mark
116 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 7 | PARK-7 | Mark | Mark | In Progress | 16835 | L2 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L2 = Typical, some drywall replacement and some subfloor replacement. Unit needs siding. | Mark
117 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 71 | PARK-71 | Mark | Mark | In Progress | 16834 | L1 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | N |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L1 = Typical and does not need siding | Mark
118 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 75 | PARK-75 | Mark | Mark | In Progress | 16846 | L2 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | N |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | - L2 = Typical but needs extensive cabinet repair. Does not need siding | Mark
119 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 81 | PARK-81 | Mark | Mark | In Progress | 16847 | L2 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L2 = Typical but needs wall and cabinet repair, some sub floor. Unit needs siding | Mark
120 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 82 | PARK-82 | Mark | Mark | In Progress | 16836 | L1 |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | N |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L1 = Typical and does not need siding | Mark
121 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 88 | PARK-88 | Mark | Mark | In Progress | 16843 | L2+ |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | [8 empty] | Y |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L2+ = Typical but needs subfloor replacement, drywall replacement, cabinet repair. Unit needs siding | Mark
122 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 89 | PARK-89 | Mark | Mark | In Progress | 16838 | L1+ |  | 2026-08-31 | 2026-08-27 | 2026-09-29 | [8 empty] | N |  | 0 | N | Y | Pending Transfer (MHTR) | In process — track | L1+ - Typical with some sub floor replacement needed. Does not need siding. | Mark
162 | Parkwood 3118 Dudley Rd West Columbia SC 29170 | 44 | PARK-44 | Mark | Mark | In Progress | 16930 | L2 |  | 2026-08-31 |  | 2026-09-02 | [8 empty] | Y |  | 0 | N | N
| Parkwood 3118 Dudley Rd West Columbia SC 29170 | 66 |  |  |  |  | 16967 |  |  | 2026-08-31 |  | 2026-09-02 | [10 empty] | 0 | N | N
| Parkwood 3118 Dudley Rd West Columbia SC 29170 | 87 |  |  |  |  | 16968 |  |  | 2026-08-31 |  | 2026-09-02 | [10 empty] | 0 | N | N
123 | Riverwalk 8518 Gibsonton Dr Gibsonton Fl 33534 | 163 | RW-163 | Mark | Mark | Not Started | 16982 | To Be Assessed |  | 2026-07-17 | 2026-08-31 | [11 empty] | 0 | N | N | Pending Transfer (MHTR) | In process — track |  | ISSUE #; Mark
124 | Riverwalk 8518 Gibsonton Dr Gibsonton Fl 33534 | 63 | RW-63 | Mark | Mark | Not Started | 16853 | To Be Assessed |  | 2026-07-17 | 2026-08-31 | [11 empty] | 0 | N | N | Pending Transfer (MHTR) | In process — track |  | Mark
| Riverwalk 8518 Gibsonton Dr Gibsonton Fl 33534 | 35 |  |  |  |  | 16981
125 | Royal Oaks 8125 US 1 Hwy Vero Beach Fl 32970 | 22 | ROYAL-22 | Mark | Mark | Not Started | 16574 | NA |  | 2026-07-06 | 2026-08-20 | [11 empty] | 0 | N | MVD - SU16 | No Title | START missing-title (Melanie) |  | Mark; Melanie
168 | Royal Oaks 8125 US 1 Hwy Vero Beach Fl 32970 | 14 | ROYAL-14 | Mark | Mark | Not Started | 16931 | To Be Assessed | [14 empty] | 0 |  | N
126 | Sea Shells 51 Hitching Post Rd Cape Canaveral Fl 32724 | 284 | SS-284-v1 | Mark | Mark | Not Started | 16858 | To Be Assessed |  | 2026-08-03 | 2026-08-20 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
127 | Shady Acres 54 Holtz Rd Brunswick Ga 31523 | 180 | SA-180 | Mark | Mark | In Progress | 16856 | L1+ |  | 2026-06-30 | 2026-08-14 | [9 empty] | Y |  | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
128 | Shady Acres 54 Holtz Rd Brunswick Ga 31523 | 214 | SA-214 | Mark | Mark | In Progress | 16854 | L2 |  | 2026-06-30 | 2026-08-14 | [9 empty] | Y |  | 0 | N | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
129 | Shady Acres 54 Holtz Rd Brunswick Ga 31523 | 35 | SA-35 | Mark | Mark | In Progress | 16855 | L1+ |  | 2026-06-30 | 2026-08-14 | [9 empty] | Y |  | 0 | N | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
130 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 10 | SILVER-10 | Mark | Mark | In Progress | 16759 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
131 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 20 | SILVER-20 | Mark | Mark | Completed | 16761 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-07-01 | 2026-08-31 | 20222 | Y | 3200 | Y | 1950 | N |  | Y | 4900 | 30272 | Y | Y | No Title | START missing-title (Melanie) | Add skirting for $1,500.00 included in total | Mark; Melanie
132 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 21 | SILVER-21 | Mark | Mark | Completed | 16762 | Full Gut Remodel |  | 2026-05-11 | 2026-07-24 | 2026-06-15 | 2026-07-02 | 18232.4 | Y | 1600 | Y | 1950 | Y | 1500 | Y | 4900 | 28182.4 | Y | Y | Clear Title | Clear — in hand | Add skirting for $1,500.00 included in total | Mark
133 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 23 | SILVER-23 | Mark | Mark | In Progress | 16772 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
134 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 30 | SILVER-30 | Mark | Mark | In Progress | 16756 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
135 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 31 | SILVER-31 | Mark | Mark | In Progress | 16757 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
136 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 35 | SILVER-35 | Mark | Mark | In Progress | 16755 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
137 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 37 | SILVER-37 | Mark | Mark | In Progress | 16752 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
138 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 38 | SILVER-38 | Mark | Mark | In Progress | 16750 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
139 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 42 | SILVER-42 | Mark | Mark | In Progress | 16753 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | No Title | START missing-title (Melanie) |  | Mark; Melanie
140 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 5 | SILVER-5 | Mark | Mark | Completed | 16758 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-07-01 | 2026-08-31 | 19554 | Y | 3200 | Y | 1950 | N |  | Y | 4900 | 29604 | Y | Y | No Title | START missing-title (Melanie) | Add skirting for $1,500.00 included in total | Mark; Melanie
141 | Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 8 | SILVER-8 | Mark | Mark | In Progress | 16754 | Full Gut Remodel |  | 2026-05-11 | 2026-08-28 | 2026-05-11 | [8 empty] | Y |  | 0 | Y | Y | Clear Title | Clear — in hand |  | Mark
| Silver Breeze 925 Cheney Hwy Titusville Fl 32780 | 11 |  | Mark | Mark | Completed | 16866 | Full Gut Remodel |  |  |  | 2026-07-01 | 2026-08-31 | 18219.9 | Y | 3200 | Y | 1950 | N |  | y | 4900 | 28269.9 |  |  |  |  | Add skirting for $1,500.00 included in total
142 | Silver Hill 3615 Percival Rd Columbia Sc 29223 | 110 | SH-110 | Mark | Mark | In Progress | 16857 | L1+ |  | 2026-07-20 | 2026-08-31 | 2026-09-01 | [10 empty] | 0 | N | N | Clear Title | Clear — in hand |  | Mark
163 | Silver Hill 3615 Percival Rd Columbia Sc 29223 | 73 | SH-73 | Mark | Mark | In Progress | 16932 | L1+ |  | 2026-08-01 |  | 2026-09-01 | [10 empty] | 0 | N | N
143 | Southgate 8817 N Atlantic Ave Cape Canaveral Fl 32920 | 86 | SOUTH-86 | Mark | Mark | In Progress | 16607 | L2-3 |  | 2026-07-13 | 2026-07-29 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand | Countertops, Sub Floor, Walls | Mark
144 | Su-Rene 810 8th St Vero Beach Fl 32962 | 16 | SUR-16 | Mark | Mark | Not Started | 16859 | To Be Assessed |  | 2026-07-20 | 2026-09-03 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
145 | Su-Rene 810 8th St Vero Beach Fl 32962 | 43 | SUR-43 | Mark | Mark | Not Started | 16596 | To Be Assessed |  | 2026-07-20 | 2026-09-03 | [11 empty] | 0 | N | Y | Clear Title | Clear — in hand |  | Mark
164 | Su-Rene 810 8th St Vero Beach Fl 32962 | 79 | SUR-79 | Mark | Mark | Not Started | 16933 | To Be Assessed | [14 empty] | 0 | N | N
169 | Su-Rene 810 8th St Vero Beach Fl 32962 | 71 | SUR-71 | Mark | Mark | Not Started | 16934 | To Be Assessed | [14 empty] | 0 | N | N
| Terrace Crossing 9901 E Fowler Ave Thonotosassa Fl 33592 | E9 |  |  | Mark | In Progress | 16969 | L2+ |  | 2026-08-24 |  | 2026-08-28 | [10 empty] | 0 | N | N |  |  | Roof repair, ceiling repair, sub floor repair
146 | Terrace Crossing 9901 E Fowler Ave Thonotosassa Fl 33592 | A11 | TC-A-11 | Mark | Mark | Not Started | 16595 | NA | [14 empty] | 0 | N | MVD-TRW APT1 | Pending Transfer (MHTR) | In process — track |  | Mark
147 | Terrace Crossing 9901 E Fowler Ave Thonotosassa Fl 33592 | B4 | TC-B-4 | Mark | Mark | Not Started | 16860 | NA | [14 empty] | 0 | N | N | Pending Transfer (MHTR) | In process — track |  | Mark
148 | The Oaks 10321 Main St Thonotosassa Fl 33592 | 123 | TO-123 | Mark | Mark | Complete | 16594 | NA | [14 empty] | 0 | N | MVD - OA 95 | Pending Transfer (MHTR) | In process — track |  | Mark
172 | The Oaks 10321 Main St Thonotosassa Fl 33592 | B1 | TO-B1 | Mark | Mark | In Progress | 16935 | L1+ |  | 2026-08-24 |  | 2026-08-28 | [10 empty] | 0 | N | N
173 | The Oaks 10321 Main St Thonotosassa Fl 33592 | 22 | TO-22 | Mark | Mark | In Progress | 16936 | L1+ |  | 2026-08-24 |  | 2026-08-28 | [10 empty] | 0 | N | N |  |  | Minor Sub Floor
| The Oaks 10321 Main St Thonotosassa Fl 33592 | 32 |  |  |  | In Progress | 16982 | L2 |  |  |  | 2026-08-28 | [15 empty] | Large House, sub floor , new stairs, bathroom vanities
149 | Tradewinds 4100 N Cocoa Blvd Cocoa Fl 32927 | 30 Olsen | TRADE-30Olsen | Mark | Mark | Not Started | 16606 | L3+ |  | 2026-07-20 | 2026-09-03 | [9 empty] | N |  | 0 | N | Y | Clear Title | Clear — in hand | Full Gut Remodel | Mark
150 | Tradewinds 4100 N Cocoa Blvd Cocoa Fl 32927 | Apt 1 | TRADE-APT 1 | Mark | Mark | Not Started | 16861 | To Be Assessed |  | 2026-07-20 | 2026-09-03 | [11 empty] | 0 | N | Y |  | START missing-title (Melanie) |  | Mark; Melanie
151 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 353 Daisy | WPMH-353 Daisy | Mark | Mark | Complete | 16722 | L3 |  |  |  | 2026-04-02 | 2026-05-29 | 17542 | [6 empty] | Y | 4900 | 22442 | N | Y | Clear Title | Clear — in hand | [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16722), final invoice $14,042.00. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Itemized detail image-only. | Mark
152 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 354 Daisy | WPMH-354 Daisy | Mark | Mark | Complete | 16600 | L1 |  |  |  | 2026-04-02 | 2026-05-29 | 13125 | [6 empty] | Y | 4900 | 18025 | N | Y | Clear Title | Clear — in hand |  | Mark
153 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 358 Lily | WPMH-358 Lily | Mark | Mark | Complete | 16603 | L1 |  |  |  | 2026-04-02 | 2026-05-29 | 10037 | [6 empty] | N |  | 10037 | N | Y | Clear Title | Clear — in hand | Some Sub Floor | Mark
154 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 359 Daisy | WPMH-359 Daisy | Mark | Mark | Complete | 16602 | L2-3 |  |  |  | 2026-04-02 | 2026-05-29 | 18523 | [6 empty] | Y | 4900 | 23423 | Y | Y | Clear Title | Clear — in hand | Ceiling, Sub Floor, Replace counter & Cab rep ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program, invoice 50219 $15,023.18 (GL# 16600, 16601, 16602, 16603). Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Itemized detail image-only. | Mark
155 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 4700 Periwinkle | WPMH-4700 Periwinkle | Mark | Mark | Complete | 16601 | L2-3 |  |  |  | 2026-04-02 | 2026-05-29 | 13152 | [6 empty] | Y | 4900 | 18052 | Y | Y | No Title | START missing-title (Melanie) | Sub Floor Replace, Closet Doors | Mark; Melanie
156 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 4885 Clover | WPMH-4885 Clover | Mark | Mark | Complete | 16604 | L3 |  |  |  | 2026-04-02 | 2026-05-29 | 22919 |  |  |  |  | Y | 2500 | Y | 4900 | 30319 | Y | Y | No Title | START missing-title (Melanie) | Demo non permit structure and Gut , full sub floors ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program. Two invoices total $28,999.00: final rehab $21,919.00 (GL# 16604) + additional invoice 50144 $7,080.00 (GL# 16605). Base scope: cleanout, power wash exterior siding/skirting/stairs, broom-clean; level-based interior remodel (floors, walls, cabinets, kitchen/bath fixtures, ceilings, windows, electrical). Also part of the Whispering Pines exterior siding bundle. Itemized detail image-only. | Mark; Melanie
157 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 4925 Clover | WPMH-4925Clover | Mark | Mark | Complete | 16605 | L3+ |  |  |  | 2026-04-02 | 2026-05-29 | 16840 | [6 empty] | Y | 4900 | 21740 | Y | Y | No Title | START missing-title (Melanie) | Full Gut Remodel ¦ [CAPEX docs] High Pace Construction rehab under All-Florida program (GL# 16605), final invoice $13,239.60. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Also part of Whispering Pines siding bundle. Itemized detail image-only. | Mark; Melanie
158 | Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 5085 Clover | WPMH-5085 Clover | Mark | Mark | Complete | 16723 | L3+ |  |  |  | 2026-04-02 | 2026-05-29 | 24244 | [6 empty] | Y | 4900 | 29144 | Y | Y | Clear Title | Clear — in hand | [CAPEX docs] High Pace Construction rehab under All-Florida program, final invoice $20,144.40. Filed against multiple GLs (16604, 16605, 16616, 16618, 16622, 16625, 16722, 16723) — this document also appears to recap the broader final-invoice bundle. Base scope: cleanout, power wash exterior, broom-clean; level-based interior remodel. Itemized detail image-only. | Mark
| Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 4770 Periwinkle |  |  |  |  | 16983
| Whispering Pines 359 Cheney Hwy Titusville Fl 32780 | 366 Lily |  |  |  |  | 16984
159 | Windward Knoll 12415 Thonotosassa Rd Thonotosassa Fl 33592 | 102 | WIND-102 | Mark | Mark | In Progress | 16593 | Full Remodel |  | 2026-08-24 | 2026-09-13 | 2026-08-28 | [10 empty] | 0 | N | Y | Pending Transfer (MHTR) | In process — track | Full House Remodel | Mark
| Riverwalk 8518 Gibsonton Dr Gibsonton Fl 33534 | 171
| The Oaks 10321 Main St Thonotosassa Fl 33592 | 49
| Fox Creek 491 Chapman Rd Foundain Inn SC 29644 | 24

## Alt Vendor
Alt Vendor (John) — every magenta cell is yours. Teal cells were pre-filled from CAPEX/REHAB docs & invoices — verify. Lavender = Melanie titles.
# | Community | Lot | RM Asset | Track | Vendor | Rehab Status | GL # | Rehab Tier | Alt Vendor Name | Target Start | Target End | Actual Start | Actual End | Final Cost ($) | HVAC Y/N | Water Heater Y/N | Roof Y/N | Siding Y/N | Siding Deposit Y/N | Rehab Deposit Y/N | Title Status (RM) | Title Action (Melanie) | Scope / Notes | Needs From | ISSUE #
1 | Auburn Ridge | 132A | ARD-132A | Alt Vendor | Alt | Complete | 16497 |  | A New Day Construction | 2026-06-29 |  | 2025-11-21 | 2026-03-12 | 4274.25 | N | N | N | N |  | N |  | START missing-title (Melanie) | [CAPEX docs] Full unit rehab by A New Day Construction (multiple draws: deposit + $10,000 draw + $4,274.25 final). Filed under WIP# 16497. Detailed line items image-only; consistent with A New Day rehab scope (demolition, plywood/sheetrock repair, paint, LVP flooring, door/window trim, electrical fixtures, plumbing trim). | John Clark; Mark; Melanie | 12921
2 | Auburn Ridge | 136B | ARD-136B | Alt Vendor | Alt | Complete | 16495 |  | A New Day Construction | 2026-06-29 |  | 2025-12-15 | 2026-04-08 | 44306.66 | N | N | N | Y |  | N |  | START missing-title (Melanie) | [CAPEX docs] Full unit rehab by A New Day Construction with 7 draws/invoices summing to $44,306.66 (folder named '136B - Rehab - COMPLETE $44306.66'). Includes change-order work ($5,150 CO's) plus a metal railing invoice ($650). Detailed line items image-only; consistent with A New Day scope: demolition, structural/plywood and sheetrock repair, paint, LVP flooring, door/window/trim replacement, electrical fixtures, plumbing trim, and exterior stairs/railing. | John Clark; Mark; Melanie | 11552
3 | Auburn Ridge | 151A | ARD-151A | Alt Vendor | Alt | Complete | 16466 |  | A New Day Construction | 2026-06-29 |  | 2025-09-29 | 2025-11-19 | 47009.48 | N | N | Y | Y |  | N | Pending Transfer (MHTR) | In process — track | [CAPEX docs] Comprehensive gut remodel by A New Day Construction (est. $41,460; CO #1 +$3,800.40 for rot around window; final billed $47,009.48). Scope: systematic demolition of damaged plywood wall panels, interior/exterior doors, window sills, flooring, vanities and full rear exterior staircase/landing. Plumbing rough-in/trim for two new furniture-style vanities with chrome fixtures, reset existing toilet on new wax ring, reseal upstairs shower. Electrical: replace ceiling fans, flush-mount fixtures, upstairs bath exhaust fan/light combo, install five new flush-mount ceiling lights incl. stairwell. Replace ~6-7 sheets of sanded plywood, repair water-damaged walls, remediate upstairs bedroom roof leak. Replace all window casing/sills, baseboards, shoe molding, 3 exterior + 5 interior six-panel doors. Paint all interior walls/doors/trim (Agreeable Gray), paint lower kitchen cabinets white. LVP throughout upstairs/downstairs (allowance $3.25/SF, excludes staircase). Build new 5x5 back staircase/landing with PT lumber. Ceilings, appliance install, permits excluded. | John Clark; Mark | 9220
4 | Brunswick | 155 | BRUN-155 | Alt Vendor | Alt | Complete | 16461 |  | Primary Home Repair And Maintenance | 2026-07-06 |  | 2025-09-30 | 2026-04-06 | 96400 | N | N | N |  |  |  |  | START missing-title (Melanie) | [CAPEX docs] Window repair / primary remodel work covered jointly with 21 Gressel on a single $4,800 Primary Home Repair bid (job line reads '21 Gressel, 155 Robarts'). Bundled bid; per-home split not itemized. | John Clark; Mark; Melanie | 11611
5 | Brunswick | 203 | BRUN-203 | Alt Vendor | Alt | In Progress | 16465 |  |  | 2026-07-06 | 2026-08-20 | [8 empty] | N |  | START missing-title (Melanie) |  | John Clark; Mark; Melanie
6 | Brunswick | 21 | BRUN-21 | Alt Vendor | Alt | In Progress | 16462 |  | Primary Home Repair & Maintenance | 2026-07-06 | 2026-08-20 | 2025-09-29 | 2026-01-14 | 40300 | Y | N | Y | N |  | N |  | START missing-title (Melanie) | [CAPEX docs] Rehab/remodel of 21 Gressel (primary unit) by Primary Home Repair. Final invoice line items: 3 exterior flush-mount lights, living room fan, exterior/interior wiring reconfiguration (more damage found), 2 interior flush-mount lights, 5 exterior door lock replacements, plumbing ($2,800), back door railing, kitchen floor transition. A separate $4,800 window-repair bid (covering 21 Gressel + 155 Robarts) was issued as a change order. | John Clark; Mark; Melanie | 9159
7 | Brunswick | 37 | BRUN-37 | Alt Vendor | Alt | Not Started | 16541 |  | Jams + Stark LLC | 2026-07-06 | 2026-08-20 | 2025-12-23 |  | 10600 | N | N | N | N |  | N | Clear Title | Clear — in hand |  | John Clark; Mark | 11592
8 | Brunswick | 66 | BRUN-66 | Alt Vendor | Alt | Not Started | 16666 |  | Primary Home Repair And Maintenance | 2026-07-06 | 2026-08-20 | 2026-03-23 |  | 1950 | N | N | N | N |  | N | Clear Title | Clear — in hand |  | John Clark; Mark | 14749
9 | Brunswick | 8 | BRUN-8 | Alt Vendor | Alt | Not Started | 16642 | L1 | Primary Home Repair And Maintenance | 2026-07-06 | 2026-08-20 | 2026-02-17 |  | 11685 | N | N | N | N |  | N | Clear Title | Clear — in hand |  | John Clark; Mark | 12984
10 | Druid Oaks | 155 | DO-155 | Alt Vendor | Alt | Complete | 16543 |  | Jams + Stark LLC | 2026-07-06 |  | 2025-12-30 | 2026-05-21 | 15500 | N | N | N | Y |  | N | FFT Sent to DMV | In process — track | [CAPEX docs] Comprehensive rehab to rent-ready by Jams + Stark (est. $14,400; billed $15,500 via invoice 1232). Exterior: replace both steps, replace entire skirting, siding repairs and trim, install exterior lights. Interior: full demolition incl. old flooring, paint walls/trim with patching, clean cabinets, repair ceilings/drywall/wall surfaces, repair rotten main flooring areas. Install new LVT throughout ($4,000 of budget). Replace front door + jamb (with paint) and multiple broken windows. Four new smoke detectors + new lights/bulbs. Final cleaning. No major HVAC/plumbing/electrical beyond lighting; appliances not specified. | John Clark; Mark | 11626
11 | Druid Oaks | 22 | DO-22 | Alt Vendor | Alt | In Progress | 16641 | L1 | Primary Home Repair & Maintenance | 2026-07-06 | 2026-08-20 | 2026-06-06 |  | 6375 | N | N | N | N |  | N | FFT Sent to DMV | In process — track | [CAPEX docs] Remodel of 14.5ft x 57ft home. Exterior: pressure wash, repair siding and skirting, replace front and back steps. Interior: full cleanout, interior painting, sheetrock touch-ups. Flooring: install 900 sq ft new LVP (materials client-provided). Excludes hidden electrical/plumbing/water damage. | John Clark; Mark | 13872
12 | Druid Oaks | 41 | DO-41 | Alt Vendor | Alt | In Progress | 16640 | L1 | Primary Home Repair & Maintenance | 2026-07-06 | 2026-08-20 | 2026-06-06 |  | 1150 | N | N | N | N |  | N | FFT Sent to DMV | In process — track | [CAPEX docs] Small-scope rehab of 14.5ft x 57ft home (est. $1,150). Limited punch-list level work; detailed line items image-only. | John Clark; Mark | 13874
13 | Parkwood | 12 | PARK-12 | Alt Vendor | Alt | Complete | 16478 |  |  | 2026-07-13 | [9 empty] | N | Pending Transfer (MHTR) | In process — track |  | John Clark; Mark
14 | Parkwood | 16 | PARK-16 | Alt Vendor | Alt | Complete | 16635 |  | Jams + Stark LLC | 2026-07-13 |  | 2026-02-11 | 2026-03-10 | 9000 | N | N | N | N |  | N | Pending Transfer (MHTR) | In process — track | [CAPEX docs] Rehab by Jams + Stark (kickoff/closeout est. $8,900; billed $9,000 invoice 1226, Net 30). Closeout signed; deliverables complete (kickoff Feb 11, implementation Feb 23). Standard Jams + Stark refurb scope: exterior pressure wash and skirting/window repair, interior demo, paint, flooring (LVT/LVP), light fixtures and smoke detectors, cabinet/sink cleaning, professional rent-ready clean. | ISSUE #; John Clark; Mark | 13459
15 | Parkwood | 41 | PARK-41 | Alt Vendor | Alt | Complete | 16479 |  |  | 2026-07-13 | [9 empty] | N | Clear Title | Clear — in hand |  | John Clark; Mark
16 | Parkwood | 45 | PARK-45 | Alt Vendor | Alt | Complete | 16480 |  |  | 2026-07-13 | [9 empty] | N | Pending Transfer (MHTR) | In process — track |  | John Clark; Mark
17 | Parkwood | 54 | PARK-54 | Alt Vendor | Alt | Complete | 16481 |  |  | 2026-07-13 | [9 empty] | N | Pending Transfer (MHTR) | In process — track |  | John Clark; Mark
18 | Parkwood | 63 | PARK-63 | Alt Vendor | Alt | Complete | 16482 |  |  | 2026-07-13 | [9 empty] | N | Pending Transfer (MHTR) | In process — track |  | John Clark; Mark
19 | Shady Acres | 101 | SA-101 | Alt Vendor | Alt | Not Started | 16547 |  | Jams + Stark LLC |  |  | 2025-12-23 |  | 11400 | N | N | N | N |  |  | Clear Title | Clear — in hand |  | John Clark; Mark | 11754
20 | Shady Acres | 104 | SA-104 | Alt Vendor | Alt | Not Started | 16546 |  | Jams + Stark LLC |  |  | 2025-12-23 |  | 10600 | N | N | N | N |  |  | Clear Title | Clear — in hand |  | John Clark; Mark | 11758
21 | Shady Acres | 167 | SA-167 | Alt Vendor | Alt | Not Started | 16649 |  | Primary Home Repair & Maintenance |  |  | 2026-02-18 |  | 1600 | N | N | N | N |  |  | No Title | START missing-title (Melanie) |  | John Clark; Mark; Melanie | 13597
22 | Shady Acres | 246 | SA-246 | Alt Vendor | Alt | Not Started | [14 empty] | No Title | START missing-title (Melanie) |  | ISSUE #; John Clark; Mark; Melanie
23 | Silver Hill | 103 | SH-103 | Alt Vendor | Alt | Complete | 16493 |  | Jams + Stark LLC (wade) |  |  | 2025-11-11 | 2025-11-18 | 11714 | N | N | N | N |  | N | Clear Title | Clear — in hand | [CAPEX docs] Rehab by Jams + Stark (Wade), final invoice 1207 billed $11,714.00. Folder marked complete (archived). Detailed line items image-only; consistent with Jams + Stark refurb scope (exterior pressure wash/skirting, interior demo, paint, flooring, lighting, smoke detectors, professional clean). | ISSUE #; John Clark; Mark | 11337

## Pre-fill Log
Pre-fill Log v8 — auto-extracted from signed CAPEX/REHAB docs + invoices (verify)
Estimate → Actual variances (from invoices):
Auburn Ridge 132a | est 38549.25 | actual 4274.25
Auburn Ridge 136b | est 43792.21 | actual 44306.66
Auburn Ridge 151a | est 41460.0 | actual 47009.48
Druid Oaks 155 | est 14400.0 | actual 15500
Fox Creek 27 | est 9000.0 | actual 13700
Brunswick 21 Gressel | est 4800 | actual 4285
Conflicts (tracker had a different value; not overwritten):
Brunswick 37 | Rehab Status | Not Started | In Progress
Brunswick 66 | Rehab Status | Not Started | In Progress
Brunswick 8 | Rehab Status | Not Started | In Progress
Druid Oaks 22 | Actual Start | 2026-06-06 | 2026-02-17
Druid Oaks 22 | Siding Y/N | N | Y
Druid Oaks 41 | Actual Start | 2026-06-06 | 2026-02-17
Shady Acres 101 | Rehab Status | Not Started | In Progress
Shady Acres 104 | Rehab Status | Not Started | In Progress
Shady Acres 167 | Rehab Status | Not Started | In Progress
Brunswick 21 Gressel | Rehab Status | In Progress | Complete
Brunswick 21 Gressel | Final Cost | 40300.0 | 4285
Brunswick 21 Gressel | HVAC Y/N | Y | N
Brunswick 21 Gressel | Roof Y/N | Y | N
Brunswick 155 Robarts | Rehab Status | Complete | In Progress
Brunswick 155 Robarts | Alt Vendor Name | Primary Home Repair And Maintenance | Primary Home Repair & Maintenance
Belle Haven 16 | Final Cost | 8106 | 8106.6
Belle Haven 78 | Siding Y/N | N | Y
Whispering Pines 4885 Clover Lane | Actual End | 2026-05-29 | 2026-06-05
Whispering Pines 4885 Clover Lane | Final Cost | 21919 | 28999
Whispering Pines 4925 Clover Lane | Actual End | 2026-05-29 | 2026-05-17
Whispering Pines 5085 Clover Lane | GL # | 16723 | 16604
Whispering Pines 5085 Clover Lane | Actual End | 2026-05-29 | 2026-05-17
Whispering Pines 5085 Clover Lane | Final Cost | 20744.4 | 20144.4
Whispering Pines 353 Daisy Lane | Actual End | 2026-05-29 | 2026-05-17
Whispering Pines 359 Daisy Lane | GL # | 16602 | 16600
Central C15 | Actual Start | 2026-06-01 | 2026-04-02
Not matched / bundles (manual):
American 22
Brunswick 153 Robarts (sfh)
Belle Haven Siding Bundle (lots Inc. 16, 25, 26, 27, 28, 33, 57)
Whispering Pines Fl Lots 354d / 358l / 359l / 4700p (bundle)
Whispering Pines Fl Siding Bundle (4885/4925/5085 Clover, 353/359 Daisy, Etc.)
Silver Breeze Siding Package (community-wide)
High Pace (program-level) All Florida Rehab (59 Homes) — Initial Allotment
Cells pre-filled: 265
Auburn Ridge 132a | ISSUE # | 12921
Auburn Ridge 132a | Actual Start | 2025-11-21
Auburn Ridge 132a | Actual End | 2026-03-12
Auburn Ridge 132a | Final Cost | 4274.25
Auburn Ridge 132a | HVAC Y/N | N
Auburn Ridge 132a | Water Heater Y/N | N
Auburn Ridge 132a | Roof Y/N | N
Auburn Ridge 132a | Siding Y/N | N
Auburn Ridge 132a | Alt Vendor Name | A New Day Construction
Auburn Ridge 132a | Scope/Notes | (detail added)
Auburn Ridge 136b | ISSUE # | 11552
Auburn Ridge 136b | Actual Start | 2025-12-15
Auburn Ridge 136b | Actual End | 2026-04-08
Auburn Ridge 136b | Final Cost | 44306.66
Auburn Ridge 136b | HVAC Y/N | N
Auburn Ridge 136b | Water Heater Y/N | N
Auburn Ridge 136b | Roof Y/N | N
Auburn Ridge 136b | Siding Y/N | Y
Auburn Ridge 136b | Alt Vendor Name | A New Day Construction
Auburn Ridge 136b | Scope/Notes | (detail added)
Auburn Ridge 151a | ISSUE # | 9220
Auburn Ridge 151a | Actual Start | 2025-09-29
Auburn Ridge 151a | Actual End | 2025-11-19
Auburn Ridge 151a | Final Cost | 47009.48
Auburn Ridge 151a | HVAC Y/N | N
Auburn Ridge 151a | Water Heater Y/N | N
Auburn Ridge 151a | Roof Y/N | Y
Auburn Ridge 151a | Siding Y/N | Y
Auburn Ridge 151a | Alt Vendor Name | A New Day Construction
Auburn Ridge 151a | Scope/Notes | (detail added)
Brunswick 155 | ISSUE # | 11611
Brunswick 155 | Actual Start | 2025-09-30
Brunswick 155 | Actual End | 2026-04-06
Brunswick 155 | Final Cost | 96400.0
Brunswick 155 | Alt Vendor Name | Primary Home Repair And Maintenance
Brunswick 21 | ISSUE # | 9159
Brunswick 21 | Actual Start | 2025-09-29
Brunswick 21 | Final Cost | 40300.0
Brunswick 21 | HVAC Y/N | Y
Brunswick 21 | Water Heater Y/N | N
Brunswick 21 | Roof Y/N | Y
Brunswick 21 | Siding Y/N | N
Brunswick 21 | Alt Vendor Name | Primary Home Repair & Maintenance
Brunswick 37 | ISSUE # | 11592
Brunswick 37 | Actual Start | 2025-12-23
Brunswick 37 | Final Cost | 10600.0
Brunswick 37 | HVAC Y/N | N
Brunswick 37 | Water Heater Y/N | N
Brunswick 37 | Roof Y/N | N
Brunswick 37 | Siding Y/N | N
Brunswick 37 | Alt Vendor Name | Jams + Stark LLC
Brunswick 66 | ISSUE # | 14749
Brunswick 66 | Actual Start | 2026-03-23
Brunswick 66 | Final Cost | 1950.0
Brunswick 66 | HVAC Y/N | N
Brunswick 66 | Water Heater Y/N | N
Brunswick 66 | Roof Y/N | N
Brunswick 66 | Siding Y/N | N
Brunswick 66 | Alt Vendor Name | Primary Home Repair And Maintenance
Brunswick 8 | ISSUE # | 12984
Brunswick 8 | Actual Start | 2026-02-17
Brunswick 8 | Final Cost | 11685.0
Brunswick 8 | Alt Vendor Name | Primary Home Repair And Maintenance
Druid Oaks 155 | ISSUE # | 11626
Druid Oaks 155 | Actual Start | 2025-12-30
Druid Oaks 155 | Actual End | 2026-05-21
Druid Oaks 155 | Final Cost | 15500
Druid Oaks 155 | HVAC Y/N | N
Druid Oaks 155 | Water Heater Y/N | N
Druid Oaks 155 | Roof Y/N | N
Druid Oaks 155 | Siding Y/N | Y
Druid Oaks 155 | Alt Vendor Name | Jams + Stark LLC
Druid Oaks 155 | Scope/Notes | (detail added)
Druid Oaks 22 | ISSUE # | 13872
Druid Oaks 22 | Final Cost | 6375.0
Druid Oaks 22 | Alt Vendor Name | Primary Home Repair & Maintenance
Druid Oaks 22 | Scope/Notes | (detail added)
Druid Oaks 41 | ISSUE # | 13874
Druid Oaks 41 | Final Cost | 1150.0
Druid Oaks 41 | Alt Vendor Name | Primary Home Repair & Maintenance
Druid Oaks 41 | Scope/Notes | (detail added)
Fox Creek 103 | ISSUE # | 13072
Fox Creek 103 | Actual Start | 2025-12-08
Fox Creek 103 | Actual End | 2025-12-22
Fox Creek 103 | Final Cost | 9000.0
Fox Creek 103 | HVAC Y/N | N
Fox Creek 103 | Water Heater Y/N | N
Fox Creek 103 | Roof Y/N | N
Fox Creek 103 | Siding Y/N | Y
Fox Creek 103 | Scope/Notes | (detail added)
Fox Creek 121 | ISSUE # | 13263
Fox Creek 121 | Actual Start | 2025-12-10
Fox Creek 121 | Actual End | 2026-01-30
Fox Creek 121 | Final Cost | 9000.0
Fox Creek 121 | HVAC Y/N | N
Fox Creek 121 | Water Heater Y/N | N
Fox Creek 121 | Roof Y/N | N
Fox Creek 121 | Siding Y/N | Y
Fox Creek 121 | Scope/Notes | (detail added)
Fox Creek 27 | ISSUE # | 13269
Fox Creek 27 | Actual Start | 2025-12-10
Fox Creek 27 | Actual End | 2026-03-10
Fox Creek 27 | Final Cost | 13700
Fox Creek 27 | HVAC Y/N | N
Fox Creek 27 | Water Heater Y/N | N
Fox Creek 27 | Roof Y/N | N
Fox Creek 27 | Siding Y/N | Y
Fox Creek 27 | Scope/Notes | (detail added)
Fox Creek 32 | ISSUE # | 13257
Fox Creek 32 | Actual Start | 2025-12-10
Fox Creek 32 | Actual End | 2026-01-21
Fox Creek 32 | Final Cost | 9000.0
Fox Creek 32 | HVAC Y/N | N
Fox Creek 32 | Water Heater Y/N | N
Fox Creek 32 | Roof Y/N | N
Fox Creek 32 | Siding Y/N | Y
Fox Creek 32 | Scope/Notes | (detail added)
Fox Creek 35 | ISSUE # | 13271
Fox Creek 35 | Actual Start | 2025-12-30
Fox Creek 35 | Actual End | 2026-04-22
Fox Creek 35 | Final Cost | 9000.0
Fox Creek 35 | HVAC Y/N | N
Fox Creek 35 | Water Heater Y/N | N
Fox Creek 35 | Roof Y/N | N
Fox Creek 35 | Siding Y/N | Y
Fox Creek 35 | Scope/Notes | (detail added)
Fox Creek 39 | ISSUE # | 13273
Fox Creek 39 | Actual Start | 2025-12-30
Fox Creek 39 | Actual End | 2026-02-03
Fox Creek 39 | Final Cost | 9000.0
Fox Creek 39 | HVAC Y/N | N
Fox Creek 39 | Water Heater Y/N | N
Fox Creek 39 | Roof Y/N | N
Fox Creek 39 | Siding Y/N | Y
Fox Creek 39 | Scope/Notes | (detail added)
Fox Creek 45 | ISSUE # | 13261
Fox Creek 45 | Actual Start | 2026-02-11
Fox Creek 45 | Actual End | 2026-03-17
Fox Creek 45 | Final Cost | 9000
Fox Creek 45 | HVAC Y/N | N
Fox Creek 45 | Water Heater Y/N | N
Fox Creek 45 | Roof Y/N | N
Fox Creek 45 | Siding Y/N | Y
Fox Creek 45 | Scope/Notes | (detail added)
Fox Creek 60 | ISSUE # | 13275
Fox Creek 60 | Actual Start | 2025-12-23
Fox Creek 60 | Actual End | 2026-02-25
Fox Creek 60 | Final Cost | 9000.0
Fox Creek 60 | HVAC Y/N | N
Fox Creek 60 | Water Heater Y/N | N
Fox Creek 60 | Roof Y/N | N
Fox Creek 60 | Siding Y/N | N
Fox Creek 60 | Scope/Notes | (detail added)
Fox Creek 74 | ISSUE # | 13277
Fox Creek 74 | Actual Start | 2025-12-10
Fox Creek 74 | Actual End | 2026-03-10
Fox Creek 74 | Final Cost | 9000.0
Fox Creek 74 | HVAC Y/N | N
Fox Creek 74 | Water Heater Y/N | N
Fox Creek 74 | Roof Y/N | N
Fox Creek 74 | Siding Y/N | Y
Fox Creek 74 | Scope/Notes | (detail added)
Fox Creek 88 | ISSUE # | 13471
Fox Creek 88 | Actual Start | 2026-01-12
Fox Creek 88 | Actual End | 2026-03-10
Fox Creek 88 | Final Cost | 9000
Fox Creek 88 | HVAC Y/N | N
Fox Creek 88 | Water Heater Y/N | N
Fox Creek 88 | Roof Y/N | N
Fox Creek 88 | Siding Y/N | Y
Fox Creek 88 | Scope/Notes | (detail added)
Fox Creek 90 | GL # | 16527
Fox Creek 90 | ISSUE # | 11634
Fox Creek 90 | Actual Start | 2025-12-11
Fox Creek 90 | Actual End | 2025-12-15
Fox Creek 90 | Final Cost | 9000.0
Fox Creek 90 | HVAC Y/N | N
Fox Creek 90 | Water Heater Y/N | N
Fox Creek 90 | Roof Y/N | N
Fox Creek 90 | Siding Y/N | N
Fox Creek 90 | Scope/Notes | (detail added)
Parkwood 16 | GL # | 16635
Parkwood 16 | ISSUE # | 13459
Parkwood 16 | Actual Start | 2026-02-11
Parkwood 16 | Actual End | 2026-03-10
Parkwood 16 | Final Cost | 9000
Parkwood 16 | HVAC Y/N | N
Parkwood 16 | Water Heater Y/N | N
Parkwood 16 | Roof Y/N | N
Parkwood 16 | Siding Y/N | N
Parkwood 16 | Alt Vendor Name | Jams + Stark LLC
Parkwood 16 | Scope/Notes | (detail added)
Shady Acres 101 | ISSUE # | 11754
Shady Acres 101 | Actual Start | 2025-12-23
Shady Acres 101 | Final Cost | 11400.0
Shady Acres 101 | HVAC Y/N | N
Shady Acres 101 | Water Heater Y/N | N
Shady Acres 101 | Roof Y/N | N
Shady Acres 101 | Siding Y/N | N
Shady Acres 101 | Alt Vendor Name | Jams + Stark LLC
Shady Acres 104 | ISSUE # | 11758
Shady Acres 104 | Actual Start | 2025-12-23
Shady Acres 104 | Final Cost | 10600.0
Shady Acres 104 | HVAC Y/N | N
Shady Acres 104 | Water Heater Y/N | N
Shady Acres 104 | Roof Y/N | N
Shady Acres 104 | Siding Y/N | N
Shady Acres 104 | Alt Vendor Name | Jams + Stark LLC
Shady Acres 167 | ISSUE # | 13597
Shady Acres 167 | Actual Start | 2026-02-18
Shady Acres 167 | Final Cost | 1600.0
Shady Acres 167 | HVAC Y/N | N
Shady Acres 167 | Water Heater Y/N | N
Shady Acres 167 | Roof Y/N | N
Shady Acres 167 | Siding Y/N | N
Shady Acres 167 | Alt Vendor Name | Primary Home Repair & Maintenance
Silver Hill 103 | GL # | 16493
Silver Hill 103 | ISSUE # | 11337
Silver Hill 103 | Actual Start | 2025-11-11
Silver Hill 103 | Actual End | 2025-11-18
Silver Hill 103 | Final Cost | 11714
Silver Hill 103 | HVAC Y/N | N
Silver Hill 103 | Water Heater Y/N | N
Silver Hill 103 | Roof Y/N | N
Silver Hill 103 | Siding Y/N | N
Silver Hill 103 | Alt Vendor Name | Jams + Stark LLC (wade)
Silver Hill 103 | Scope/Notes | (detail added)
Brunswick 21 Gressel | Actual End | 2026-01-14
Brunswick 21 Gressel | Scope/Notes | (detail added)
Brunswick 155 Robarts | HVAC Y/N | N
Brunswick 155 Robarts | Water Heater Y/N | N
Brunswick 155 Robarts | Roof Y/N | N
Brunswick 155 Robarts | Scope/Notes | (detail added)
Belle Haven 5 | Actual Start | 2026-04-02
Belle Haven 5 | Actual End | 2026-05-17
Belle Haven 5 | Scope/Notes | (detail added)
Belle Haven 16 | Actual Start | 2026-04-02
Belle Haven 16 | Scope/Notes | (detail added)
Belle Haven 18 | Actual Start | 2026-04-02
Belle Haven 18 | Scope/Notes | (detail added)
Belle Haven 30a | Actual Start | 2026-04-02
Belle Haven 30a | Scope/Notes | (detail added)
Belle Haven 33 | ISSUE # | 13728 (roof-over)
Belle Haven 33 | Actual Start | 2026-04-02
Belle Haven 33 | Actual End | 2026-05-17
Belle Haven 33 | Roof Y/N | Y
Belle Haven 33 | Scope/Notes | (detail added)
Belle Haven 57 | Actual Start | 2026-04-02
Belle Haven 57 | Actual End | 2026-05-17
Belle Haven 57 | Scope/Notes | (detail added)
Belle Haven 78 | GL # | 16620
Belle Haven 78 | Actual Start | 2026-04-02
Belle Haven 78 | Scope/Notes | (detail added)
Whispering Pines 4885 Clover Lane | Actual Start | 2026-04-02
Whispering Pines 4885 Clover Lane | Scope/Notes | (detail added)
Whispering Pines 4925 Clover Lane | Actual Start | 2026-04-02
Whispering Pines 4925 Clover Lane | Scope/Notes | (detail added)
Whispering Pines 5085 Clover Lane | Actual Start | 2026-04-02
Whispering Pines 5085 Clover Lane | Scope/Notes | (detail added)
Whispering Pines 353 Daisy Lane | Actual Start | 2026-04-02
Whispering Pines 353 Daisy Lane | Scope/Notes | (detail added)
Whispering Pines 359 Daisy Lane | Actual Start | 2026-04-02
Whispering Pines 359 Daisy Lane | Scope/Notes | (detail added)
Central C15 | Siding Y/N | Y
Central C15 | Scope/Notes | (detail added)