parakeet

Workflow: Full Rehab Lifecycle

Home Becomes Vacant → TBD Call → Three Paths → Market Release

| Process Owner | Operations — owns Path A from TBD Call decision through market listing |
| --- | --- |
| Applies To | Asset Management, Operations, Regional Managers, Community Managers, Maintenance Team, Contracted Vendors, Sales , Construction (Path C only) |
| Construction Role | Path C (Demo + Infill) ONLY — site survey, demo, placement, trim-out through COI. Zero role in Path A. |
| Disposition Paths | Path A — Rehab (Operations-owned) Path B — Sell As-Is · Path C — Demo + Infill → |
| Path A Turnaround | One (1) week: initial punchlist walkthrough → home listed on market |
| Systems | Rent Manager · Rehab Punchlist Jotform · Home Market Jotform · Unit Turn Sheet · Rehab Walk Sheet |

# Ownership Statement

The Operations team owns the rehab process from the moment the rehab decision is made at the TBD Call through final listing activation. This ownership is total: no step in Path A is initiated, approved, or closed by any team other than Operations without the Operations' direction.

Phase 1 — Vacancy & TBD Call  ·  Applies to ALL Paths

Step 1 — Home Becomes Vacant

- Home becomes vacant (move-out, abandonment, acquisition, or other cause).

- Asset Management confirms the vacancy and flags the home/lot for disposition review.

- Asset Management schedules a TBD Call with all required stakeholders promptly.

IMPORTANT: The TBD Call must be scheduled with no delay. A lot without a disposition decision accumulates carrying cost and deferred maintenance. Asset Management owns scheduling.

Step 2 — TBD Call

Attendees: Asset Management (leads) · Operations · Regional Manager · Sales · Construction

- Asset Management leads the call; presents home/lot condition, financial context, and options.

- Operations advises on operational capacity, rehab feasibility, and timeline.

- Sales advises on marketability, sale potential, and infill home options.

- Construction advises on demo feasibility and infill scope — advisory role only at this stage.

- Regional Manager provides on-site operational and community context.

◆ DECISION: What is the disposition decision?

YES → Rehab (Path A) · Sell As-Is (Path B) · Demo + Infill (Path C). Decision must be recorded before the call ends.

NO  → Decision not reached → Operations documents the open question in Rent Manager, assigns a decision owner, and sets a hard follow-up date. No path work begins until decision is recorded.

Step 3 — Post-Call Actions (all paths)

- Asset Management opens the appropriate issues in Rent Manager per the decision.

- Asset Management changes the listing status in Rent Manager to reflect the chosen path.

- Operations takes ownership of Path A immediately and begins directing next steps.

- Operations notifies the Regional Manager of path assignment and next steps.

IMPORTANT: Asset Management must open all RM issues and update listing status before any path-specific work begins. No team proceeds ahead of the RM record.

PATH A — Rehab Home  ·  Owner: Operations / Operations — from TBD Call decision to listing activation

Phase 2A: Scope Preparation & Vendor Kickoff

Objective: Prepare the rehab scope, assign the contracted vendor, and get work underway under Operations direction.

Step 1 — Operations Prepares Scope Documents

- Operations directs preparation of the Unit Turn Sheet and Rehab Walk Sheet for the home.

- Regional Manager reviews scope documents to ensure they reflect the full condition of the home.

Step 2 — Vendor Assignment & Kickoff

- Operations assigns the contracted vendor to the rehab.

- Regional Manager shares the Unit Turn Sheet and Rehab Walk Sheet with the contracted vendor on behalf of Operations.

- Regional Manager confirms vendor has accepted the scope and work is underway.

- Regional Manager records vendor assignment and kickoff date in Rent Manager.

IMPORTANT: The Unit Turn Sheet and Rehab Walk Sheet define the vendor's complete scope. Any items not on these documents are out of scope. Scope changes must be directed by the Operations.

Step 3 — Vendor Executes Rehab

- Contracted vendor executes all approved scope items.

- Vendor notifies the Operations and Regional Manager when all scope items are complete.

➤ HANDOFF: Vendor completion notification triggers Operations closeout. The Operations drives every remaining step through market release.

Phase 3A: Operations Closeout & Market Release

Objective: Inspect, resolve all deficiencies, obtain Regional Manager final approval, and list the home within the one-week target.

Step 1 — Regional Manager Initiates Closeout

- Regional Manager receives vendor completion notification.

- Regional Manager notifies the Community Manager and Maintenance team that the home is ready for the initial punchlist walkthrough.

- Regional Manager records the notification date in Rent Manager — the one-week turnaround clock starts at this moment.

- Operations monitors the one-week clock and is the sole authority to extend the deadline.

IMPORTANT: The one-week turnaround clock starts when the Regional Manager notifies the Community Manager. All steps in Phase 3A — walkthroughs, deficiency resolution, re-walks, final approval, and listing activation — must be completed within this single week.

Step 2 — Community Manager Punchlist Walkthrough

- Community Manager performs a full walkthrough using the Rehab Punchlist Jotform on the same day notification is received whenever possible.

- Community Manager documents all findings:

  - Overall rehab condition

  - Remaining deficiencies

  - Cleaning concerns

  - Incomplete work and safety concerns

  - Cosmetic concerns

- Community Manager selects a home status at the conclusion of the walkthrough.

- Completed Jotform auto-distributes to: Regional Manager, Operations, Director of Sales.

IMPORTANT: A completed Rehab Punchlist Jotform is required for every walkthrough — initial and all re-walks. No exceptions under any circumstances.

Step 3 — Walkthrough Status Decision

The Community Manager selects one of three statuses at the end of every walkthrough:

Option 1: Ready to List / Show

Criteria: Rehab fully complete. Home meets all company standards. No outstanding deficiencies.

- Community Manager installs the Parakeet 'P' plaque in the home window.

- Community Manager submits the Home Market Jotform with all required listing photos.

➤ HANDOFF: Home Market Jotform is the formal Operations → Sales handoff. Operations' process is complete. Sales activates the listing per the Home Listing & Marketing SOP.

Option 2: Not Ready — Maintenance Scope

Criteria: Minor operational items remain — cleaning, paint touch-ups, minor repairs, small corrections.

- Community Manager opens work orders in Rent Manager and assigns them to Maintenance.

- Maintenance completes all assigned items within the one-week turnaround window.

- Maintenance updates work order status in Rent Manager upon completion.

- Community Manager tracks all progress in Rent Manager.

- Once all items are resolved, Community Manager performs a re-walk (Step 4).

IMPORTANT: All maintenance items must be documented and tracked in Rent Manager. Verbal updates do not count as completed.

Option 3: Needs Additional Work — Vendor Scope

Criteria: Outstanding items related to incomplete or missed work from the approved vendor scope.

- Community Manager documents all deficiencies in the Jotform notes field.

- Community Manager confirms the Regional Manager has received the punch list for vendor follow-up.

- Regional Manager contacts the contracted vendor directly and coordinates completion of missed scope items.

- Regional Manager updates Rent Manager notes with deficiency details and follow-up status.

- Once vendor corrections are complete, Community Manager performs a re-walk (Step 4).

Step 4 — Re-Walk Process

- Once repairs or corrections are complete, Community Manager performs a re-walk using the Rehab Punchlist Jotform.

- Community Manager documents findings and selects a new status.

◆ DECISION: Is the home ready after re-walk?

YES → Proceed to Step 5 — Regional Manager Final Market Approval.

NO  → Deficiencies remain — return to Step 3 and assign the appropriate corrective path (Option 2 or 3). Re-walk loop continues until Regional Manager confirms market-ready.

IMPORTANT: The re-walk loop continues without limit until the home meets all standards. No home may skip the re-walk gate to proceed to market.

Step 5 — Regional Manager Final Market Approval

This is the Operations quality gate. No home is released to market without this approval.

- Regional Manager reviews all completed Jotform submissions and Rent Manager notes for the home.

- Regional Manager confirms the home meets all operational standards.

◆ DECISION: Does the home meet all operational standards?

YES → Regional Manager notifies Community Manager: home is approved for market release. Proceed to Step 6.

NO  → Regional Manager identifies remaining issues and directs Community Manager back to Step 3 for the appropriate corrective action.

ADD THE INTERNAL REHAB PIECE TO SOP

Step 6 — Home Market Jotform & Listing Activation

- Community Manager ensures the Parakeet 'P' plaque is installed in the home window.

- Community Manager submits the Home Market Jotform with all required listing photos.

- Sales reviews the submission and determines whether professional photography is needed.

- If photography is needed, Sales schedules it before listing activation.

- Sales activates the listing. Home is live and available for showings.

➤ HANDOFF: Home Market Jotform submission is the formal, final Operations → Sales handoff. All listing and marketing activity from this point is owned by Sales per the Home Listing & Marketing SOP.

PATH B — Sell As-Is  ·  Operations coordinates clean-up; Sales leads the sale

Phase 2B: Clean-Up & Prep

Objective: Prepare the home for sale with basic clean-up only — no rehab scope.

- Regional Manager notifies Community Manager and Maintenance of the clean-up scope.

- Community Manager coordinates basic clean-up (trash removal, cleaning, exterior tidy).

- Maintenance completes all assigned clean-up items and updates status in Rent Manager.

- Community Manager notifies Regional Manager when clean-up is complete.

NOTE: No rehab issues are opened in Rent Manager for Path B. Asset Management set listing status to Sell As-Is at the TBD Call. Only basic clean-up work orders are opened.

Phase 3B: Marketing & Sale

Objective: Pass the clean home to Sales and complete the sale.

- Regional Manager reviews the home and confirms it is presentable for sale.

- Regional Manager notifies Sales that the home is ready.

- Sales lists the home for sale and coordinates showings and buyer outreach.

- Sale closes; lot disposition is complete for Path B.

➤ HANDOFF: Regional Manager confirmation → Sales takes full ownership of the listing and sale process.

PATH C — Demo + Infill Unit  ·  Construction leads demo/placement/trim-out through COI; Operations takes over when COI obtained

Construction owns Path C through COI: site survey, demo vendor, new home delivery, placement, utility connections, trim-out, and all work necessary to obtain the Certificate of Occupancy. Construction's role ends when COI is obtained and notification is sent to Operations, Sales, and Asset Management. At that point, Operations takes ownership and Path A begins.

Phase 2C: Site Survey & Demo

Objective: Remove the existing structure and prepare the lot for a new home.

- Asset Management has set listing status to Infill/Pending in Rent Manager and opened demo and infill issues.

- Construction orders a site survey for the lot.

- Construction sources and contracts a demo vendor.

- Demo vendor removes the existing structure from the lot.

- Construction updates Rent Manager notes upon demo completion.

Phase 3C: New Home Purchase & Placement

Objective: Identify, approve, purchase, and place the infill home on the lot.

- Sales researches available homes and identifies candidates for purchase for the lot.

- Sales and Operations review options and approve the home purchase.

- Construction coordinates delivery and physical placement of the new home on the lot.

- Construction manages utility connections, trim-out, and all work necessary to obtain COI.

- Construction notifies Operations, Sales, and Asset Management: new home placed, COI obtained, ready for scope definition.

NOTE: Sales identifies options. Sales/Operations jointly approve the purchase. Construction owns placement through COI. The moment COI notification is sent, Operations takes ownership and Path A begins.

Phase 4C: Operations Takes Over — Re-enters Path A

Objective: Transfer ownership to Operations and begin the standard rehab process.

- Operations receives COI handoff notification from Construction.

- Operations takes full ownership of the new home.

- Operations directs preparation of the Unit Turn Sheet and Rehab Walk Sheet.

➤ HANDOFF: Path C re-enters Path A at Phase 2A — Scope Preparation & Vendor Kickoff. All steps of Path A from Phase 2A through market listing apply in full. Construction has no further role after this point.

IMPORTANT: There is no separate market release process for Path C. After COI, the full Path A rehab and Operations closeout process applies without exception.

# Forms & Checklists

| Form / Document | Path | Prepared / Filled By | Routes To | Notes |
| --- | --- | --- | --- | --- |
| Unit Turn Sheet | A | Operations (Regional Manager shares with vendor) | Contracted Vendor | Defines full rehab scope. Shared by Operations at vendor kickoff. Linked. |
| Rehab Walk Sheet | A | Operations (Regional Manager shares with vendor) | Contracted Vendor | Physical walk reference for vendor. Shared alongside Unit Turn Sheet. Linked. |
| Rehab Walk Punchlist (Manager Fillable PDF) | A | Community Manager | Regional Manager (filed in RM notes) | On-site paper checklist used during CM walkthrough. Linked. |
| Rehab Punchlist Jotform | A | Community Manager | Regional Mgr, Operations, Director of Sales (auto) | Required for every walkthrough — initial and ALL re-walks. No exceptions. Linked. |
| Home Market Jotform | A | Community Manager | Sales Team | Submitted ONLY after Regional Manager final approval. Must include listing photos. Formal Operations → Sales handoff. Linked. |

# Roles & Accountability (RACI)

R = Responsible (does the work)  ·  A = Accountable (owns the outcome)  ·  C = Consulted  ·  – = Not involved

| Activity | Asset Mgmt | Operations | Reg. Mgr | Comm. Mgr | Maint. | Vendor | Sales |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PHASE 1: VACANCY & TBD CALL (All Paths) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Home becomes vacant; flagged for review | A/R | C | C | – | – | – | – |
| Schedule & lead TBD Call | A/R | R | R | – | – | – | R |
| Make disposition decision at TBD Call | A | A/R | R | A/R | – | – | C |
| Open RM issues; change listing status | A/R | C | – | – | – | – | – |
| PATH A: REHAB (Operations Owned) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Direct scope sheet prep (Unit Turn + Rehab Walk Sheet) | – | A/R | C | – | – | – | – |
| Share scope sheets with contracted vendor | – | C | A/R | – | – | – | – |
| Assign & contract vendor for rehab | – | A/R | C | – | – | – | – |
| Execute approved rehab scope | – | – | – | – | – | A/R | – |
| Notify DOO & Regional Mgr of completion | – | R | R | – | – | A | – |
| Notify CM & Maintenance; start 1-week clock | – | C | A/R | – | – | – | – |
| Perform punchlist walkthrough (Jotform) | – | C | C | A/R | – | – | – |
| Open RM work orders (Option 2: maintenance) | – | C | C | A/R | R | – | – |
| Complete maintenance work orders (Option 2) | – | – | – | C | A/R | – | – |
| Coordinate vendor return for missed scope (Option 3) | – | C | A/R | C | – | R | – |
| Grant final market approval | – | C | A/R | – | – | – | – |
| Install 'P' plaque; submit Home Market Jotform | – | – | – | A/R | – | – | – |
| Review listing; coordinate photography | – | – | – | – | – | – | A/R |
| PATH B: SELL AS-IS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate clean-up of home | – | C | C | A/R | R | – | – |
| Confirm home ready; notify Sales | – | C | A/R | – | – | – | – |
| Market & complete sale | – | – | – | – | – | – | A/R |
| PATH C: DEMO + INFILL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Order site survey; contract & manage demo | – | – | – | – | – | A/R | – |
| Research & identify infill home options | – | – | – | – | – | – | A/R |
| Review & approve infill home purchase (Sales/Ops) | A/R | C | – | – | – | – | R |
| Coordinate new home delivery, placement, trim-out, COI | – | – | – | – | – | A/R | – |
| Notify Operations, Sales & Asset Mgmt: COI obtained | – | R | R | – | – | A | – |
| Hand off to Operations; re-enters Path A | – | A/R | R | – | – | – | – |

# Standard Requirements

- A TBD Call must be held and a disposition decision recorded before any path work begins.

- Asset Management opens all Rent Manager issues and changes listing status before path work starts.

- Operations owns Path A from the TBD Call decision to listing activation. No exceptions.

- Vendors are contracted and managed directly by Operations — not by Construction.

- [Path A] Rehab Punchlist Jotform required for every walkthrough — initial and all re-walks.

- [Path A] All deficiencies documented in Jotform and tracked in Rent Manager.

- [Path A] One-week turnaround from initial punchlist walkthrough to home listed on market.

- [Path A] Regional Manager issues final market approval. No home listed without it.

- [Path A] Parakeet 'P' plaque installed before Home Market Jotform is submitted.

- [Path C] Construction owns site survey, demo, placement, trim-out through COI.

- [Path C] Sales and Operations jointly approve infill home purchase.

- [Path C] Construction's role ends at COI notification. Operations owns Path A forward.

- All documentation must remain accessible in Rent Manager for audit and accountability.

# Review & Revision

| Date | Author | Changes |
| --- | --- | --- |
| June 2026 | Operations | Workflow v3. Updated from uploaded SOP. Path C updated: Construction now owns trim-out and all work through COI (not just placement). Home purchase approval updated to Sales/Operations joint review (not Asset Management alone). All other ownership rules unchanged: Operations owns Path A from TBD Call decision. |