OPERATIONAL PROCEDURE

Path A Rehab — TBD Call to Listing Activation

Parakeet Communities |  Operations SOP

| Process Owner | Operations / Director of Operations — Natalie Magurne |
| --- | --- |
| Triggers Downstream | Home Listing & Marketing SOP (Sales) ¦ Vendor Payment process (Accounting) |
| Version | 1.0 — July 9, 2026 |

Purpose

This SOP governs the Path A Rehab process from the moment the TBD Call disposition decision is recorded as "Rehab" through vendor assignment and execution, punch list walkthrough and re-walk loop, listing activation, and final vendor invoice and payment. It defines who does what, in what order, and what must be documented at each step.

Scope

| Applies To | Operations ¦ Director of Operations ¦ Regional Manager ¦ Community Manager ¦ Maintenance Team ¦ Contracted Vendor ¦ Sales ¦ Accounting |
| --- | --- |
| Trigger | TBD Call disposition decision recorded as "Rehab" (Path A). The TBD Call itself is out of scope — this SOP begins the moment that result is known. |
| Finish Line | Vendor invoice processed by Accounting and home is live on market. |
| Out of Scope | The TBD Call itself ¦ (Sell As-Is) ¦ (Demo + Infill) |

Phase 1 — Vendor Assignment & Kickoff

Objective: Assign the contracted vendor to the approved rehab scope and get work on record in Rent Manager before any work begins.

Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Operations | Assigns contracted vendor to the rehab. |

Tasks

Task 1 — Assign Contracted Vendor

- Operations assigns the contracted vendor to the rehab following the TBD Call Rehab decision.

Task 2 — Share Scope & Confirm Kickoff

- Operations work with vendors to schedule scope walks and calls

- Vendor to send scope or level status for each rehab to be approved prior to start,

Task 3 — Record Vendor Assignment & Kickoff Date in Rent Manager

- Director of  records the vendor assignment and confirms kickoff date in Rent Manager before work begins.

IMPORTANT: Nothing proceeds until the vendor’s assignment and kickoff date are recorded in Rent Manager. No Rent Manager record = no work starts.

HANDOFF: Vendor kickoff recorded in Rent Manager triggers Phase 2 — Vendor Execution & Weekly Review.

Phase 2 — Vendor Execution & Weekly Review

Objective: Vendor executes the approved scope while Operations and Director of Operations conduct weekly reviews and maintain updated scope notes until rehab is complete.

Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Contracted Vendor | Executes all approved scope items. Provides progress updates on weekly review calls. Notifies Operations and Regional Manager upon completion. |
| Director of Operations | Co-leads weekly review calls. Updates Rehab Walk Sheet and scope notes in Rent Manager after each review. |
| Operations Coordinator | Monitors overall turnaround. Approves and records any extensions in Rent Manager. |
| Regional Manager | Receives delay notifications escalated from Operations. Tracks vendor progress at the site level. |

Tasks

Task 1 — Vendor Executes Approved Scope

- Contracted vendor executes all items on agreed-upon scope or level rehab.

- If delays arise, vendor notifies Director of Operations directly on the weekly review call.

Task 2 — Weekly Review of Vendor Progress (Operations + Director of Operations)

- Director of Operations conducts a weekly review call with the vendor every week throughout execution — no weeks skipped.

- Director of Operations updates the scope notes in Rent Manager with any necessary updates after each review call.

IMPORTANT: If vendor reports delays: vendor communicates directly to the Director of Operations on the review call. Operations then notify Regional Manager.

Task 3 — Vendor Completion Notification

- Contracted vendor notifies both Operations and Regional Manager when all approved scope items are complete.

HANDOFF: Vendor completion notification triggers Phase 3. Regional Manager immediately initiates the punch list closeout process.

Phase 3 — Punchlist Walkthrough & Re-walk Loop

Objective: Inspect the home, resolve all deficiencies, and prepare for listing — all within one week from the date Regional Manager records the punch list notification in Rent Manager.

Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Regional Manager | Notifies Community Manager and Maintenance that the home is ready for punch list. Records notification date in Rent Manager (starts 1-week clock). Coordinates vendor return for Option 3 deficiencies. |
| Community Manager | Performs punch list walkthrough and all re-walks using Rehab Punchlist Jotform. Selects walkthrough status. Opens Rent Manager work orders. Installs Parakeet plaque. Submits Home Market Jotform. |
| Maintenance Team | Completes assigned work orders within the one-week window. Updates Rent Manager upon completion. |
| Contracted Vendor | Returns to complete missed scope items (Option 3 only). Notifies Operations and Regional Manager when corrections are done. |
| Operations | Monitors the one-week turnaround clock. Sole authority to approve and record extensions. Closes Rent Manager rehab issue after Home Market Jotform is submitted. |

Tasks

Task 1 — Notify Community Manager & Maintenance — Start 1-Week Clock

- Regional Manager notifies Community Manager and Maintenance Team that the home is ready for the initial punch list walkthrough.

- Regional Manager records the notification date in Rent Manager immediately. This is the moment the one-week clock starts.

Task 2 — Punchlist Walkthrough (Rehab Punchlist Jotform)

- Community Manager performs a full punch list walkthrough using the Rehab Punchlist Fastfield form on the same day notification is received, whenever possible.

- Community Manager documents all findings: overall rehab condition, deficiencies, cleaning concerns, incomplete work, safety concerns, and cosmetic concerns.

- Completed form auto-routes to: Regional Manager  |  Operations  |  Director of Operations.

IMPORTANT: A completed Rehab Punchlist Jotform is required for every walkthrough — initial and every re-walk. No exceptions. No verbal walkthrough substitutes for the Jotform.

Task 3 — Select Walkthrough Status

Community Manager selects one of three statuses at the end of every walkthrough:

DECISION: What is the walkthrough status?

Option 1: Ready to List / Show

Criteria: Rehab fully complete. Home meets all standards. No outstanding deficiencies.

- Community Manager installs the Parakeet "P" plaque in the home window.

- Community Manager submits the Home Market form with all required listing photos.

- Home Market form routes to: Sales (primary)  |  Regional Manager (copy)  |  Director of Operations (copy).

- Operations closes the Rent Manager rehab issue upon Home Market form submission.

HANDOFF: Home Market Jotform submission is the formal Operations -> Sales handoff. Proceed to Phase 4.

Option 2: Not Ready — Maintenance Scope

Criteria: Minor items remain — cleaning, paint touch-ups, minor repairs.

- Community Manager opens work orders in Rent Manager and assigns to Maintenance Team.

- Maintenance Team completes all items and updates work order status in Rent Manager upon completion.

IMPORTANT: All maintenance items must be in Rent Manager. Verbal updates do not count as complete.

- Once all items are resolved, Community Manager performs a re-walk (return to Task 2).

Option 3: Needs Additional Work — Vendor Scope

Criteria: Incomplete or missed items from the approved vendor scope.

- Community Manager documents all deficiencies in the Rehab Punchlist form.

- Community Manager confirms Regional Manager has received the form.

- Regional Manager contacts the contracted vendor and coordinates return for missed scope items.

- Regional Manager updates Rent Manager notes with deficiency details and follow-up status.

- Contracted vendor completes missed scope and notifies Operations and Regional Manager when done.

- Community Manager performs a re-walk (return to Task 2).

Task 4 — Monitor 1-Week Clock — Approve Extensions if Needed

- Operations monitors the one-week turnaround clock throughout Phase 3.

- Operations is the sole authority to approve and record an extension in Rent Manager.

Phase 4 — Listing Activation

Objective: Sales reviews the Home Market Form, determines photography need, and activates the listing within 24 hours.

Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Sales | Reviews Home Market Form. Determines if professional photography is needed. Schedules photography if required. Activate the listing within 24 hours of receiving the Form. |

Tasks

Task 1 — Review Home Market Form & Determine Photography

- Sales reviews the Home Market form and all listing photos.

IMPORTANT: Sales must activate the listing — or initiate photography — within 24 hours of receiving the Home Market Jotform.

DECISION: Is professional photography needed?

YES -> Sales schedules professional photography, then activates listing after photography is complete.

NO -> Sales activates the listing directly.

Task 2 — Activate Listing

- Sales activates the listing. Home is live and available for showings.

HANDOFF: All listing and marketing activity from this point is owned by Sales per the Home Listing & Marketing SOP. Proceed to Phase 5.

Phase 5 — Vendor Invoice & Payment

Objective: Vendor submits invoice and after-completion photos. Operations reviews and forwards to accounting for payment. This is the final step of the Rehab SOP.

Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Contracted Vendor | Submits invoice and after photos of completed scope to Operations. |
| Operations | Reviews invoice and after photos. Confirms scope completed as approved. Forwards to Accounting for payment processing. |
| Accounting | Processes vendor invoice upon receipt from Operations. |

Tasks

Task 1 — Vendor Submits Invoice & After Photos

- Contracted vendor submits invoice for the completed rehab scope to Operations.

- Vendor includes after photos of completed work with the invoice.

IMPORTANT: After photos are required with every invoice. Invoice submissions without after photos will not be forwarded to Accounting for payment processing.

Task 2 — Operations Reviews & Forwards to Accounting

- Operations reviews the invoice and after photos to confirm scope was completed as approved.

- Operations forwards invoice and after photos to Accounting for payment processing.

HANDOFF: Operations submission to Accounting is the formal final handoff. Accounting processes payment per standard vendor procedures. This is the end of the Path A Rehab SOP.

Forms & Checklists

| Form / Document | Status | Filled By | Routes To | Notes |
| --- | --- | --- | --- | --- |
| Unit Turn Sheet | Linked | Regional Manager (shares with vendor on behalf of Operations) | Contracted Vendor | Defines full rehab scope. Nothing outside this sheet is in scope. |
| Rehab Walk Sheet | Linked | Director of Operations (updates during weekly reviews) | Contracted Vendor | Physical walk reference. Updated by Director of Operations after each weekly review. |
| Rehab Punchlist Jotform | Linked | Community Manager | Regional Manager, Operations, Director of Operations (auto) | Required for EVERY walkthrough and re-walk. No exceptions. |
| Home Market Jotform | Linked | Community Manager | Sales (primary), Regional Manager (copy), Director of Operations (copy) | Submitted only when status = Ready to List / Show. Must include all listing photos. Formal Operations -> Sales handoff. |

Frequently Asked Questions

Q: When exactly does the one-week turnaround clock start?

A: When Regional Manager records the punchlist notification date in Rent Manager — not when the vendor finishes. That recorded date is the official clock start for all of Phase 3.

Q: Can Community Manager skip the Rehab Punchlist Jotform if the repairs look done?

A: No. A completed Rehab Punchlist Jotform is required for every single walkthrough and re-walk without exception.

Q: Who can extend the one-week deadline?

A: Operations only. Operations records the extension in Rent Manager and notifies Regional Manager.

Q: What happens if a vendor submits an invoice without after photos?

A: Operations does not forward the invoice to Accounting until after photos are received. Vendor must resubmit.

Review & Revision

| Date | Author | Changes |
| --- | --- | --- |
| July 9, 2026 | Natalie Magurne | Initial version — rebuilt from Lucid flowchart (July 3, 2026). |

Open Item: Formal 1-week extension documentation process [TBD — Operations to define].