OPERATIONAL PROCEDURE

Internal Rehab

Parakeet Communities  ·  Operations SOP

| Process Owner | Regional Manager |
| --- | --- |
| Effective Date | August 1, 2026 |
| Triggers Downstream | Home Listing Process |

PURPOSE

Track all internal rehab costs in Rent Manager under the correct issue number and GL codes, and ensure the home is ready to list upon close-out.

SCOPE

Applies To: Regional Managers, DOO, Community Managers (CM), District Managers (DM), Maintenance

Trigger: TBD call — Asset Management flags the unit as an internal rehab

Finish Line: Rehab marked complete in Rent Manager; CM/DM submits the Home Market Jotform

KEY DEFINITIONS

- Issue Number: Created in Rent Manager by Asset Management when the unit is flagged. All charges must be booked to this number.

- Ramp Charges: Purchases on the Ramp company credit card. Must be entered in Rent Manager immediately with the GL code in the memo field.

- UDF / "GL — Total Cost" field: The pop-out field on the Rent Manager issue page where the DOO enters GL codes before any charges are booked.

PHASE 1: INITIATION

1. [CM / DM] Complete the Unit Turn Sheet before the TBD call.

↳ This is the scope of work for the rehab.

2. [Regional Manager] Lead the TBD call with Asset Management; review the Unit Turn Sheet.

3. [Asset Management] Flag the unit as Internal Rehab and create the issue in Rent Manager.

4. [CM / DM / Regional Manager] Confirm the issue number in Rent Manager before moving to Phase 2.

⚠  IMPORTANT: No charges may be booked until a valid issue number exists in Rent Manager.

PHASE 2: SCOPE & GL SETUP

1. [Regional Manager] Finalize the scope of work based on the Unit Turn Sheet.

2. [Director of Operations (DOO)] Contact Accounting with the issue number to request GL codes.

3. [Accounting] Provide GL codes for each charge type:

| Charge Type | GL Code | Examples |
| --- | --- | --- |
| Materials & Supplies (Ramp card charges) | [GL-XXXX] | Paint, flooring, fixtures, hardware Any rehab purchase on the Ramp card |

4. [DOO] Open the issue in Rent Manager → click the UDF pop-out → enter GL codes in the "GL — Total Cost" field.

⚠  IMPORTANT: DOO must enter GL codes in the UDF before Phase 3 begins. CM/DM cannot book charges correctly without this.

PHASE 3: ACTIVE REHAB

📋  Note: Expected duration: 14–30 days.

1. [Maintenance] Complete all work per the Unit Turn Sheet. Flag any scope changes to the Regional Manager immediately.

2. [CM / DM] Enter every materials/supply purchase in Rent Manager under the correct issue number with the GL code.

↳ Navigate to the issue → enter cost → select GL code → save. Book at time of purchase.

3. [CM / DM] Enter every Ramp card charge in Rent Manager with the GL code in the memo field.

↳ Memo format: GL [XXXX] — [vendor or description]. Enter as soon as the charge appears on the card.

4. [Regional Manager] Spot-check charges in Rent Manager throughout the rehab. Correct errors before close-out.

⚠  IMPORTANT: All Ramp card charges must include the GL code in the memo field — enter immediately, not at close-out.

PHASE 4: PUNCHLIST WALKTHROUGH & RE-WALK

1. [CM / DM] Walk the unit and submit the Rehab Walkthrough Jotform, marking each scope item Complete / Incomplete / Needs Attention.

2. [Regional Manager] Review the Rehab Walkthrough form.

✔  All items COMPLETE:  Proceed to Phase 5.

✘  Items INCOMPLETE:  Continue below.

3. [Regional Manager] Send the punchlist to Maintenance with a deadline for completion.

4. [Maintenance] Complete remaining items; notify CM/DM when ready for re-walk.

5. [CM / DM] Conduct the re-walk — return to Task 1 and repeat until all items pass.

⚠  IMPORTANT: Do not advance to Phase 5 until Regional Manager confirms all punchlist items are complete.

PHASE 5: COMPLETION & CLOSE-OUT

1. [CM / DM] Confirm all costs and Ramp card charges are entered in Rent Manager under the correct issue number.

↳ No charges missing; all Ramp memo fields contain the GL code.

2. [Regional Manager] Review all charges on the issue. Escalate any GL code discrepancies to Accounting before proceeding.

3. [Accounting] Confirm all charges are correctly GL coded.

4. [Regional Manager] Mark the rehab as completed in Rent Manager — only after Accounting confirmation.

⚠  IMPORTANT: Do not mark complete in Rent Manager until Accounting has confirmed GL coding.

PHASE 6: HANDOFF TO SALES

1. [CM / DM] Submit the Home Market Jotform immediately after the Regional Manager marks the rehab complete.

→ HANDOFF: Sales team receives the Home Market Jotform and lists the home for sale.

FORMS & CHECKLISTS

| Form | Who | When | Where It Goes |
| --- | --- | --- | --- |
| Unit Turn Sheet | CM / DM | Before TBD call (Phase 1) | Scope of work for the rehab |
| Rehab Walkthrough | CM / DM | Phase 4; repeat each re-walk | Jotform — confirms unit readiness |
| Home Market Jotform | CM / DM | After rehab marked complete (Phase 6) | Jotform → Sales team to initiate listing |

RELATED RESOURCES

- Rent Manager — Issues module; UDF pop-out on the issue detail page

- Unit Turn Sheet — [Link TBD]

- Rehab Walkthrough Form — [Link TBD]

- Home Market Jotform — [Link TBD]

FREQUENTLY ASKED QUESTIONS

Q: What if the issue number doesn't exist yet when a charge comes in?

Hold the invoice and notify the Regional Manager. Do not book any charge until Asset Management has created the issue in Rent Manager.

Q: What should I write in the Ramp card memo field?

GL [XXXX] — [vendor or description]. Example: "GL 5010 — Home Depot, flooring materials." This is how Accounting verifies the charge.

REVIEW & REVISION

| Date | Author | Changes |
| --- | --- | --- |
| August 1, 2026 | Natalie | Initial version |
| August 26, 2026 | Natalie | Added Phase 4 Punchlist Walkthrough & Re-walk loop; renamed Home Listing Form → Home Market Jotform; renumbered phases 5–6 |