PARAKEET COMMUNITIES Standard Operating Procedure · CONST-002 Demo to Infill · Demolition & Lot Preparation

| SOP Title | Demo to Infill — Demolition & Lot Preparation |
| --- | --- |
| SOP ID | CONST-002 |
| Version | 1.0 |
| Effective Date | August 2026 |
| Process Owner | Director of Construction |
| Primary Roles | Director of Construction · Regional Manager · Community Manager · Facility Manager · Demo Contractor |
| Trigger | TBD Call disposition decision assigns the home/lot to the Demo + Infill path |
| Finish Line | Lot cleared, graded, and documented; Rent Manager updated to 'Demo / Vacant Lot'; Regional Manager has verified lot; infill home ordered |
| Triggers Downstream | Infill Home Ordering & Lot Prep SOP · Rehab Lifecycle SOP (Path A) |
| Systems Used | Rent Manager |

1.  Purpose

To establish a standardized, safe, and fully documented process for the demolition of an existing home and preparation of the lot for an infill replacement unit. The Director of Construction owns this process from written authorization through Regional Manager closeout verification — ensuring that no demo work begins without written approval, all utilities are confirmed off, all required permits and testing are complete, and the lot is properly documented and updated in Rent Manager before any infill or lot prep work begins.

2.  Scope

| Applies To | All Parakeet community homes and lots where the TBD Call has resulted in a Demo + Infill disposition decision. |
| --- | --- |
| Trigger | TBD Call disposition decision assigns the home/lot to the Demo + Infill path. This SOP begins at that moment. Written authorization must be in hand before any physical work begins. |
| Finish Line | Lot is graded, cleared, and safe. All documentation is filed. Rent Manager status is updated to 'Demo / Vacant Lot.'. Facilities has verified completion. Infill home has been ordered, and lot prep is underway. |
| Does NOT Cover | Infill home selection, purchase, placement, and the subsequent rehab process. This SOP ends at lot clearance and verification. |

3.  Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Director of Construction | Process owner. Obtains and holds written demo authorization. Coordinates all contractor engagement, permit tracking, utility shutoffs, compliance testing, and post-demo closeout. Authorizes every phase transition. Updates Rent Manager and files all documentation. |
| Facilities Manager (FM) | Co-verifies that all utilities are off before demo begins. Receives notification of demo plan and timeline. Verifies completed lot via in-person site visit or full photo package. Countersigns closeout. |
| Community Manager (CM) | Notifies residents that might be affected in writing. Present on-site on demo day if facilities can’t be to confirm the pre-demo checklist before the contractor begins work. |
| Facility Manager (FM) | Secures the home — doors, windows, and posted signage — before demo. On-site on demo day alongside or in place of Community Manager. Takes required day-of photos and video. |
| Demo Contractor (Vendor) | Executes demolition under a written scope approved by the Director of Construction. Applies for demo and infill permits. Provides before photos, after photos, debris removal tickets, and haul-off receipts as required deliverables. |

4.  Process Phases & Steps

| PHASE 1 — Pre-Demo Authorization · Owner: Director of Construction |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 1 | Director of Construction | Confirm written demo authorization is in hand — budgeted and signed off by the approving authority. File original in the Construction file; copy to Regional Manager. ▸ IMPORTANT |  |
| 2 | Director of Construction | Update Rent Manager status for the home/lot to 'Lot Demo.' |  |
| 3 | Director of Construction | Create a Rent Manager issue for the lot. Upload current photos and notes documenting the condition of the home. If this is an eviction home, flag it in the issue notes. Eviction flag affects resident notification requirements and documentation standards. |  |
| 4 | Director of Construction | Determine whether residents are present or recently vacated. ▸ DECISION YES → Regional Manager and Community Manager notify residents in writing of the demo plan and timeline before any work begins. NO → No notification required. Proceed to Phase 2. |  |

| PHASE 2 — Safety & Utility Shutoffs · Owner: Director of Construction + Regional Manager (verification) |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 5 | Construction Team | Submit shutoff request to the utility company for power. Document the request confirmation. |  |
| 6 | Director of Construction | Confirm power shutoff is complete and that lock/tagout is in place. File written confirmation. |  |
| 7 | Director of Construction | Coordinate with Facility Manager to cap or disconnect water and sewer lines so no leaks occur during or after demo. |  |
| 8 | Regional Manager + Community Manager | Physically confirm on-site that all utilities — power, water, and sewer — are completely off. Document confirmation in writing. File in the Construction file. |  |

| PHASE 3 — Vendor & Contractor Coordination · Owner: Director of Construction |  |  |  |
| --- | --- | --- | --- |
| # | Who | Action |  |
| 9 | Director of Construction | Approve the contractor bid. |  |
| 10 | Director of Construction | Verify that the contractor's Certificate of Insurance (COI) and applicable permits are on file before the contractor is engaged. ▸ IMPORTANT An uninsured contractor on site violates Parakeet's vendor standards. COI must be on file before any site work begins. |  |
| 11 | Director of Construction | Schedule the demo date and confirm the full scope in writing with the contractor: home structure, skirting, piers, and all debris haul-off. |  |
| 12 | Demo Contractor | Apply for the demo permit and, where applicable, the replacement/infill permit. Director of Construction tracks permit issuance. Contractor is responsible for applying for their own permits. Director of Construction confirms permit is in hand before the demo date. |  |
| 13 | Director of Construction | Confirm in writing with the contractor that before and after photos are required deliverables: before photos prior to demo start, after photos upon completion. |  |

| PHASE 4 — Site Security Before Demo · Owner: Facility Manager (tasks) · Director of Construction (oversight) |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 14 | Facility Manager (FM) | Lock and secure all doors and windows on the home. |  |
| 15 | Facility Manager (FM) | Post a clearly visible "No Trespassing / Demolition Scheduled" sign on the property. |  |
| 16 | Director of Construction | Monitor the demo schedule. If demo is delayed more than 7 days from the originally scheduled date, direct Facility Manager to fence or physically block off the site. |  |

| PHASE 5 — Compliance & Permits · Owner: Director of Construction |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 17 | Director of Construction | Confirm with the contractor that the demo permit has been issued by the jurisdiction, where required. File a copy. |  |
| 18 | Director of Construction | Determine whether the jurisdiction requires asbestos, lead, or pest control testing for this property. ▸ DECISION YES → Order testing through a licensed vendor. Testing must be complete and results received before demo proceeds. NO → Document in the Rent Manager issue that no testing was required for this jurisdiction. |  |
| 19 | Director of Construction | Confirm all test results and permits are in hand before authorizing the demo date to proceed. ▸ IMPORTANT All required testing — asbestos, lead, pest — must be complete before demo begins. When in doubt, test. |  |

| PHASE 6 — Day of Demo · Owner: Community Manager + Facility Manager (on-site) · Director of Construction (oversight) |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 20 | Community Manager (CM) or Facility Manager (FM) | Be on-site when demo begins. Before the contractor starts work, confirm all three pre-demo requirements: (1) all utilities are off, (2) safety signage is posted, (3) contractor has permit and all required paperwork physically in hand. ▸ IMPORTANT If any item is not confirmed, halt demo and notify Director of Construction immediately. |  |
| 21 | Community Manager (CM) or Facility Manager (FM) | Take photos and video documenting: utilities-off confirmation, signage posted, and contractor on-site with permits. File in the Construction file and share with Regional Manager. |  |

| PHASE 7 — Post-Demo Closeout · Owner: Director of Construction + Regional Manager (verification) |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 22 | Director of Construction | Collect from contractor: after photos, debris removal. No closeout is accepted without all three. |  |
| 23 | Director of Construction | Verify the site is graded, cleared of all debris, and safe for access. |  |
| 24 | Director of Construction | Update Rent Manager: change the home/lot status to 'Demo / Vacant Lot.' |  |
| 25 | Facilities Manager | Verify the completed lot via an in-person site visit or a full photo package submitted by the Director of Construction or the contractor. |  |
| 26 | Director of Construction | Confirm infill home has been ordered and lot prep is underway. Close this SOP and hand off to the Infill Home Ordering & Lot Prep SOP. |  |

5.  Forms & Checklists

All documents listed below must be filed in the Construction file in SharePoint. No phase may close without the required documents on file.

| Document / Form | Phase | Filled / Ordered By | Routes To | Notes |
| --- | --- | --- | --- | --- |
| Written Demo Authorization | 1 | Director of Construction (from approving authority) | Construction file; copy to Regional Manager | Must be in hand before any demo work begins. Verbal approval is not sufficient. |
| Rent Manager Issue — 'Lot Demo' | 1 | Director of Construction | Rent Manager | Include current photos, condition notes, and eviction flag if applicable. |
| Resident Notification (written) | 1 | Regional Manager + Community Manager | Residents; copy in Rent Manager notes | Required if occupied or recently vacated. Timeline must be stated. |
| Utility Shutoff Confirmation | 2 | Construction Team | Construction file; Regional Manager sign-off | Lock/tagout confirmed before demo start. No verbal confirmation accepted. |
| Demo Contractor — COI + Permit Verification | 3 | Director of Construction | Construction file | COI and permit copies on file before contractor is engaged. |
| Before Photos | 3 + 6 | Demo Contractor; Community Manager / Facility Manager | Construction file | Taken before demo begins. Required from contractor per written scope. |
| Demo Permit | 5 | Demo Contractor (applied for by vendor) | Construction file; copy to Regional Manager | Contractor holds permit physically on day of demo. |
| Asbestos / Lead / Pest Test Report | 5 | Director of Construction (via licensed vendor) | Construction file; copy to Regional Manager | Required where jurisdiction mandates. Must be complete before demo starts. |
| Day-of Photos + Video | 6 | Community Manager / Facility Manager (on-site) | Construction file; shared with Regional Manager | Documents utilities off, signage posted, contractor on-site with permits. |
| After Photos + Debris Tickets + Haul-off Receipts | 7 | Demo Contractor | Construction file; Regional Manager | All three required before closeout is accepted. No exceptions. |

6.  Related Resources

| Resource | Description |
| --- | --- |
| Infill Home Ordering & Lot Prep SOP | Downstream SOP. Triggered upon Director of Construction closeout of this SOP. |
| Rehab Lifecycle SOP — Path A | Triggered once the new infill home is placed on the cleared lot. |
| Rent Manager | System of record for lot status updates and issue tracking throughout this process. |
| Demo Contractor Vendor File | Held by Director of Construction. Includes COI, bid, written scope, and permit copies. |
| Construction File (SharePoint) | Central repository for all documents, photos, permits, and receipts for each demo project. |

7.  Frequently Asked Questions

Q:  Can demo work begin before written authorization is received?

A:  No. Written authorization must be in hand before any utility shutoff requests, contractor engagement, or physical work begins. A verbal approval is not sufficient and does not protect Parakeet from liability.

Q:  What happens if the jurisdiction does not require an asbestos or lead test?

A:  The Director of Construction documents in the Rent Manager issue that no testing was required for this jurisdiction and proceeds to Phase 6. When in doubt, order testing — the cost is far lower than the cost of a hazmat incident.

Q:  Who is responsible for the demo permit — Parakeet or the contractor?

A:  The Demo Contractor is responsible for applying for the demo permit and any applicable infill permit. The Director of Construction tracks issuance and confirms the permit is physically on-site before demo begins.

Q:  What if the demo is delayed after the contractor is engaged?

A:  If demo is delayed more than 7 days from the originally scheduled date, the Director of Construction directs the Facility Manager to fence or physically block off the site. A posted sign alone is not sufficient for an extended delay.

Q:  Does a cleared lot automatically move to the Infill Home Ordering SOP?

A:  Not automatically. The Director of Construction must confirm all three: (1) infill home has been ordered, (2) Rent Manager status is updated to 'Demo / Vacant Lot,' and (3) the Regional Manager has verified the lot. All three must be true before this SOP closes and the handoff is made.

8.  Review & Revision History

This SOP is reviewed annually by the Director of Construction and Director of Operations, or any time a significant process change occurs.

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 1.0 | August 2026 | Parakeet Construction Dept. | Initial release. Rewritten from original Approved SOP into Parakeet branded format. Roles updated: Director of Construction as process owner; Facility Manager replaces generic Maintenance team. 7 phases, 26 steps, 10 required documents. |

9.  Sign-Off & Distribution

The Director of Construction signs to close this SOP and authorize handoff. The completed closeout package must be distributed to all parties below on the same day as sign-off.

| Director of Construction — Reviewed & Authorized: ______________________________ | Date: ______________________________ |
| --- | --- |
| Regional Manager — Lot Verified: ______________________________ | Date: ______________________________ |

| DISTRIBUTION — Completed closeout package must be shared with all parties below upon Director of Construction sign-off. |  |  |  |
| --- | --- | --- | --- |
| Recipient | Purpose | Date Sent / Acknowledged |  |
| Director of Sales | Informs home selection timeline and site readiness for infill ordering | ______________________________ |  |
| Director of Operations | Coordinates resource planning and confirms lot prep sequencing | ______________________________ |  |
| Asset Management | Updates lot record; files closeout documentation in asset system | ______________________________ |  |