parakeet

Operational Procedure: Demo Home — Lot Prep

Parakeet Communities · Construction SOP

| Process Owner | Construction |
| --- | --- |
| Applies To | Construction, Regional Manager, Community Manager, Maintenance Team, Demo Contractor (vendor) |
| Trigger | TBD Call disposition decision — home/lot assigned to Demo + Infill path |
| Finish Line | Infill home ordered and lot prep underway; Rent Manager status updated to 'Demo / Vacant Lot'; Regional Manager has verified lot via site visit or photo package |
| Triggers Downstream | Infill Home Ordering & Lot Prep SOP; Rehab Lifecycle SOP (Path A) once new home is placed |
| Systems Used | Rent Manager |
| Status | Approved |

# Purpose

This SOP establishes a standardized process for the safe, compliant, and documented demolition of a home and preparation of the lot for an infill replacement unit. Construction owns this process from written authorization through Regional Manager closeout verification. The process ensures that demolition is never started without written approval, all utilities are confirmed off, all required permits and testing are complete, and the lot is properly documented and recorded in Rent Manager before any infill or lot prep work begins.

# Scope

Applies To

All Parakeet community homes and lots where the TBD Call has resulted in a Demo + Infill disposition decision.

Trigger

The TBD Call disposition decision assigns the home/lot to the Demo + Infill path. This SOP begins at that moment. Written demo authorization must be obtained before any physical work begins.

Finish Line

This SOP is complete when: the lot is graded, cleared, and safe; all documentation is filed; Rent Manager status is updated to 'Demo / Vacant Lot'; the Regional Manager has verified the lot via site visit or photo package; and the infill home has been ordered and lot prep is underway. Construction then hands off to the Infill Home Ordering & Lot Prep SOP.

Out of Scope

Infill home selection, purchase, placement, and the subsequent rehab process are covered in separate SOPs. This SOP ends at lot clearance and Regional Manager verification.

Phase 1: Pre-Demo Authorization  ·  Owner: Construction

Objective: Confirm all approvals are in place and Rent Manager is updated before any demo work is initiated.

Tasks

- Construction confirms written demo authorization is in hand — budgeted and signed off by the approving authority. No demo work begins without this document on file.

- Construction updates the Rent Manager status for the home/lot to 'Lot Demo.'

- Construction creates a Rent Manager issue for the lot: uploads current photos and notes documenting the condition of the home. If this is an eviction home, Construction flags this in the notes.

- Regional Manager and Community Manager notify residents of the demo plan and timeline if residents are present or recently vacated.

IMPORTANT: Written authorization must be in hand before any utility shutoff requests, contractor engagement, or physical work begins. A verbal approval is not sufficient.

IMPORTANT: If this is an eviction home, the note must be added to the Rent Manager issue at this step. This affects resident notification requirements and documentation standards.

Resident Notification — Decision

◆ DECISION: Are residents present or recently vacated from the home?

YES → Regional Manager and Community Manager notify residents in writing of the demo plan and timeline before any work begins.

NO  → No notification required. Construction proceeds to Phase 2.

Phase 2: Safety & Utility Shutoffs  ·  Owner: Construction + Regional Manager (verification)

Objective: Confirm all utilities are completely shut off and locked out before any contractor or demo crew sets foot on site.

Tasks

- Construction submits a shutoff request to the utility company for power. Construction confirms the shutoff is completed and that lock/tagout is in place.

- Construction coordinates with Maintenance to cap or disconnect water and sewer lines so that no leaks occur during or after demo.

- Regional Manager and Community Manager must physically double-check and confirm that all utilities — power, water, sewer — are completely off before demo is authorized to begin.

IMPORTANT: Demo does not start until the Regional Manager and Community Manager have confirmed all utilities are off. This confirmation must be documented — verbal sign-off is not accepted. Utility shutoff confirmation is filed in the Construction file.

Phase 3: Vendor & Contractor Coordination  ·  Owner: Construction

Objective: Engage the demo contractor with a fully approved bid, verified insurance and permits, and a confirmed scope covering the complete demolition.

Tasks

- Construction approves the contractor bid. Construction verifies that the contractor's Certificate of Insurance and applicable permits are on file before the contractor is engaged.

- Construction schedules the demo date and confirms the full scope in writing with the contractor: home structure, skirting, piers, and all debris haul-off.

- The contractor applies for the demo permit and, where applicable, the replacement/infill permit. Construction tracks permit issuance.

- Construction confirms with the contractor in writing that before and after photos are required deliverables. Contractor must provide before photos prior to demo start and after photos upon completion.

IMPORTANT: The contractor's Certificate of Insurance must be on file before any site work begins. An uninsured contractor on site is a liability and a violation of Parakeet's vendor standards. Construction is responsible for verifying this before contractor engagement.

NOTE: The contractor is responsible for applying for their own permits. Construction tracks issuance and confirms the permit is in hand before the demo date.

Phase 4: Site Security Before Demo  ·  Owner: Maintenance (tasks) · Construction (oversight)

Objective: Secure the site so that no unauthorized person can enter between authorization and demo start.

Tasks

- Maintenance locks and secures all doors and windows on the home.

- Maintenance posts a clearly visible 'No Trespassing / Demolition Scheduled' sign on the property.

- Construction monitors the demo schedule. If the demo is delayed by more than 7 days from the originally scheduled date, Construction directs Maintenance to fence or block off the site so that entry is physically prevented.

IMPORTANT: If demo is delayed more than 7 days, the site must be fenced or physically blocked. A sign alone is not sufficient for an extended delay. Construction is responsible for tracking the schedule and triggering this step.

Phase 5: Compliance & Permits  ·  Owner: Construction

Objective: Confirm all regulatory requirements are satisfied before demo day — permits issued, required testing complete.

Tasks

- Construction confirms with the contractor that the demo permit has been issued by the jurisdiction, where required. Construction files a copy.

- Construction orders asbestos, lead, and pest control testing through a vendor where required by the city or county. Construction receives and files test results.

- Construction confirms all test results and permits are in hand before authorizing the demo date to proceed.

IMPORTANT: All required testing — asbestos, lead, pest — must be complete and results received before demo begins. Construction is responsible for knowing the local jurisdiction's requirements for each property. When in doubt, test.

◆ DECISION: Does the jurisdiction require asbestos/lead/pest testing for this property?

YES → Construction orders testing via vendor. Testing must be complete and results received before demo proceeds.

NO  → Construction documents in the Rent Manager issue that no testing was required for this jurisdiction and proceeds to Phase 6.

Phase 6: Day of Demo  ·  Owner: Community Manager + Maintenance (on-site) · Construction (oversight)

Objective: Confirm all pre-demo requirements are met on demo day before the contractor begins work.

Tasks

- Community Manager or Maintenance must be on-site when demo begins. They confirm the following before the contractor starts: all utilities are off; safety signage is posted; the contractor has their permit and all required paperwork physically on hand.

- Community Manager or Maintenance takes photos and video at the start of demo documenting: utilities-off confirmation, signage posted, contractor on-site with permits.

- Photos and video are filed in the Construction file and shared with the Regional Manager.

IMPORTANT: Demo does not start until Community Manager or Maintenance has physically confirmed all three items: utilities off, signage posted, contractor has permits. If any item is not confirmed, demo is halted and Construction is notified immediately.

NOTE: Community Manager or Maintenance are the eyes on the ground on demo day. Construction is accountable for ensuring the on-site team knows what to verify before the contractor starts work.

Phase 7: Post-Demo Closeout  ·  Owner: Construction + Regional Manager (verification)

Objective: Confirm the site is properly cleared and documented, update Rent Manager, and obtain Regional Manager verification before this SOP closes.

Tasks

- Construction collects from the contractor: after photos, debris removal tickets, and haul-off receipts. No closeout is accepted without all three.

- Construction verifies the site is graded, cleared of all debris, and safe for access.

- Construction updates Rent Manager: changes the home/lot status to 'Demo / Vacant Lot.'

- Regional Manager verifies the completed lot via an in-person site visit or a full photo package submitted by Construction or the contractor.

- Construction confirms the infill home has been ordered and lot prep is underway, formally closing this SOP and handing off to the Infill Home Ordering & Lot Prep SOP.

IMPORTANT: Contractor must provide debris removal tickets and haul-off receipts. A contractor claim that debris was removed without documentation is not accepted. Construction holds the contractor to this requirement before final payment or closeout.

➤ HANDOFF: Regional Manager verification of lot clearance + Rent Manager status 'Demo / Vacant Lot' + infill home ordered → hands off to the Infill Home Ordering & Lot Prep SOP.

# Forms & Checklists

| Document / Form | Phase | Filled / Ordered By | Routes To | Notes |
| --- | --- | --- | --- | --- |
| Written Demo Authorization | Phase 1 | Construction (obtained from approving authority) | Construction file; copy to Regional Manager | Must be in hand before any demo work begins. Linked. |
| Rent Manager Issue — Lot Demo | Phase 1 | Construction | Rent Manager (visible to Operations + Regional Manager) | Include photos, notes, and flag if eviction home. Status: 'Lot Demo.' |
| Resident Notification (written) | Phase 1 | Regional Manager + Community Manager | Residents; copy retained in Rent Manager notes | Required if occupied or recently vacated. Timeline must be stated. |
| Utility Shutoff Confirmation | Phase 2 | Construction | Construction file; Regional Manager sign-off | Lock/tagout must be confirmed before demo start. No verbal confirmation accepted. |
| Demo Contractor — Insurance + Permit Verification | Phase 3 | Construction | Construction file | COI and permit copies on file before contractor is engaged. |
| Demo Permit | Phase 5 | Contractor (applied for by vendor) | Construction file; copy to Regional Manager | Required where jurisdiction mandates. Contractor holds on day of demo. |
| Asbestos / Lead / Pest Test Report | Phase 5 | Construction (via vendor) | Construction file; copy to Regional Manager | Required where city/county mandates. Must be complete before demo start. |
| Before Photos | Phase 3 + 6 | Contractor; Community Manager / Maintenance | Construction file | Taken before demo begins. Required from contractor per contract. |
| Day-of Photos / Videos | Phase 6 | Community Manager / Maintenance on-site | Construction file; Regional Manager | Document utilities off, signage posted, contractor on-site with permits. |
| After Photos + Debris Tickets + Haul-off Receipts | Phase 7 | Contractor | Construction file; Regional Manager for verification | Contractor must provide before closeout is accepted. No receipt = no closeout. |
| Rent Manager Status Update — Demo / Vacant Lot | Phase 7 | Construction | Rent Manager | Final status change. Triggers visibility for infill and lot prep planning. |

# Roles & Accountability (RACI)

R = Responsible (does the work)  ·  A = Accountable (owns the outcome)  ·  C = Consulted  ·  – = Not involved

| Activity | Construction | Regional Mgr | Comm. Mgr | Maintenance | Vendor |
| --- | --- | --- | --- | --- | --- |
| PHASE 1: PRE-DEMO AUTHORIZATION |  |  |  |  |  |
| TBD Call disposition decision triggers SOP | R | R | C | – | – |
| Confirm written demo approval (budgeted + signed) | A/R | C | – | – | – |
| Update Rent Manager status to 'Lot Demo' | A/R | C | – | – | – |
| Create Rent Manager issue; upload photos + notes | A/R | – | – | – | – |
| Notify residents of demo plan and timeline | C | A/R | R | – | – |
| PHASE 2: SAFETY & UTILITY SHUTOFFS |  |  |  |  |  |
| Submit utility shutoff request (power) | A/R | – | – | – | – |
| Confirm power shutoff + lock/tagout in place | A/R | C | – | – | – |
| Cap or disconnect water/sewer lines | A/R | – | – | R | – |
| Double-check and confirm ALL utilities are OFF | C | A/R | R | – | – |
| PHASE 3: VENDOR & CONTRACTOR COORDINATION |  |  |  |  |  |
| Approve contractor bid; verify insurance + permits | A/R | C | – | – | – |
| Schedule demo date; confirm full scope | A/R | C | – | – | R |
| Contractor applies for demo + replacement permit | – | – | – | – | A/R |
| Confirm before/after photo requirement with contractor | A/R | – | – | – | C |
| PHASE 4: SITE SECURITY BEFORE DEMO |  |  |  |  |  |
| Lock and secure all doors and windows | C | – | – | A/R | – |
| Post no-trespassing / demolition signage | C | – | – | A/R | – |
| Fence or block site if demo delayed 7+ days | A/R | C | – | R | – |
| PHASE 5: COMPLIANCE & PERMITS |  |  |  |  |  |
| Confirm demo permit issued (if required) | A/R | C | – | – | – |
| Order asbestos/lead/pest testing via vendor | A/R | – | – | – | R |
| Receive and file test results | A/R | C | – | – | – |
| PHASE 6: DAY OF DEMO |  |  |  |  |  |
| Confirm utilities OFF on day of demo | C | A | R | R | – |
| Confirm safety signage is posted | C | C | R | R | – |
| Confirm contractor has permits + paperwork | A/R | C | – | – | C |
| Take photos/videos of demo in progress | C | – | R | R | – |
| PHASE 7: POST-DEMO CLOSEOUT |  |  |  |  |  |
| Contractor provides after photos, debris tickets + receipts | A/R | – | – | – | R |
| Confirm site is graded, cleared, and safe | A/R | C | – | – | – |
| Update Rent Manager status to 'Demo / Vacant Lot' | A/R | C | – | – | – |
| Regional Manager verifies via site visit or photo package | C | A/R | – | – | – |
| Handoff: infill home ordered + lot prep begins | A/R | C | – | – | – |

# Standard Requirements

- Written demo authorization must be in hand before any utility shutoffs, contractor engagement, or physical work begins.

- Rent Manager must be updated to 'Lot Demo' before Phase 2 begins. All documentation — photos, notes, eviction flag — must be in the Rent Manager issue.

- All utilities must be confirmed off by Regional Manager and Community Manager before demo starts. Verbal confirmation is not accepted.

- Contractor insurance (Certificate of Insurance) and permits must be verified and on file before contractor is engaged.

- All required asbestos, lead, and pest testing must be complete and results received before demo proceeds.

- Community Manager or Maintenance must be on-site at demo start. Demo does not begin until all three day-of checks are confirmed: utilities off, signage posted, contractor has permits.

- Contractor must provide before photos, after photos, debris removal tickets, and haul-off receipts. Closeout is not accepted without all four.

- Regional Manager must verify lot clearance via site visit or full photo package before this SOP is closed.

- Rent Manager status must be updated to 'Demo / Vacant Lot' before handoff to the next SOP.

- If demo is delayed more than 7 days, the site must be physically fenced or blocked — signage alone is not sufficient.

# Frequently Asked Questions

| Question | Answer |
| --- | --- |
| What if the demo contractor says testing is not required? | The contractor's opinion does not override Parakeet's requirement to verify local jurisdiction rules independently. Construction is responsible for confirming the regulatory requirement — not the contractor. When in doubt, Construction orders the testing. |
| What if utilities cannot be confirmed off before demo day? | Demo does not proceed. Construction is notified immediately. The demo date is rescheduled and the contractor is informed. A demo that begins with live utilities is a safety violation and a liability — there are no exceptions to this rule. |
| Who is responsible if the contractor does not provide debris tickets or haul-off receipts? | Construction is accountable for collecting this documentation before closeout is accepted and before any final payment is made to the contractor. If the contractor fails to provide it, Construction withholds closeout sign-off and escalates. |
| What if the home is an eviction property — does anything change? | The process steps are the same, but the eviction flag must be noted in the Rent Manager issue at Phase 1. This flag may trigger additional resident notification obligations — Regional Manager confirms requirements with Operations before notification goes out. |
| What triggers the handoff to the next SOP? | Four conditions must all be true: (1) lot is graded, cleared, and safe; (2) Rent Manager status is 'Demo / Vacant Lot'; (3) Regional Manager has verified lot via site visit or photo package; and (4) infill home has been ordered and lot prep is underway. All four must be met before Construction closes this SOP. |

# Review & Revision

| Date | Author | Changes |
| --- | --- | --- |
| June 2026 | Construction | Initial draft. Process documented from TBD Call disposition decision through lot clearance, Rent Manager update, and Regional Manager verification. Handoff to Infill Home Ordering & Lot Prep SOP. |