PARAKEET COMMUNITIES Standard Operating Procedure · CONST-003 Site Condition Assessment · Part 1: Pre-Permit Site Evaluation

| SOP Title | Site Condition Assessment — Pre-Permit Site Evaluation |
| --- | --- |
| SOP ID | CONST-003 |
| Version | 3.0 |
| Effective Date | August 2026 |
| Process Owner | Director of Construction |
| Auditor Role | Facility Manager (FM) |
| Audit Stage | Pre-permit — before any home is selected or permits are pulled |
| Triggers Downstream | Site Approval & Permitting SOP · Director of Sales · Director of Operations · Asset Management |

1.  Purpose

To evaluate and document existing lot conditions before any home is selected or permits are pulled — confirming that the site is physically suitable for new home placement and identifying any demolition, utility, grading, or environmental work required prior to permitting. The Director of Construction schedules assessments; the Facility Manager conducts and documents them.

2.  Scope

| Applies To | Every lot being evaluated for new home placement — manufactured/mobile or site-built — across all Parakeet Communities properties. |
| --- | --- |
| Auditor | Director of Construction, Facility Manager (FM) |
| Trigger | Director of Construction identifies a lot for potential new home placement. |
| Finish Line | Facility Manager completes and submits the Site Condition Assessment. Director of Construction reviews findings and determines next steps. |
| Does NOT Cover | Permit applications · Home selection · Foundation or pad construction · Installation inspections |

3.  Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Director of Construction | Identifies lots for potential new home placement. Schedules site condition assessments with Facility Managers. Reviews completed assessments and determines whether to proceed to permitting or address site issues first. |
| Facility Manager (FM) | Conducts the on-site condition assessment. Completes, signs, and submits the Site Condition Assessment checklist. Documents all existing utility conditions, grading concerns, demo requirements, and site constraints. |
| Regional Manager | Receives completed checklist. Notified immediately of any Fail items. Acknowledges receipt and files checklist in SharePoint. |
| Vendor / Contractor | Completes all deficiency remediation identified on the punch list before re-inspection. |

4.  Process Phases & Steps

| PHASE 1 — Assessment Setup |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 1 | Director of Construction | Identify lot for potential new home placement and schedule site condition assessment with Facility Manager. |  |
| 2 | Facility Manager (FM) | Obtain any available lot information: survey, zoning map, prior utility records, community site plan. Not required — document what is available; gaps will be noted in the assessment. |  |
| 3 | Facility Manager (FM) | Confirm lot is accessible and safe to enter. Print or open the Site Condition Assessment checklist (Section 5). |  |

| PHASE 2 — On-Site Condition Assessment |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 4 | Facility Manager (FM) | Check for existing structures or abandoned homes on the lot. Document demo requirements if applicable. If demo is needed, note scope, estimated effort, and any underground hazards in Section A. |  |
| 5 | Facility Manager (FM) | Walk all 8 checklist sections (A–H) and mark each item Yes, No, or N/A. Yes = condition confirmed / acceptable. No = issue identified — written note required. N/A = not applicable to this lot. |  |
| 6 | Facility Manager (FM) | Photograph and document all existing utility connections, grading conditions, setback measurements, and any concerns. Photos must be dated. Upload to SharePoint with completed checklist. |  |
| 7 | Facility Manager (FM) | Record specific observations and measurements in the Notes column for every item — especially utilities and setbacks. |  |

| PHASE 3 — Documentation & Submission |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 8 | Facility Manager (FM) | Review completed checklist. Determine overall site status: ▸ DECISION PROCEED = site is ready for permitting. ISSUES IDENTIFIED = remediation or further evaluation needed before permitting. |  |
| 9 | Facility Manager (FM) | Sign and date the completed assessment. Email or upload to Director of Construction within 24 hours. |  |

| PHASE 4 — Director Review & Decision |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 10 | Director of Construction | Review completed Site Condition Assessment. Determine next step: ▸ DECISION PROCEED TO PERMITTING = no blocking issues. REMEDIATE FIRST = address Fail items before permits are pulled. DO NOT PROCEED = site is not suitable. |  |
| 11 | Director of Construction | If remediation required: issue written scope to responsible vendor and set timeline. |  |
| 12 | Facility Manager (FM) | If remediation required: confirm completion on site and update assessment notes. Notify Director of Construction. |  |
| 13 | Director of Construction | File completed assessment in SharePoint. Distribute signed assessment to Director of Sales, Director of Operations, and Asset Management. Authorize Facility Manager to proceed to permitting phase. ▸ HANDOFF HANDOFF — Assessment valid 90 days. Director of Sales: informs home selection timeline. Director of Operations: coordinates resource planning. Asset Management: updates lot record. |  |

5.  Site Condition Assessment Checklist

Complete a new assessment for each lot being evaluated. All Fail items must be reviewed by the Director of Construction before permits are pulled. Assessment is valid for 90 days from Facility Manager signature date.

INSTRUCTIONS: Mark each item Yes (condition confirmed / acceptable), No (issue identified), or N/A. Every No requires a written note in the Notes column. Photograph each section and upload with completed checklist.

| PRE-AUDIT GATE: Is there a vacant or existing home on this lot that must be demolished before new home placement? ☐ No — proceed with site audit. ☐ Yes — STOP. Demo must be completed, debris removed, and lot cleared before this audit may be conducted. Do not schedule delivery until demo is confirmed complete. |  |  |  |  |
| --- | --- | --- | --- | --- |
| DEMO DOCUMENTATION — Complete this section if an existing home is present on the lot. Form should still be completed in full. |  |  |  |  |
| Existing Home Description (type, size, condition) ______________________________________ |  | Year / Make / Model (if known) ______________________________________ |  |  |
| Estimated Demo Scope ______________________________________ |  | Hazardous Materials Concerns (asbestos, lead paint — note if unknown) ______________________________________ |  |  |
| Utilities to Disconnect Before Demo (electric, water, gas, sewer) ______________________________________ |  | Demo Contractor / Responsible Party ______________________________________ |  |  |
| Estimated Demo Completion Date ______________________________________ | Demo Authorized By (Director of Construction) ______________________________________ |  | Photos Taken? ☐ Yes ☐ No ______________________________________ |  |

| Community / Property ______________________________ | Lot Number ______________________________ |
| --- | --- |

| Facility Manager ______________________________ | Inspection Date ______________________________ |
| --- | --- |

| Scheduled Install Date ______________________________ | Home Type ☐ Manufactured ☐ Site-Built ______________________________ |
| --- | --- |

| Assessment Item | Yes | No | N/A | Notes / Observations |
| --- | --- | --- | --- | --- |
| A · EXISTING STRUCTURES & DEMO |  |  |  |  |
| A1 Lot is clear of structures, debris, and abandoned vehicles — or demo plan is confirmed in writing with Director of Construction | ☐ | ☐ | ☐ |  |
| A2 If structure present: demo scope, timeline, and responsible party documented | ☐ | ☐ | ☐ |  |
| A3 Underground hazards identified and noted (old foundations, buried tanks, cisterns, septic remnants) | ☐ | ☐ | ☐ |  |
| B · LOT GRADING & DRAINAGE |  |  |  |  |
| B1 No active drainage problems, standing water, or flood-prone low spots observed | ☐ | ☐ | ☐ |  |
| B2 Soil condition is stable — no signs of settlement, sinkholes, soft spots, or erosion | ☐ | ☐ | ☐ |  |
| C · SETBACKS & SITE DIMENSIONS |  |  |  |  |
| C1 Lot dimensions sufficient for target home size — confirmed against site evaluation form (note usable footprint in Notes) | ☐ | ☐ | ☐ |  |
| C2 Front setback meets local zoning minimum — measured and recorded | ☐ | ☐ | ☐ |  |
| C3 Side and rear setbacks meet local zoning minimums — measured and recorded | ☐ | ☐ | ☐ |  |
| C4 No encroachments from neighboring structures, fences, or overhead lines into buildable area | ☐ | ☐ | ☐ |  |
| D · ELECTRICAL SERVICE |  |  |  |  |
| D1 Existing electrical service on lot: assessed and documented (present / absent / condition / location) — Meter #: _______________ | ☐ | ☐ | ☐ |  |
| D2 Service capacity adequate for planned home — or upgrade requirement identified and noted | ☐ | ☐ | ☐ |  |
| D3 Overhead electrical clearance from proposed home placement is acceptable | ☐ | ☐ | ☐ |  |
| E · WATER SERVICE |  |  |  |  |
| E1 Existing water service on lot: source, location, and condition documented (municipal / well) — Meter #: _______________ | ☐ | ☐ | ☐ |  |
| E2 Water service route to proposed home location is feasible | ☐ | ☐ | ☐ |  |
| F · SEWER / SEPTIC |  |  |  |  |
| F1 Existing sewer lateral or septic system: location and condition documented (municipal / septic / none) | ☐ | ☐ | ☐ |  |
| F2 Sewer / septic capacity adequate for planned home — or new install / upgrade requirement noted | ☐ | ☐ | ☐ |  |
| F3 No signs of sewer backup, odors, wet spots, or septic failure in area | ☐ | ☐ | ☐ |  |
| G · GAS / PROPANE (mark N/A if all-electric) |  |  |  |  |
| G1 Existing gas or propane service on lot: type, location, and condition documented — Meter #: _______________ | ☐ | ☐ | ☐ |  |
| G2 Gas / propane feasibility confirmed for proposed home — or all-electric noted | ☐ | ☐ | ☐ |  |
| H · ENVIRONMENTAL & SAFETY |  |  |  |  |
| H1 FEMA flood zone designation confirmed — lot is buildable; flood insurance requirement noted if applicable | ☐ | ☐ | ☐ |  |
| H2 No signs of hazardous materials, soil contamination, or environmental concerns on site | ☐ | ☐ | ☐ |  |
| H3 No protected wetlands, conservation easements, or deed restrictions impacting buildable area | ☐ | ☐ | ☐ |  |

| ☐ PROCEED TO PERMITTING All items Yes or N/A. No blocking conditions identified. | ☐ ISSUES IDENTIFIED Items marked No identified. See notes below. Director of Construction review required before permitting. |
| --- | --- |

Notes on Items Marked "No" (attach additional pages as needed)

| Facility Manager Signature: ______________________________ | Date: ______________________________ |
| --- | --- |
| Director of Construction — Reviewed & Authorized: ______________________________ | Date: ______________________________ |

| DISTRIBUTION — Completed assessment must be shared with all parties below upon Director of Construction sign-off. |  |  |  |
| --- | --- | --- | --- |
| Recipient | Purpose | Date Sent / Acknowledged |  |
| Director of Sales | For awareness of lot timeline and home selection readiness | ______________________________ |  |
| Director of Operations | For resource planning and coordination of remediation if required | ______________________________ |  |
| Asset Management | To update lot record and file assessment in asset documentation | ______________________________ |  |

6.  Related Resources

| Resource | Description |
| --- | --- |
| Site Approval Checklist Form | Embedded in this SOP (Section 5). Print or complete digitally per site. |
| Approved Site Plan | Issued by local authority. Required before audit begins. |
| Photo Documentation Log | Dated site photos uploaded to SharePoint after each audit. |
| Home Installation / Placement SOP | Next downstream SOP. Triggered upon site approval. |
| HUD Installation Standards (CFR 3285) | Federal standards for manufactured home installation. |

7.  Frequently Asked Questions

Q:  What if we cannot determine whether an existing utility line is active?

A:  Mark the item Fail and note "status unknown — requires utility locate or inspection" in the Notes column. Do not assume a line is active or inactive. The Director of Construction will determine whether to commission a utility locate before proceeding to permitting.

Q:  Does every Fail item mean the lot cannot be used?

A:  No. A Fail item means a condition exists that must be addressed or evaluated before permits are pulled — not necessarily that the lot is unsuitable. The Director of Construction reviews all Fail items and decides whether to remediate, adjust the home placement plan, or pass on the lot.

Q:  How long is a Site Condition Assessment valid?

A:  A completed and signed assessment is valid for 90 days. If permits are not pulled within 90 days, the Facility Manager should re-walk the lot to confirm conditions have not changed before proceeding.

Q:  Is an assessment required for a lot where a home is being replaced?

A:  Yes. Any time an existing home is removed and a new home is planned for the same lot, the Facility Manager must complete a new Site Condition Assessment — existing utility conditions and setbacks should be re-confirmed against current requirements.

8.  Review & Revision History

This SOP is reviewed annually by the Construction Manager and Director of Operations, or any time a significant process change occurs.

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 3.0 | August 2026 | Parakeet Construction Dept. | Consolidated B section to 2 items (removed natural grade and delivery access). Removed E3 (pressure/flow). C1 updated to reference site evaluation form. Meter # fields added for D1, E1, G1. Status language changed from Pass/Fail to Yes/No. Signature block updated: Director of Construction replaces Regional Manager. |