PARAKEET COMMUNITIES Standard Operating Procedure · CONST-004 New Home Readiness Workflow · Phase 1: Installation Gate · Phase 2: Buyer's-Eye Walk

| SOP Title | New Home Readiness Workflow |
| --- | --- |
| SOP ID | CONST-203 |
| Version | 1.0 |
| Effective Date | August 2026 |
| Process Owner | Director of Construction |
| Participating Roles | Facility Manager · Community Manager · Sales Representative |
| Triggers Downstream | Home Listing Process · Manufacturer Warranty Claim · Vendor Punch-Out |

1.  Purpose

To ensure every new home placement moves through a structured two-phase sign-off before any home is listed, shown, or handed to a resident. Phase 1 confirms that the home is safely and correctly installed (the Construction Gate). Phase 2 confirms that the home is ready from a buyer's perspective (the Ops & Sales Walk). No home advances to listing without both gates cleared and documented.

2.  Scope

| Applies To | All new home placements across Parakeet Communities. |
| --- | --- |
| Trigger | Vendor emails Director of Construction to confirm the home is set on the lot and ready for Phase 1 inspection. |
| Finish Line | All Phase 2 issues are resolved or formally routed; Community Manager submits the Home Listing JotForm; home is cleared for active listing and showing. |
| Does NOT Cover | Site evaluation and permitting (see CONST-202) · Demo and lot prep (see CONST-200) · Move-out or turnover processes. |

3.  Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Vendor / Set Crew | Sets the home on lot. Emails Director of Construction when home is ready for inspection. Corrects any installation issues identified during Phase 1 or Phase 2. |
| Director of Construction | Receives vendor notification. Notifies Facility Manager to begin Phase 1 inspection. Reviews and approves the Phase 1 JotForm. Routes Phase 1 failures back to the vendor for correction. |
| Facility Manager | Conducts the Phase 1 on-site installation inspection using the Construction/Installation checklist. Submits Phase 1 JotForm to Director of Construction for approval. |
| Community Manager | Receives Phase 1 clearance notification. Schedules and leads the Phase 2 buyer's-eye walk. Logs all Phase 2 issues in JotForm and opens corresponding work orders in Rent Manager. Routes issues to manufacturer or vendor. Submits Home Listing JotForm when all issues are resolved. |
| Sales Representative | Participates in the Phase 2 buyer's-eye walk alongside the Community Manager. Participates in re-walk after issues are resolved. |
| Manufacturer | Receives warranty defect submissions from Director of Sales/Director of Construction. Responds and completes repairs per warranty terms. |

4.  Process Phases & Steps

| PHASE 1 — Home Set Notification |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 1 | Vendor / Set Crew | Set home on lot per installation specifications. |  |
| 2 | Vendor / Set Crew | Email Director of Construction to confirm home is set and ready for Phase 1 inspection. ▸ HANDOFF Email subject should include: community name, lot number, and date set. This email is the official start trigger for the workflow. |  |
| 3 | Director of Construction | Receive vendor email and notify Facility Manager via email to schedule and begin Phase 1 inspection. ▸ IMPORTANT IMPORTANT: Phase 1 inspection must be completed within 1 week of receiving vendor notification. |  |

| PHASE 2 — Phase 1: Installation Inspection |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 4 | Facility Manager | Complete the Construction/Installation checklist on-site, verifying all structural, mechanical, and systems items. |  |
| 5 | Facility Manager | Submit completed checklist to Director of Construction via Phase 1 JotForm submitted for review and approval. ▸ HANDOFF HANDOFF — Director of Construction receives submission for review. |  |
| 6 | Director of Construction | Review Phase 1 JotForm submission and determine status: ▸ DECISION All items pass → approve JotForm and proceed to Step 7. ¦ Items fail → email vendor/set crew with written list of failed items for correction; Facility Manager re-inspects after corrections are made; return to Step 5. |  |
| 7 | Director of Construction | Approve Phase 1 JotForm. JotForm automatically notifies Construction, Operations, and Sales that Phase 1 is complete and the home has cleared the installation gate. ▸ HANDOFF HANDOFF — Construction, Operations, and Sales each receive Phase 1 clearance notification. Phase 2 may now begin. |  |

| PHASE 3 — Phase 2: Buyer's-Eye Walk |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 8 | Community Manager | Receive Phase 1 JotForm clearance notification and schedule Phase 2 walk. ▸ IMPORTANT IMPORTANT: Phase 2 walk must be completed within 1 week of Phase 1 clearance notification. |  |
| 9 | Community Manager / Sales Representative | Walk the home together using the Ops & Sales checklist — evaluating the home through the eyes of a prospective buyer. Focus: Does the home look, feel, and function the way a buyer would expect? Presentation, cleanliness, operation of all systems, curb appeal, and odor. |  |
| 10 | Community Manager | Log all identified issues in the Phase 2 JotForm and open a corresponding work order in Rent Manager for each issue. Each Rent Manager work order must include: location, description, photos, and category (manufacturer defect or installation/set crew issue). |  |
| 11 | Community Manager | Categorize each issue and determine routing: ▸ DECISION Warranty defect (cracks in walls, factory defect, appliance malfunction) → route to manufacturer (Step 12). ¦ Hook-up or installation issue (connection, sealing, leveling, on-site work) → route to vendor/set crew (Step 13). |  |

| PHASE 4 — Issue Resolution & Routing |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 12 | Community Manager | Submit warranty defects to Director of Sales/ Director of Operations/ Director of Construction via email. [TBD — confirm the number of days from home delivery within which defects must be reported to preserve warranty coverage.] Copy Director of Construction on all manufacturer submissions. |  |
| 13 | Regional Manager | Email Director of Operations and Director of Construction with written list of installation issues requiring correction. Include photos and Rent Manager work order numbers in the email. Be specific about each item: location, description, and expected resolution. |  |
| 14 | Manufacturer / Vendor | Complete repairs or corrections and notify Community Manager that work is finished. |  |
| 15 | Community Manager / Sales Representative | Conduct re-walk to verify all reported issues have been fully resolved. |  |
| 16 | Community Manager | Assess re-walk results: ▸ DECISION All issues resolved → update Rent Manager work orders to closed; proceed to Phase 5. ¦ Issues remain → return to Step 12 or Step 13 as applicable; document in Rent Manager. |  |

| PHASE 5 — Home Listing Clearance |  |  |
| --- | --- | --- |
| # | Who | Action |  |
| 17 | Community Manager | Confirm all Phase 2 issues are resolved and all Rent Manager work orders are closed. |  |
| 18 | Community Manager | Submit the Home Listing JotForm to formally clear the home for listing and showing. ▸ HANDOFF HANDOFF — Submission triggers the Home Listing process. Home is now eligible for active listing, marketing, and showing. |  |

5.  Forms & Checklists

| Form / Checklist | Filled By | Approver / Routing | System |
| --- | --- | --- | --- |
| Phase 1 Construction/ Installation Checklist | Facility Manager | Director of Construction approves. JotForm auto-notifies Construction, Ops, and Sales upon approval. | JotForm |
| Phase 2 Ops & Sales Checklist | Community Manager / Sales Representative | Issues logged in Rent Manager. Routed to manufacturer or vendor/set crew by Community Manager. | JotForm + Rent Manager |
| Home Listing JotForm | Community Manager | Submitted after all Phase 2 issues are resolved. Triggers home listing process. | JotForm |

6.  Key Notes & Common Pitfalls

▸ IMPORTANT Interdepartmental communication failure is the most common breakdown in this process. The Phase 1 JotForm auto-notification is the official handoff signal — do not assume another department knows the home is ready. If the JotForm has not been received, Phase 2 does not start.

▸ IMPORTANT Phase 2 cannot begin until the Director of Construction has approved the Phase 1 JotForm and all failed items have been corrected and re-inspected. Do not conduct the buyer's-eye walk on a home that has not cleared the installation gate.

▸ NOTE When categorizing Phase 2 issues: hook-up and on-site installation problems are the responsibility of the vendor/set crew. Warranty items — including cracks in walls, factory defects, and appliance malfunctions — go to the manufacturer. When in doubt, consult the Director of Construction before routing.

▸ NOTE [TBD] Confirm the manufacturer warranty reporting window — the number of days from home delivery within which defects must be submitted to preserve warranty coverage. Until confirmed, submit all defect claims as soon as they are identified.

7.  Related Resources

| Resource | Description |
| --- | --- |
| Phase 1 Construction/Installation Checklist | Completed by Facility Manager during Phase 1 on-site inspection. |
| Phase 2 Ops & Sales Checklist | Completed by Community Manager and Sales Representative during Phase 2 buyer's-eye walk. |
| Home Listing JotForm | Submitted by Community Manager upon Phase 2 clearance to trigger the listing process. |
| Rent Manager | Used to open and track work orders for all Phase 2 issues. |
| Manufacturer Warranty Portal | Used (where applicable) to submit warranty defect claims. Email used as fallback. |
| CONST-002 Demo to Infill SOP | Upstream SOP covering demolition and lot preparation prior to home placement. |
| CONST-003 Site Condition Assessment | Upstream SOP covering site evaluation and permitting prior to home placement. |

8.  Frequently Asked Questions

Q:  Can Phase 2 begin before Phase 1 is fully approved?

A:  No. Phase 2 cannot begin until the Director of Construction has approved the Phase 1 JotForm and all failed items have been corrected and re-inspected. The Phase 1 JotForm auto-notification is the official clearance signal. If it has not been received, the Phase 2 walk should not be scheduled.

Q:  How do I know whether to route a Phase 2 issue to the manufacturer or the vendor?

A:  Hook-up and on-site installation work — connections, sealing, leveling, tie-downs — are the responsibility of the vendor/set crew. Warranty items — cracks in walls, factory defects in cabinetry or fixtures, appliance malfunctions that are not installation-related — go to the manufacturer. When in doubt, consult the Director of Construction before routing the issue.

Q:  What if the manufacturer or vendor does not respond after an issue is submitted?

A:  [TBD — escalation path for non-responsive manufacturer or vendor to be defined. Until confirmed, notify the Director of Construction and document the non-response in Rent Manager.]

9.  Review & Revision History

This SOP is reviewed annually by the Director of Construction and Director of Operations, or any time a significant process change occurs.

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 1.0 | August 2026 | Natalie, Parakeet Communities | Initial draft. Two-phase JotForm-based workflow: Phase 1 Construction Gate (Facility Manager + Director of Construction) and Phase 2 Buyer's-Eye Walk (Community Manager + Sales Representative). Manufacturer warranty window TBD. |