SOP: Utility Activation — New Infill Homes

Parakeet Communities  ·  Construction / Accounting

| Applies To | All new infill homes |
| --- | --- |
| Process Owner | Construction |
| Utility Execution | Accounting — responsible for all utility activations and account requests |
| Trigger | Home assigned to a lot (MRB created) OR home delivery scheduled — whichever comes first |
| Finish Line | All utilities verified live; Rent Manager updated; Operations and Sales notified |
| Last Revised | _________________ |

PURPOSE

Ensure all new infill homes have utilities activated on time to support home delivery, set, punchlist, showings, and sale. Construction owns and drives this process. Accounting executes all utility activations and account setup. Utilities must be proactive — not reactive.

OWNERSHIP

| Role | Responsibility |
| --- | --- |
| Construction | Process owner. Confirms utility requirements, submits Form, verifies utilities live at delivery and set, updates Rent Manager, notifies teams. |
| Accounting | Execute all utility activations and account requests. Contacts providers, opens accounts in Parakeet's name, confirms account details, coordinates meter installs, notifies Construction when utilities are live. |
| Derek | Tracks Form submissions; verify Rent Manager entries against tracking log. |
| Sales | Coordinates showing and sale timing; confirms utilities are live before showings. |
| Operations | Confirms utilities during walkthroughs. |

ACCOUNTING: Construction submits the Form — Accounting takes it from there.

TRIGGER

This process begins when a home is assigned to a lot (Issue created) OR when home delivery is scheduled — whichever comes first. Do not wait until delivery week to initiate utility setup. Lead times for new meter installs can be significant.

PROCESS

Step 1.  Confirm Utility Requirements

Owner: Construction

- Identify all utilities needed for the lot: Electric, Water, Sewer/Septic, Gas (if applicable).

- Confirm utility providers for each service at the lot address.

- Determine meter status:

  - Existing meter → activate or transfer

  - No meter → new install required. Flag this immediately on the JotForm — new meter installs have significant lead times.

Step 2.  Submit Utility JotForm

Owner: Construction

- Complete and submit the Utility Form. Include:

  - Property and lot number

  - Utility providers and services needed

  - Meter status (existing / new install required)

  - Target activation date — utilities must be ON before or immediately after home delivery

  - Any known delays, flags, or special circumstances

ACCOUNTING: Form submission is the trigger for Accounting to begin all utility activation work

Step 3.  Utility Account Setup & Activation

Owner: Accounting

- Upon receiving the Form, contact all utility providers on behalf of Parakeet.

- Open accounts in Parakeet's name.

- Confirm and document for each utility:

  - Account number

  - Activation / service start date

  - Deposit requirements (if any)

- If a new meter install is required: coordinate with the provider and notify Construction of the scheduled install date and any lead time delays.

- Schedule activation so utilities are ON before or immediately after home delivery.

- Notify Construction once all accounts are open and activation is confirmed.

Step 4.  Verify Utilities Are Live — At home set completion

Owner: Construction

- On completion date, physically verify on site:

  - Electric: live

  - Water: running

  - Sewer/septic: functional

  - Gas (if applicable): confirmed

IMPORTANT: Account confirmation from Accounting does not substitute for on-site physical verification. No assumptions.

- If any utility is not live: do not proceed. Log in Rent Manager Issues, notify Accounting immediately for provider escalation, and notify Regional and Construction leadership.

Step 5.  Verify Utilities Are Live — At CO and completion

Owner: Construction

- Once home set is completed, verify activation on site that water and electric are functioning as expected.

- Do not begin the interior punch process if utilities are not confirmed operational.

- Notify Accounting of any utility issues at set for immediate provider follow-up.

Step 6.  Notify Teams — Home Ready

Owner: Construction

- Confirm utilities are active and notify:

  - Operations — home is ready for walkthrough and maintenance coordination

  - Sales — home is ready for showings

WHEN THERE ARE ISSUES

| Issue | Action |
| --- | --- |
| No meter / new install required | Flag on Form at submission. Accounting escalates to provider and updates Construction on lead time and install date. |
| Delayed activation | Accounting notifies Construction immediately. Log in Rent Manager Issues. Escalate to Regional and Construction leadership. |
| Utility not live at delivery or set | Do not proceed. Accounting contacts provider for emergency escalation. |
| Infrastructure not ready | Log in RM Issues. Update Form. |

KEY EXPECTATIONS

- Submit the Form as soon as the issue is created or delivery is scheduled — not the week of delivery.

- Construction does not contact utility providers. All activation goes through Accounting.

- Utilities must be ON before: interior punch, showings.

- No home sits without utilities due to lack of follow-up.

WARNING: Failure to follow this process leads to delays in setup, missed sales timelines, and poor showing conditions.

Parakeet Communities, LLC  ·  Confidential Internal Document