SOP: Utility Activation — Rehabs

Parakeet Communities  ·  Operations / Accounting

| Applies To | All rehab homes |
| --- | --- |
| Process Owner | Operations |
| Utility Execution | Accounting — responsible for all utility activations and account requests |
| Trigger | Rehab is approved and scheduled OR vendor work requires utilities to be live |
| Finish Line | All utilities verified live; Rent Manager updated; teams notified |
| Last Revised | _________________ |

PURPOSE

Ensure all rehab homes have utilities activated on time to support vendor work, manager walkthroughs, punchlist, showings, and sale. Operations owns and drives this process. Accounting executes all utility activations and account setup. Utilities must be proactive — not reactive.

OWNERSHIP

| Role | Responsibility |
| --- | --- |
| Operations | Process owner. Confirms utility requirements, submits Form, verifies utilities live before vendor work begins, keeps utilities on through full rehab, updates Rent Manager, notifies teams. |
| Accounting | Executes all utility activations and account requests. Contacts providers, opens or transfers accounts in Parakeet's name, confirms account details, coordinates meter installs, notifies Operations when utilities are live. |
| Gabe | Tracks JotForm submissions; verifies Rent Manager entries against tracking log. |
| Sales | Coordinates showing timing; confirms utilities are live before showings. |

ACCOUNTING: Operations does not contact utility providers. All provider contact, account opening, transfers, and activation requests go through Accounting. Operations submits the JotForm — Accounting takes it from there.

TRIGGER

This process begins when a rehab is approved and scheduled, or when vendor work requires utilities to be live. Do not wait until the day before vendor work starts. If a new meter install is required, lead times can be significant — initiate immediately.

PROCESS

Step 1.  Confirm Utility Requirements

Owner: Operations

- Confirm which utilities the rehab vendor work requires: Electric, Water, Sewer/Septic, Gas (if applicable).

- Confirm utility providers for the property address.

- Determine meter status:

  - Existing meter → activate or transfer

  - No meter → new install required. Flag this immediately on the JotForm — new meter installs have significant lead times.

Step 2.  Submit Utility Form

Owner: Operations

- Complete and submit the Utility JotForm. Include:

  - Property and unit/lot number

  - Utility providers and services needed

  - Meter status (existing / new install required)

  - Target activation date — utilities must be ON before vendor work begins

  - Any known delays, flags, or special circumstances

ACCOUNTING: Form submission is the trigger for Accounting to begin all utility activation work. Do not contact providers. Submit the form — Accounting handles everything from here.

Step 3.  Utility Account Setup & Activation

Owner: Accounting

- Upon receiving the JotForm, contact all utility providers on behalf of Parakeet.

- Open or transfer accounts in Parakeet's name.

- Confirm and document for each utility:

  - Account number

  - Activation / service start date

  - Deposit requirements (if any)

- If a new meter install is required: coordinate with the provider and notify Operations of the scheduled install date and any lead time delays.

- Schedule activation so utilities are ON before vendor work begins.

- Notify Operations once all accounts are open and activation is confirmed.

Step 4.  Verify Utilities Are Live — Before Vendor Work

Owner: Operations

- Before vendor work begins, physically verify on site:

  - Electric: live

  - Water: running

  - Sewer/septic: functional (if applicable to vendor scope)

IMPORTANT: Vendor work does not begin until utilities are confirmed live on site. Account confirmation from Accounting is not sufficient — Operations must physically verify.

- If any utility is not live: do not start vendor work. Log in Rent Manager Issues, notify Accounting immediately for provider escalation, and notify Regional.

Step 5.  Utilities During Rehab

Owner: Operations

- Utilities remain ON throughout the full rehab process for:

  - All vendor work

  - Manager walkthrough and punchlist

  - Cleaning

  - Showings

- Operations monitors utility status throughout the rehab. If service is interrupted, notify Accounting immediately for restoration.

Step 6.  Notify Teams — Rehab Ready for Showings

Owner: Operations

- Once rehab and punchlist are complete and utilities are confirmed active, notify:

  - Sales — home is ready for showings

  - Regional — for awareness and sign-off if required

WHEN THERE ARE ISSUES

| Issue | Action |
| --- | --- |
| No meter / new install required | Flag on Form at submission. Accounting escalates to provider and updates Operations on lead time and install date. |
| Delayed activation | Accounting notifies Operations immediately. Log in Rent Manager Issues. Escalate to Regional. |
| Utility not live before vendor work | Do not start work. Log in RM Issues. Accounting contacts provider for emergency escalation. Notify Regional. |
| Service interrupted mid-rehab | Notify Accounting immediately for provider contact. Log in RM Issues. Pause vendor work if safety or quality is affected. |
| Infrastructure not ready | Log in RM Issues. Update Form. Escalate to Regional and leadership. No work proceeds until resolved. |

KEY EXPECTATIONS

- Submit the JotForm as soon as the rehab is approved — not the day before vendor work begins.

- Operations does not contact utility providers. All activation goes through Accounting.

- Utilities must be ON before: vendor work starts, manager walkthrough, punchlist, showings.

- Utilities stay ON throughout the full rehab — do not allow service to lapse mid-process.

- No home sits without utilities due to lack of follow-up.

WARNING: Failure to follow this process leads to vendor delays, missed timelines, poor showing conditions, and rework.

Parakeet Communities, LLC  ·  Confidential Internal Document