## SOP Tracker
SOP Rollout Master Tracker ¦ v3
Rebuilt 2026-08-06 from full audit of OneDrive working folder + ROCK processes + shared Lucid folder. Statuses reflect actual files, not intentions. See Change Log tab.
# | Dept | Process / SOP | Priority Tier | Category | Complexity | Creation Owner | Workflow Status | Workflow Location | SOP Status | SOP Location | Target | Lead | Workflow Needed? | Next Action
SALES / MARKETING
001 | Sales / Marketing | Home Ordering / New Home Purchase (Dealer) | Tier 2 - High | Property Mgmt | Medium | Sales + Operations | Final draft - ready for approval | Lucid: *001_Home Ordering Process | Final draft - ready for approval | OneDrive: 001-home_ordering_sop_FINAL.docx |  | AB | No | Final review + sign-off, then publish
002 | Sales / Marketing | Home Sales Process | Tier 1 - Critical | MH-Specific | High | Sales + Operations | Drafted - pending review | Lucid: *002_Home Sales Process; *002-004 Home Sales to Closing | Drafted - pending review | OneDrive: 002-combined-home sale process.docx |  | AB | In review | Team review
003 | Sales / Marketing | Home Closing Prep & Documentation (incl. 003a Lease w/ Option) | Tier 1 - Critical | MH-Specific | High | Sales + Operations | Drafted - pending review | Lucid: *003_CLOSING PREP & DOCUMENTATION | Drafted - pending review | OneDrive: 003- Home_Sale_Closing_SOPv1.docx; 003a Lease w/ Option SOP; Closing Doc Checklist |  | AB | In review | Team review
004 | Sales / Marketing | Closing Day Process | Tier 1 - Critical | MH-Specific | Medium | Sales + Operations | Drafted - pending review | Lucid: *004_Closing Day Process | Drafted - pending review | OneDrive: 003-CLOSING STEPS 05.05.2026.docx |  | AB | In review | Team review
005 | Sales / Marketing | POH Sales Title Transfer | Tier 1 - Critical | MH-Specific | High | Sales + Operations | Drafted - pending review | Lucid: *005_Home Title Transfer Process | Drafted - pending review | OneDrive: 005-Park Owned Home Sales Title Transfer SOP.pdf |  | AB | In review | Team review
006 | Sales / Marketing | Lead Intake, Tracking, Application & Screening (incl. AMRENT background check & income verification) | Tier 2 - High | Property Mgmt | Medium | Sales + Operations | Drafted - pending review | Lucid: 006-lead tracking and application process | Drafted - pending review | OneDrive: 006-lead tracking-application and background check V1.docx; SOP - Lead Intake PDF |  | AB | In review | Team review. Absorbs the two separate AMRENT/Prospect Screening tracker rows
| Sales / Marketing | Online Loan Application Process | Tier 2 - High | MH-Specific | Medium | Sales + Operations | Not started |  | Raw material - needs formalizing | ROCK: Online Loan Application Process.docx |  |  | YES | Formalize existing draft into numbered SOP + Lucid workflow
| Sales / Marketing | Sales Application-to-Lease Execution (Lease Generation in Rent Manager) | Recommended Addition | Property Mgmt | Medium | Sales + Operations | Partial draft | Lucid: Lead to Lease Process 2026.1 (outside shared folder) | Raw material - needs formalizing | ROCK: 3x Lease Generation SOP PDFs (RM Express, publish signable lease) |  |  | YES | Formalize - lease generation PDFs were never numbered or added to tracker
| Sales / Marketing | Home Listing Process | Recommended Addition | MH-Specific | Medium | Sales + Operations | Partial draft | Lucid: Home Listing Process (draft) | Not started |  |  |  | YES | Number it, finish workflow, draft SOP
| Sales / Marketing | Offer Submission Process | Recommended Addition | MH-Specific | Medium | Sales + Operations | Partial draft | Lucid: Offer Submission (draft) | Not started |  |  |  | YES | Number it, finish workflow, draft SOP. Ties to "rehab home for sale as-is" pause step
| Sales / Marketing | Rehab Home For-Sale As-Is Steps (offer pauses rehab) | Recommended Addition | MH-Specific | Medium | Sales + Ops + Construction | Not started |  | Not started |  |  |  | YES | Define workflow: offer Jotform pauses rehab, circle back to close out rehab if sold
| Sales / Marketing | Open House Process | Tier 3 - Standard | Property Mgmt | Low | Sales | Not started |  | Raw material - needs formalizing | ROCK: SOP-Open_House_Process_10-2022.docx |  |  | YES | Update 2022 draft, renumber, add workflow
| Sales / Marketing | Sales Rep Property Walk | Tier 3 - Standard | Property Mgmt | Low | Sales | Not started |  | Raw material - needs formalizing | ROCK: DRAFT sales property walk checklist V2.pdf |  |  | YES | Formalize checklist into SOP
| Sales / Marketing | Marketing Photography | Tier 3 - Standard | Property Mgmt | Low | Sales | Not started |  | Not started |  |  |  | YES | Build
OPERATIONS
100 | Operations | AR & Collections (incl. Demand Day cadence) | Tier 1 - Critical | Property Mgmt | High | Operations | Drafted - pending review | OneDrive: 100-collections_flowchart.html | Drafted - pending review | OneDrive: 100-collections_sop.docx | 2026-10-31 | AB | In review | Team review. Absorbs duplicate "Collections" tracker row
101 | Operations | Lease Renewal Process | Tier 1 - Critical | Property Mgmt | Medium | Operations | Drafted - pending review | Lucid: 101_Lease Renewal | Drafted - pending review | OneDrive: 101-lease_renewal_sop.docx | 2026-10-31 | AB | In review | Team review
102 | Operations | Move Out Process | Tier 1 - Critical | MH-Specific | High | Operations | Drafted - pending review | Lucid: 102_Move Out Process | Drafted - pending review | OneDrive: 102-move_out_sop.docx | 2026-10-31 | AB | In review | Team review. Delete stale Lucid duplicate (102 V1)
103 | Operations | Move In Process | Tier 1 - Critical | MH-Specific | High | Operations | Drafted - pending review | Lucid: 103_Move In Process | Drafted - pending review | OneDrive: 103-move_in_sop.docx |  | AB | In review | Team review
104 | Operations | TBD Unit Review & Allocate Process | Tier 1 - Critical | MH-Specific | High | Operations | Drafted - pending review | Lucid: 104_TBD Process | Drafted - pending review | OneDrive: TBD rehab and data entry Draft.docx; ROCK: 2x TBD Reporting SOP PDFs |  | AB | In review | Team review. Demo list + home ordering list adjustments feed 200/001
105 | Operations | POH Rehab Process (incl. Rehab Data Entry) | Tier 1 - Critical | MH-Specific | High | Construction + Operations | Drafted - pending review | Lucid: 105- POH rehab process | Drafted - pending review | OneDrive: 105-POH rehab process final draft.docx; Rehab_Data_Entry_SOP v1.1 |  | AB | In review | Team review. Delete stale Lucid 105a original draft
105a | Operations | Rehab Handoff Checklist (Jotform) | Tier 1 - Critical | MH-Specific | Medium | Construction + Operations | Partial draft | OneDrive: SOP-rehab handoff-MGR REHAB JOTFORM WORKFLOW.pdf | Raw material - needs formalizing | ROCK: 3x rehab handoff Jotform drafts; punchlist fillable PDF |  |  | YES | v2 note says "create fast form" - build the form, then finalize SOP
106 | Operations | Regional 30-Day Site Visit & Follow-Up | Tier 3 - Standard | Property Mgmt | Low | Operations | Drafted - pending review | OneDrive: 106-30day community visit action plan lucid flowchart V1.pdf | Drafted - pending review | OneDrive: 106- Regional 30-day action plan draft.docx |  |  | In review | Team review. Absorbs "Site Visit and Follow-Up Process" recommended-addition row. v2 tracker showed no workflow - it exists
107 | Operations | Eviction Process | Tier 1 - Critical | MH-Specific | High | Legal + Operations | Drafted - pending review | Lucid: 107-eviction flowchart v1; Eviction Process 26.01 | Drafted - pending review | OneDrive: 107-Eviction_Process_SOP_V1.docx |  | AB | In review | Team review. CONSOLIDATED: replaces both 800-series eviction rows + older 800-eviction_sop.docx. Decide final number (files use 107; 800-block is Legal)
| Operations | Emergency Property Level Issue Reporting | Tier 1 - Critical | Property Mgmt | Medium | Operations | Not started |  | Not started |  |  |  | YES | BUILD - Tier 1 gap. Life safety escalation paths
| Operations | Incident Reporting | Tier 1 - Critical | Property Mgmt | Medium | Operations | Not started |  | Not started |  |  |  | YES | BUILD - Tier 1 gap. Liability / insurance / legal feed
| Operations | Utility Onboarding (Current Communities) | Tier 1 - Critical | MH-Specific | High | Ops + Acct + Construction | Not started | Lucid: 0XX_Utility Account Establishment (draft, outside shared folder) | Raw material - needs formalizing | ROCK: SOP-Utility turn on.docx; Utilities SOP draft.docx; Utility draft flowchart |  |  | YES | Formalize - raw drafts exist, needs number + finished workflow
| Operations | Utility Transfers (Resident Move In/Out) | Tier 2 - High | MH-Specific | Medium | Ops + Acct | Covered by related SOP | See 303a/b + 102/103 | Covered by related SOP | See 303a/b + 102/103 |  |  | YES | Partially covered by 303a/b + 102/103 - confirm remaining scope, then build
| Operations | Month End Ops Close Out | Tier 2 - High | Property Mgmt | Medium | Operations | Not started |  | Raw material - needs formalizing | ROCK: L-Month End Checklist-Updated notes V1.pdf |  |  | YES | Formalize checklist into SOP + workflow
| Operations | Stipulation Process | Tier 2 - High | Property Mgmt | Medium | Operations | Not started |  | Not started |  |  |  | YES | Build - feeds 100 collections + 107 eviction pipeline
| Operations | Rental Inspections | Tier 2 - High | Property Mgmt | Medium | Operations | Not started |  | Not started |  |  |  | YES | Build
| Operations | Site Visit Inspection (Regional) | Tier 2 - High | Property Mgmt | Medium | Operations | Not started |  | Raw material - needs formalizing | ROCK: X-30 Day Site Visit Checklist for Facilities Managers.pdf |  |  | YES | Formalize - pairs with 106 follow-up
| Operations | Mo/Qtr Property Business Plan | Tier 2 - High | Property Mgmt | Medium | Operations | Not started |  | Not started |  |  |  | YES | Build
| Operations | Occupancy Recovery / Problem Asset Review | Recommended Addition |  |  | Ops + Sales + Asset Mgmt | Not started |  | Not started |  |  |  | YES | Build
| Operations | Emergency Infrastructure Escalation | Recommended Addition |  |  | Ops + Construction | Not started |  | Not started |  |  |  | YES | Build - pairs with Emergency Property Issue Reporting
| Operations | Rent Manager Issue Ownership & Update Standards | Recommended Addition |  |  | Ops + Systems | Not started |  | Not started |  |  |  | YES | Build
| Operations | Property Email / Communication Inclusion | Recommended Addition |  |  | Operations | Not started |  | Not started |  |  |  | YES | Build
| Operations | Rehab-to-Listing Readiness | Recommended Addition |  |  | Ops + Construction + Sales | Not started |  | Not started |  |  |  | YES | Largely covered by 105 + Home Listing - confirm gap before building
| Operations | Weekly Cross-Department Project Review | Recommended Addition |  |  | Operations | Not started |  | Not started |  |  |  | YES | Build
| Operations | Ops/Const Weekly Updates (Project Coordination) | Tier 3 - Standard | Property Mgmt | Low | Construction + Operations | Not started |  | Raw material - needs formalizing | ROCK: Weekly manager recap draft (jotform).docx; JC: WEEKLEY 5-15 REPORT.xlsx |  |  | YES | Merged two duplicate tracker rows (Ops #33 + Const #58). Formalize from recap draft
| Operations | Weekly Manager Recap (Jotform) | Recommended Addition |  |  | Operations | Not started |  | Raw material - needs formalizing | ROCK: Weekly manager recap draft (jotform).docx |  |  | YES | NEW - found in ROCK, was never in tracker. May merge with weekly updates row above
CONSTRUCTION / OPERATIONS
200 | Construction / Operations | Demo & Lot Prep | Tier 1 - Critical | MH-Specific | Medium | Construction + Operations | Approved | OneDrive: 200-Parakeet_Demo_Lot_Prep_Swimlane_Approved.html | Approved | OneDrive: 200-Parakeet_Demo_Lot_Prep_SOP_Approved.docx |  |  | No | DONE. Covers Lot Prep tracker row - confirm whether non-demo lot prep needs separate SOP
200a | Construction / Operations | Demo to Infill Process | Tier 1 - Critical | MH-Specific | High | Construction + Operations | Drafted - pending review | Lucid: 200 Demo to infill; 200a_Demo to infill | Drafted - pending review |  |  | AB | In review | Team review. Two Lucid versions - keep 200a, archive 200
201 | Construction / Operations | New Home Delivery / Set / Utility / Sales Release | Tier 1 - Critical | MH-Specific | High | Construction + Operations | Drafted - pending review | Lucid: 201 New Home delivery | Drafted - pending review | OneDrive: 201- New Home delivery-infill V1.docx; JC HOME DELIVERY PROCEDURE; ROCK: Home Delivery Confirmation JotForm SOP |  |  | In review | Team review. Absorbs "New Home Delivery/Set/Utility/Sales Release" recommended-addition row. v2 tracker row was blank - work exists
| Construction / Operations | Make Ready Board Flow | Tier 1 - Critical | MH-Specific | High | Construction + Operations | Partial draft | ROCK: MRB draft flowchart.png | Raw material - needs formalizing | ROCK: MRB draft SOP.docx; MRB draft V1 flowchart SOP.docx |  |  | YES | PRIORITY - Tier 1 with drafts sitting in ROCK. Number it, build Lucid workflow, finalize
| Construction / Operations | New Home Walkthrough Checklist | Tier 2 - High | MH-Specific | Medium | Construction + Operations | Not started |  | Raw material - needs formalizing | ROCK: PARAKEET HOMES NEW HOME CHECKLIST.pdf; Weekly Rehab & New Home Inspection Checklist |  |  | YES | Formalize checklists
| Construction / Operations | Construction Preventative Checklist | Tier 2 - High | MH-Specific | Medium | Construction | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Inhouse Construction Projects | Tier 2 - High | Property Mgmt | Medium | Construction | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Project Planning & Scope | Tier 2 - High | Property Mgmt | Medium | Construction | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Project Sign Off | Tier 2 - High | Property Mgmt | Medium | Construction | Not started |  | Not started |  |  |  | YES | Build - pairs with WIP close outs
| Construction / Operations | Property Future Cap Ex | Tier 2 - High | MH-Specific | Medium | Construction | Partial draft | Lucid: Cap Ex Decision Tree (outside shared folder) | Not started |  |  |  | YES | Pull decision tree into shared folder, draft SOP
| Construction / Operations | Construction-to-Operations Handoff | Recommended Addition |  |  | Construction + Operations | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Vendor Start / Stop / Access | Recommended Addition |  |  | Construction | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Construction Roles & Responsibilities | Tier 3 - Standard | Property Mgmt | Low | Construction | Not started |  | Raw material - needs formalizing | ROCK: JC Construction Department S.O.P. 4.19.2026.pdf |  |  | YES | Formalize from JC dept SOP
| Construction / Operations | Construction Onboarding | Tier 3 - Standard | Property Mgmt | Low | Construction + HR | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Equipment & Inventory Checklist | Tier 3 - Standard | Property Mgmt | Low | Construction + Accounting | Not started |  | Not started |  |  |  | YES | Build
| Construction / Operations | Maintenance vs Construction (routing) | Recommended Addition |  |  | Construction + Operations | Partial draft | Lucid: Maintenance vs Construction (draft) | Not started |  |  |  | YES | NEW - in Lucid shared folder, never in tracker. Number + finish
| Construction / Operations | Sign Installation Package | Recommended Addition |  |  | Construction | Not started |  | Raw material - needs formalizing | OneDrive: Parakeet Sign Installation Package.docx |  |  | YES | NEW - found in working folder, never in tracker. Formalize
ACCOUNTING / FINANCE
300 | Accounting / Finance | Avid Exchange AP Process | Tier 3 - Standard | Corporate | Medium | Accounting / Finance | Drafted - pending review | Lucid: 300_Avid AP Process | Drafted - pending review | OneDrive: 300-avid_exchange_sop.docx |  | AB | In review | Team review. Two Lucid docs (300_Avid + 300_Avid AP Process) - archive one
301 | Accounting / Finance | Rent Roll & Vacancy Reporting Approval | Tier 2 - High | Property Mgmt | Medium | Accounting / Finance | Drafted - pending review | OneDrive: 301 Rent Roll Summary Process.pdf | Drafted - pending review | ROCK: AR RR analytics SOP draft.docx |  | AB | In review | Team review
302 | Accounting / Finance | Home Lender Repo Process | Tier 2 - High | Corporate | Medium | Accounting / Finance | Drafted - pending review | Lucid: 302_Home lender repo | Drafted - pending review | OneDrive: 302-Home lender repo-draft V1.docx |  | AB | In review | Team review. Absorbs "repo home process" stub row (Sales/Acct)
303a | Accounting / Finance | Utility Activation - New Home | Recommended Addition | MH-Specific | Medium | Ops + Construction + Acct | Drafted - pending review | Lucid: 303a-Utility activation NEW HOME | Drafted - pending review | OneDrive: 303a-Utility activation-New Home-Draft V1.docx |  | AB | In review | Team review
303b | Accounting / Finance | Utility Activation - Rehab Home | Recommended Addition | MH-Specific | Medium | Ops + Construction + Acct | Drafted - pending review | Lucid: 303b- utility activation REHAB HOME | Drafted - pending review | OneDrive: 303b-Utility activation- REHAB HOME - draft V1.docx |  | AB | In review | Team review
| Accounting / Finance | Payroll Process | Tier 2 - High | Corporate | Medium | Accounting / Finance | Partial draft | Lucid: Payroll Process (in shared folder, unnumbered) | Not started |  |  |  | YES | Number it (30x), finish workflow, draft SOP
| Accounting / Finance | Utility Recapture Reporting | Tier 1 - Critical | MH-Specific | Medium | Ops + Acct + Construction | Not started |  | Not started |  |  |  | YES | BUILD - Tier 1 gap. Revenue recovery tracking
| Accounting / Finance | Utility Recapture Review | Tier 1 - Critical | MH-Specific | Medium | Ops + Acct + Construction | Not started |  | Not started |  |  |  | YES | BUILD - Tier 1 gap. Billing accuracy audit
| Accounting / Finance | Budgets (Annual Cycle) | Tier 2 - High | Property Mgmt | High | Accounting / Finance | Not started |  | Raw material - needs formalizing | ROCK: 2026 Budget workbook SOP V1.docx; Regional Manager Handout |  |  | YES | Formalize existing drafts before 2027 budget season
| Accounting / Finance | AP Process | Tier 2 - High | Corporate | Medium | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build - 300 Avid covers system side; this is PO/coding compliance
| Accounting / Finance | Financial Reporting | Tier 2 - High | Corporate | High | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build
| Accounting / Finance | P&L Reporting | Tier 2 - High | Property Mgmt | Medium | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build
| Accounting / Finance | Quarterly Reporting | Tier 2 - High | Corporate | Medium | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build
| Accounting / Finance | Corporate Model | Tier 2 - High | Corporate | High | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build
| Accounting / Finance | Month End Close (Accounting) | Tier 2 - High | Corporate | Medium | Accounting / Finance | Not started |  | Raw material - needs formalizing | ROCK/David: Accounting Team Calendar.xlsx |  |  | YES | Formalize from accounting calendar
806 | Accounting / Finance | Security Deposit Handling & Refund (FL) | Tier 3 - Standard | Property Mgmt | Low | Accounting / Finance | Drafted - pending review | OneDrive: 806-security_deposit_flowchart.html | Drafted - pending review | OneDrive: 806-security_deposit_sop.docx |  | AB | In review | Drafted 2026-08-06 from FS 83.49 + 723.031(9). GA version = 814, SC version = 824
| Accounting / Finance | Debt Payment | Tier 3 - Standard | Corporate | Low | Accounting / Finance | Not started |  | Raw material - needs formalizing | ROCK/David: MASTER Debt Overview.xlsx |  |  | YES | Build from David's master workbook
| Accounting / Finance | Tax Process | Tier 3 - Standard | Corporate | High | Accounting / Finance | Not started |  | Raw material - needs formalizing | ROCK/David: MASTER Property Final Tax Bills.xlsb |  |  | YES | Build from David's master workbook
| Accounting / Finance | Fixed Assets | Tier 3 - Standard | Property Mgmt | Medium | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build
| Accounting / Finance | WIP Close Outs | Tier 3 - Standard | Corporate | Medium | Accounting / Finance | Not started |  | Not started |  |  |  | YES | Build - pairs with Project Sign Off
ACQUISITIONS / ASSET MGMT
| Acquisitions / Asset Mgmt | Due Diligence & Acquisition Process | Tier 1 - Critical | MH-Specific | High | Asset Mgmt / Acquisitions | Partial draft | ROCK/Zach: DD Process Flowchart v2.0.pdf | Not started |  |  |  | YES | PRIORITY - Zach's flowchart exists. Move to Lucid shared folder, number in 500s, draft SOP
| Acquisitions / Asset Mgmt | Acquisitions Transitions (Community Takeover) | Tier 1 - Critical | MH-Specific | High | Asset Mgmt / Acquisitions | Not started |  | Raw material - needs formalizing | ROCK: Regional to Regional Transitions.docx |  |  | YES | BUILD - Tier 1 gap. Regional transition doc is partial raw material
| Acquisitions / Asset Mgmt | Utility Onboarding (Acquisitions) | Tier 1 - Critical | MH-Specific | High | Ops + Acct + Construction | Not started |  | Not started |  |  |  | YES | BUILD - Tier 1 gap. Sub-metering / master-meter / RUBS setup at takeover
| Acquisitions / Asset Mgmt | Acq-OPS Transition Recaps | Tier 2 - High | MH-Specific | Medium | Asset Mgmt / Acquisitions | Not started |  | Not started |  |  |  | YES | Build
| Acquisitions / Asset Mgmt | Disposition / Selling of Assets (dept requirements) | Recommended Addition |  |  | Asset Mgmt / Acquisitions | Not started |  | Not started |  |  |  | YES | Build - was a stub row in v2 with no detail
LEGAL / COMPLIANCE
| Legal / Compliance | Post Eviction Title Process | Tier 1 - Critical | MH-Specific | High | Legal / Compliance | Drafted - pending review | OneDrive: Post-Eviction Title Process.pdf | Drafted - pending review | OneDrive: Post Eviction Title Transfer SOP.pdf |  |  | In review | Drafts exist but unnumbered - number in 800s, route for review. Lucid: Abandonment Process Flow relates
| Legal / Compliance | Resident Turn-In Title Transfer | Recommended Addition | MH-Specific | Medium | Legal / Compliance | Drafted - pending review | OneDrive: Resident Turn-In Process.pdf | Drafted - pending review | OneDrive: Resident Turn-In Title Transfer SOP.pdf |  |  | In review | NEW - drafted but never in tracker. Number + review
| Legal / Compliance | Title Work Process (Master) | Tier 1 - Critical | MH-Specific | High | Legal / Compliance | Partial draft |  | Partial draft | Covered piecemeal by 005, Post-Eviction, Resident Turn-In, ROCK: Asset Title Transfer Tab SOP |  |  | YES | Unify the title SOPs into one master process w/ variants
801 | Legal / Compliance | Rent Increase & Pass-Throughs (FL Ch. 723) | Tier 1 - Critical | MH-Specific | High | Legal / Compliance | Drafted - pending review | OneDrive: 801-rent_increase_passthrough_flowchart.html | Drafted - pending review | OneDrive: 801-rent_increase_passthrough_sop.docx |  | AB | In review | Drafted 2026-08-06 from FS 723.031/.033/.037/.038 + prospectuses. FL counsel review, then team review
804 | Legal / Compliance | Prospectus Delivery, Tracking & Remediation (FL) | Tier 1 - Critical | MH-Specific | High | Legal / Compliance | Drafted - pending review | OneDrive: 804-prospectus_delivery_flowchart.html | Drafted - pending review | OneDrive: 804-prospectus_delivery_sop.docx |  | AB | In review | NEW - drafted 2026-08-06 from FS 723.011/.012. Includes no-prospectus community remediation list
805 | Legal / Compliance | Rules & Regulations Change Process (FL) | Tier 2 - High | MH-Specific | Medium | Legal / Compliance | Drafted - pending review | OneDrive: 805-rules_change_flowchart.html | Drafted - pending review | OneDrive: 805-rules_change_sop.docx |  | AB | In review | NEW - drafted 2026-08-06 from FS 723.037/.038. FL counsel review, then team review
| Legal / Compliance | Asset Title Transfer (Entity-Level) | Tier 2 - High | MH-Specific | Medium | Legal / Compliance | Not started |  | Raw material - needs formalizing | ROCK: Asset Title Transfer Tab SOP.pdf |  |  | YES | Formalize
802 | Legal / Compliance | Community Rules Violation & Enforcement (FL) | Tier 2 - High | Property Mgmt | Medium | Legal / Compliance | Drafted - pending review | OneDrive: 802-violation_enforcement_flowchart.html | Drafted - pending review | OneDrive: 802-violation_enforcement_sop.docx |  | AB | In review | Drafted 2026-08-06 - dual track FS 723.061 (lot tenants) / FS 83.56 (POH renters). FL counsel review
| Legal / Compliance | Fair Housing Annual Training | Tier 2 - High | Property Mgmt | Low | Legal + HR | Not started |  | Raw material - needs formalizing | ROCK: FHI Annual Training SOP.pdf |  |  | YES | Formalize
| Legal / Compliance | Insurance Renewals | Tier 2 - High | Property Mgmt | Medium | Legal + Asset Mgmt | Not started |  | Raw material - needs formalizing | ROCK/David: MASTER Insurance Policy Inventory.xlsx |  |  | YES | Build from David's master workbook
| Legal / Compliance | License / Permit Renewals | Tier 2 - High | MH-Specific | Medium | Legal / Compliance | Not started |  | Raw material - needs formalizing | ROCK/David: MASTER Compliance Calendar.xlsx |  |  | YES | Build from compliance calendar
803 | Legal / Compliance | Resident Notice Service & Documentation (FL) | Recommended Addition |  |  | Legal + Operations | Drafted - pending review | OneDrive: 803-notice_service_flowchart.html | Drafted - pending review | OneDrive: 803-notice_service_sop.docx |  | AB | In review | Drafted 2026-08-06 - service standards matrix (FS 723.037/.061, 83.49/.56) + 5-day mailbox rule. Referenced by 100/107/801/802/805/806
811 | Legal / Compliance | Rent Increase & Term Changes (GA) | Tier 2 - High | MH-Specific | Medium | Legal / Compliance | Drafted - pending review | OneDrive: 811-ga_rent_increase_flowchart.html | Drafted - pending review | OneDrive: 811-ga_rent_increase_sop.docx |  | AB | In review | Drafted 2026-08-06 from O.C.G.A. 44-7-7 + lease terms. GA counsel review
812 | Legal / Compliance | Violations, Demand & Dispossessory (GA) | Tier 1 - Critical | MH-Specific | High | Legal / Compliance | Drafted - pending review | OneDrive: 812-ga_violations_dispossessory_flowchart.html | Drafted - pending review | OneDrive: 812-ga_violations_dispossessory_sop.docx |  | AB | In review | Drafted 2026-08-06 - incl. 2024 three-business-day notice (44-7-50(c)) + 7-day tender rule (44-7-52). GA counsel review
813 | Legal / Compliance | Resident Notice Service & Documentation (GA) | Recommended Addition |  |  | Legal + Operations | Drafted - pending review | OneDrive: 813-ga_notice_service_flowchart.html | Drafted - pending review | OneDrive: 813-ga_notice_service_sop.docx |  | AB | In review | Drafted 2026-08-06 - sealed-envelope door posting standard
814 | Legal / Compliance | Security Deposit Handling & Refund (GA) | Tier 2 - High | Property Mgmt | Medium | Legal + Accounting | Drafted - pending review | OneDrive: 814-ga_security_deposit_flowchart.html | Drafted - pending review | OneDrive: 814-ga_security_deposit_sop.docx |  | AB | In review | Drafted 2026-08-06 from O.C.G.A. 44-7-30 to -37 (escrow, inspection lists, 30-day return)
821 | Legal / Compliance | Rent Increase & Rental Agreement Requirements (SC) | Tier 2 - High | MH-Specific | Medium | Legal / Compliance | Drafted - pending review | OneDrive: 821-sc_rent_increase_flowchart.html | Drafted - pending review | OneDrive: 821-sc_rent_increase_sop.docx |  | AB | In review | Drafted 2026-08-06 from SC 27-47-420/-310/-510 (30-day notice + continuation election). SC counsel review
822 | Legal / Compliance | Violations, Eviction & Abandoned Home (SC) | Tier 1 - Critical | MH-Specific | High | Legal / Compliance | Drafted - pending review | OneDrive: 822-sc_violations_eviction_flowchart.html | Drafted - pending review | OneDrive: 822-sc_violations_eviction_sop.docx |  | AB | In review | Drafted 2026-08-06 from SC 27-47-530 + 27-40-710; incl. 20-day abandoned home auction path (29-15-10). SC counsel review
823 | Legal / Compliance | Resident Notice Service & Documentation (SC) | Recommended Addition |  |  | Legal + Operations | Drafted - pending review | OneDrive: 823-sc_notice_service_flowchart.html | Drafted - pending review | OneDrive: 823-sc_notice_service_sop.docx |  | AB | In review | Drafted 2026-08-06
824 | Legal / Compliance | Security Deposit Handling & Refund (SC) | Tier 3 - Standard | Property Mgmt | Low | Legal + Accounting | Drafted - pending review | OneDrive: 824-sc_security_deposit_flowchart.html | Drafted - pending review | OneDrive: 824-sc_security_deposit_sop.docx |  | AB | In review | Drafted 2026-08-06 from SC 27-47-520 + 27-40-410 (30-day return, treble damages)
HR / TRAINING
| HR / Training | Manager Onboarding | Tier 2 - High | MH-Specific | Medium | HR | Not started |  | Raw material - needs formalizing | ROCK: Parakeet Online Onboarding for Community Managers.pdf |  |  | YES | Formalize
| HR / Training | Online Onboarding | Tier 3 - Standard | Property Mgmt | Low | HR | Not started |  | Raw material - needs formalizing | Same source as Manager Onboarding |  |  | YES | Formalize - may merge with row above
| HR / Training | Team Onboarding & Training | Tier 2 - High | Property Mgmt | Medium | HR | Not started |  | Not started |  |  |  | YES | Build
| HR / Training | Hiring / Onboarding Responsibilities (HR vs Ops) | Recommended Addition |  |  | HR + Operations | Not started |  | Not started |  |  |  | YES | Build - was an untiered stub in v2
| HR / Training | Triplog Training | Tier 3 - Standard | Corporate | Low | HR | Not started |  | Not started |  |  |  | YES | Build
SYSTEMS / REPORTING
| Systems / Reporting | Jotform Process (Form Ecosystem) | Tier 2 - High | Corporate | Medium | Operations + Systems | Partial draft | Lucid: JotForm Workflows | Not started |  |  |  | YES | Consolidate all Jotform SOPs into ecosystem doc
| Systems / Reporting | Rent Manager Express Docs | Tier 2 - High | Property Mgmt | Medium | Operations + Systems | Not started |  | Raw material - needs formalizing | ROCK: Lease generation RM Express PDFs |  |  | YES | Formalize
Legend:
Green row = Approved / final draft
Yellow row = Drafted, pending review
Red row = Tier 1 Critical with nothing started

## Summary
Pipeline Summary
Counts pull live from the SOP Tracker tab.
Status | Workflows | SOP Docs
Approved | 1 | 1
Final draft - ready for approval | 1 | 1
Drafted - pending review | 36 | 36
Partial draft | 11 | 1
Raw material - needs formalizing | 0 | 26
Covered by related SOP | 1 | 1
Not started | 59 | 43
Total processes tracked | 109 | 109
Workflows still needed (YES flags) | 71
Tier 1 Critical not started (red rows) | 7
Numbering System
000-099 | Sales & Marketing
100-199 | Operations
200-299 | Construction
300-399 | Accounting
400-499 | Asset Management
500-599 | Acquisitions / Dispositions
600-699 | Systems / IT / Reporting
700-799 | HR
800-899 | Legal

## Change Log
v2 to v3 Change Log ¦ 2026-08-06
Type | Change
Consolidated | "Collections" duplicate row merged into 100 AR & Collections.
Consolidated | "Eviction Process" (800) + "Evictions" (800, flagged duplicate in v2) merged into 107 Eviction Process, which has the current drafts (Aug 2026). Final number 107 vs 800 still needs a call since 800-block is Legal.
Consolidated | "Site Visit and Follow-Up Process" (recommended addition) merged into 106 Regional 30-Day Site Visit.
Consolidated | "New Home Delivery / Set / Utility / Sales Release" (recommended addition) merged into 201, which has drafted workflow + SOP.
Consolidated | "AMRENT Background Check" (Legal) + "Prospect Screening/AMRENT" (Sales) merged into 006 Lead Intake & Screening.
Consolidated | "Ops/Const Weekly Updates" (#33) + "Project Coordination Weekly Update" (#58) merged into one row.
Consolidated | "repo home process" stub merged into 302 Home Lender Repo.
Numbering fix | v2 Sheet1 had 002/003 swapped vs the main sheet and the actual files. v3 follows the files: 002 = Home Sales, 003 = Closing Prep. Stale Sheet1 list dropped entirely.
Status fix | 106: v2 showed no workflow. Lucid flowchart PDF + SOP draft both exist.
Status fix | 201: v2 row was blank. Workflow (Lucid) + SOP draft V1 + JC delivery procedure all exist.
Status fix | 200 Demo & Lot Prep: marked APPROVED (docx + swimlane approved in folder). Covers the "Lot Prep" tracker row.
Status fix | Post Eviction Title + Resident Turn-In Title: drafted SOPs/PDFs exist in folder - v2 showed Not Started / not listed.
Status fix | Make Ready Board, DD Process (Zach flowchart v2.0), Budgets, Month End, Lease Generation, Open House, Fair Housing, Online Loan App, Manager Onboarding: raw drafts exist in ROCK processes - flagged "Raw material - needs formalizing" instead of Not Started.
Added | Rows never in v2: Weekly Manager Recap, Resident Turn-In Title Transfer, Sign Installation Package, Maintenance vs Construction, Home Listing, Offer Submission, Payroll (Lucid draft).
Cleanup needed | Lucid near-duplicates to archive: 102 V1 Move Out, 105a original draft, 200 vs 200a Demo to Infill, 300_Avid vs 300_Avid AP Process, 2x Blank diagrams, Copy of 003-Sale Process, Move in & Move Out process (superseded by 102/103).