SOP: Infill Reporting Stages + Department Responsibilities

Purpose: Create one consistent, trackable workflow from vacant lot / move-out → home ready for sale/rent, with clear handoffs and reporting stages.
Scope: All communities with infill (new homes, replacements, storage deliveries, or set-up units).
Trigger: A lot becomes vacant (move-out/demo/removal) or a new infill opportunity is approved.

Stage 1 — NOT STARTED

What this stage means (box intent): A vacant lot has been identified but infill has not formally launched.

Inputs

- Confirmed vacancy (move-out, demo planned/completed, or lot identified for new placement)

Department responsibilities

- Operations (Owner):

  - Confirm lot is vacant, accessible, and safe.

  - Verify address/lot number is correct in the system.

  - Flag any resident impact, access constraints, or immediate site hazards.

- Asset Management (Owner):

  - Ensure the vacant lot is on the infill tracker and assigned a target use (sale vs rental, model type assumptions if known).

  - Confirm priority level (based on occupancy goals).

- Construction (Support):

  - Quick feasibility check: setbacks, grade, utilities location, known constraints.

- Acquisitions (Support, only if new asset/transition):

  - Provide any due diligence constraints or municipal restrictions discovered during acquisition.

Required outputs to move forward

- Lot confirmed vacant + added to tracker with basic info (community, lot #, intended strategy).

Stage 2 — SITE SURVEY

What this stage means: A site survey has been requested and/or completed to confirm feasibility for placement.

Box descriptions

- “Obtain Site Survey”: Request/receive survey (or site plan verification) and confirm boundaries, setbacks, utilities, and placement feasibility.

Department responsibilities

- Construction (Owner):

  - Order/coordinate site survey as required (or verify existing).

  - Confirm placement orientation, setbacks, utility tie-in points, elevation/grade, and access.

- Operations (Support):

  - Provide site access, lot condition notes, and known issues (tree removal, resident conflicts, gate access).

- Asset Management (Support):

  - Confirm the survey meets what lender/insurer/county may require; store documentation in the correct folder.

- Accounting/Finance (Support):

  - Confirm vendor setup/PO if needed.

Required outputs

- Survey/site plan documentation stored + summarized constraints noted on tracker.

Stage 3 — CHOOSE HOME

What this stage means: The home model/spec is selected for that lot.

Box descriptions

- “Spec New Home”: Proposed model/floorplan/features finalized for the lot (sale vs rental, beds/baths, size, skirting/deck assumptions).

Department responsibilities

- Sales & Marketing (Owner for Sale Homes; Support for Rentals):

  - Recommend home model based on demand, pricing, comps, and community standards.

  - Confirm finish package and market positioning.

- Asset Management (Owner for Rentals; Support for Sale Homes):

  - Approve strategy (rental vs sale) and confirm target returns / rent/purchase assumptions.

- Construction (Support):

  - Confirm the model fits the lot and aligns with county requirements (wind zone, tie-down needs, stairs/landing constraints).

- Operations (Support):

  - Confirm operational needs (parking layout, mailbox location, trash access, resident flow).

- Acquisitions (Support, if applicable):

  - Confirm any restrictions from acquisition docs/HOA/municipality.

Required outputs

- Selected home model and spec documented + internal approval obtained (per your approval chain).

Stage 4 — SUBMIT FOR PERMITTING

What this stage means: The build/set permit package is submitted and in process.

Box descriptions

- “Home Approved?” (decision diamond): Internal approval confirmation (model + budget + timeline).

- “File for Build Permit”: Permit application submitted (county/city), including required docs from manufacturer, site plan, foundation/anchoring package, etc.

Department responsibilities

- Construction (Owner):

  - Prepare/submit full permit package and track review status.

  - Maintain permit log: submittal date, comments, resubmittals, expected approval date.

- Accounting/Finance (Support):

  - Pay permit fees and track costs to correct project/GL.

- Asset Management (Support/Approval):

  - Confirm the approved budget and capex categorization.

- Operations (Support):

  - Provide any community-level documents needed (addresses, utility provider confirmation, access letters).

Required outputs

- Permit submitted + tracker updated with permit status and estimated approval date.

Stage 5 — LOT PREP

What this stage means: The lot is physically prepared so the home can be delivered and installed.

Box descriptions

- “Lot Prep”: Pad/grade, utility readiness, clearing, driveway, sewer/water/electric readiness, and any demo/cleanup required.

Department responsibilities

- Construction (Owner):

  - Scope and schedule lot prep work and vendors.

  - Confirm readiness standards (grade, compaction, utility stub locations, clearances).

- Operations (Support):

  - Coordinate resident communications if work impacts neighbors.

  - Verify work order tracking, site access, and onsite oversight.

- Accounting/Finance (Support):

  - Ensure PO/scope documentation matches invoices (avoid surprise charges).

- Sales & Marketing (Support):

  - Align timing if this is a retail sale (marketing launch tied to delivery ETA).

Required outputs

- Lot prep completion confirmed and documented (photos + completion date + “lot ready” status).

Stage 6 — HOME ORDERED

What this stage means: The home has been ordered from the manufacturer and is officially in the pipeline.

Box descriptions

- “Order Home”: Purchase order executed; build slot assigned.

- “Marketing Process”: For sale homes, marketing begins (pre-sales, waitlists, listing setup).

Also shown in this stage

- Asset Created (Asset Management system): The new home record is created in the system (or placeholder asset created).

- Record Home Price (Accounting/Finance): Purchase price recorded for tracking and lender reporting.

- Send Notification to Lender (Accounting/Finance): Lender notified as required for draws/approvals (if applicable).

Department responsibilities

- Construction (Owner):

  - Place the home order, confirm build specs, timeline, and delivery requirements.

- Asset Management (Owner):

  - Create the home/asset record in the system and link it to the correct lot.

  - Ensure naming conventions, status, and metadata are correct.

- Accounting/Finance (Owner):

  - Record purchase price, expected deposits, draw schedule, and vendor terms.

  - Notify lender per reporting requirements (when applicable).

- Sales & Marketing (Owner for sale homes):

  - Launch marketing timeline aligned to delivery/install.

  - Confirm pricing strategy and promotional plan.

Required outputs

- Confirmed PO/order + asset record created + financial tracking started + marketing initiated (if sale).

Stage 7 — HOME DELIVERED

What this stage means: The home has arrived (either delivered to the lot or delivered to storage).

Box descriptions

- “Home Delivery Scheduled” (vertical lane): Delivery appointment confirmed and coordinated.

- “Home Delivered to Storage”: Delivered to staging/storage yard (not yet on lot).

- Decision: “Lot Ready?”: If lot is ready → deliver to lot; if not → storage.

Department responsibilities

- Construction (Owner):

  - Schedule delivery, confirm access, escort needs, and delivery checklist.

  - Document delivery condition and any freight damage immediately.

- Operations (Support):

  - Coordinate site access and resident notifications (road closures, parking impacts).

- Asset Management (Support):

  - Update tracker status and confirm asset record reflects delivery milestone.

- Accounting/Finance (Support):

  - Confirm invoices match delivered unit/spec and handle damage claims documentation.

Required outputs

- Delivery confirmation + condition photos + tracker updated (delivered to lot or storage).

Stage 8 — SET UP HOME

What this stage means: The home is set, installed, tied down, and moving through punch and final readiness steps.

Box descriptions

- “Home Delivered to Lot”: Unit placed onsite.

- “Home Set Up”: Install (set, tie-down, utility connections, steps/landings as required, skirting, inspections).

- “Mail Docs to MD”: Required documents sent to the designated internal owner (e.g., title/installation paperwork, inspection approvals, warranty, HUD labels info).

- “Punch List”: Final deficiencies list created and cleared.

Department responsibilities

- Construction (Owner):

  - Manage install/set crew; coordinate inspections; drive punch list closure.

  - Collect installation docs and inspection approvals.

- Operations (Support/Owner for readiness coordination):

  - Confirm utilities accounts are ready to transfer/activate where needed.

  - Ensure site standards are met (address markers, mailbox, trash, lot cleanliness).

- Asset Management (Owner):

  - Ensure all documents are uploaded and the asset record is updated correctly.

- Accounting/Finance (Support):

  - Process invoices in alignment with completed milestones and required docs.

Required outputs

- Home set + inspections passing + punch list completed + documentation routed and saved.

Stage 9 — READY

What this stage means: The home is fully ready for occupancy and the next business process begins.

Box descriptions

- “Sales Process”: If the home is for sale, sales/closing process proceeds.

- (If rental: leasing process begins—marketing, screening, lease signing, move-in.)

Also shown

- Asset Updated: Final update to the system: status, serial/VIN, HUD labels (if applicable), pricing/rents, make-ready completion, and photos.

Department responsibilities

- Sales & Marketing (Owner for sale; Support for rental marketing):

  - Activate listing, manage pipeline, drive move-in/closing.

- Operations (Owner for rentals and move-in readiness):

  - Complete leasing/move-in coordination and resident onboarding.

- Asset Management (Owner):

  - Confirm asset status = Ready; verify all fields/docs complete; update KPI tracker.

- Accounting/Finance (Support):

  - Confirm capitalization/asset schedule tracking and any lender reporting closeout.

Required outputs

- “Ready” confirmed with photos + system updated + sales/leasing launched.

Reporting Rules (to keep the tracker clean)

- One stage at a time: A lot cannot move forward unless the prior stage’s required outputs are met.

- Owner updates within 24 hours of a milestone (permit submitted, lot prep complete, delivered, set, ready).

- Documentation requirement: Delivery photos, permits, inspections, and punch list must be stored in the standard folder and linked in the tracker.

Department Ownership Summary (simple)

- Construction: Survey → Permitting → Lot Prep → Order → Delivery → Install/Set → Punch

- Operations: Vacancy confirmation → access/resident comms → utilities readiness → move-in coordination (rentals)

- Sales & Marketing: Model selection input → marketing launch → sales execution (sale homes)

- Asset Management: Tracker owner + asset record creation/updates + document control

- Accounting/Finance: Pricing/cost tracking + lender notices + invoice controls

- Acquisitions: Only where asset transition restrictions or due diligence constraints apply