REHAB TO READY TO ADVERTISE

General Standard

A rehabbed home should be brought to the best condition supported by the approved scope and budget. The goal is to create a home that is safe, functional, clean, presentable, ready to show, and ready to market honestly. The goal is not to create unrealistic expectations around an older home simply because work was completed.

Managers, Marketing, and Sales must understand that an older home will never be brand new unless it has been fully gutted to the studs and rebuilt. Construction is responsible for defining the general scope being given to the vendor, and that scope must be shared with Operations so managers understand what is being completed, what is not being completed, and what the home should look like at turnover.

Process Flow

- Home Identified for Rehab:

  - During the TBD call a home is identified as needing rehab, or demo.

- General Scope is Built:

  - Construction is responsible for building the general scope of work and base budget for the home before it is turned over to a vendor or moved into active rehab. That scope should be clear enough for Operations and managers to understand what is being repaired, what is being replaced, what is cosmetic, what is functional, and what is not included.

- Scope is Shared with Operations:

  - Before or during the rehab process, Construction must share the general scope with Operations and the appropriate Regional and Community Manager so they understand what work is being completed, what work is not being completed, what condition the home is expected to be in at turnover, and how the home should be positioned later.

- Vendor Completes the Rehab:

  - Construction is responsible for managing the vendor and moving the rehab work through completion. During this stage, Construction should monitor progress, communicate delays, communicate material scope changes, and update Operations when timing or condition changes in a way that affects market readiness.

- Walk and Punch Review:

  - Once the rehab work is substantially complete, Construction or Operations should walk the home and confirm approved scope has been completed.

- Operations Punch review

  - Review operations rehab checklist and complete small items that impact marketing and salability.

- Ready for Marketing Decision:

  - Home is to be uploaded to Jotform as the Home listing request. Operations, Construction, and Sales or Marketing should be aligned so that the home is rehab complete, clean and show ready, priced appropriately for condition, ready for photos, ready to be shown, and ready to be marketed without misleading the prospect.

- Sales Positioning:

  - Once the listing is active, Sales and onsite teams should position the home based on what it is.

Department Responsibilities

Construction

Build the general scope of work

Manage vendor execution

Communication of delays or material scope changes

Complete final walk before turnover

Operations / Regional / Manager

Review and understand the approved scope

Align manager expectations with final condition

Walk home before marketing handoff

Confirm the home is ready to show

Marketing

Activate listing only when the home is truly ready

Use listing language that reflects actual completed condition

Coordinate photography and listing setup

Sales

Understand the product being shown

Speak accurately about updates and condition

Set realistic expectations with prospects

Position the home as value driven and move in ready within its actual scope