SOP: Rehab Closeout → Manager Walk → Ready to Market

Purpose

To ensure all rehab homes are properly verified, completed, and documented before being released to market.

Trigger

- Construction marks rehab as Vendor Complete and communicates that to operations. This will initiate the manager’s walkthrough process.

Step 1: Manager Final Walk (Required)

- Manager performs full walkthrough using Rehab Punchlist JotForm

- Walk must be completed on the same day as notification

- Completed form is automatically sent to:

  - Regional

  - Director of Operations

  - Director of Construction

  - Director of Sales

Decision Point (Manager Determines Status)

Manager must select one of the following at the end of the JotForm:

Option 1: Ready to List/Show

- Home meets all standards

- No outstanding issues

- Parakeet P plaque is put in window of home (indicates the home is Park owned and ready)

Next Step triggered:

- Manager submits Home Listing Request form

- Sales schedules photography

- Home moves to market

Option 2: Not Ready – Maintenance (Manager Scope)

- Minor items remaining (cleaning, touch-ups, small repairs)

Manager/ Maintenance Responsibilities:

- Open Rent Manager issues/work orders (one week to complete)

- Track to completion

Option 3: Needs Additional Work – Vendor (Construction Scope)

- Items missing from original vendor scope

Manager Responsibilities:

- Document issues in:

  - JotForm notes

  - Confirm construction has received the punchlist for vendor.

Construction Responsibilities:

- Contact vendor

- Coordinate completion of missed items

System Tracking:

- Construction updates RM notes for rehab issue

Step 4: Re-Walk Loop (Required Until Complete)

- Process repeats until home is marked: Ready to List/Show

- Parakeet P plaque is put in window of home (indicates the home is Park owned and ready)

Step 5: Managers walk home to submit Home Listing Request Form

- Manager submitting the Home Listing Request Form including photos.

- This will determine if Sales needs to schedule professional photographer to take pictures of home.

System Requirements

- All issues must be tracked in Rent Manager

- JotForm must be completed every walk