SOP: Utility Activation – Rehabs & New Homes

Purpose

Ensure all homes (rehabs + new infill) have utilities activated on time to support:

- Vendor work

- Final walkthroughs

- Showings / sales

- Move-ins

Ownership (No Gray Area)

- Primary Owner: Construction (Lead)

- Oversight: Operations

- Coordination: Sales (timing / readiness)

- Tracking / Support: Gabe

👉 Utilities are part of the construction delivery process, not a follow-up task.

When This Starts (Trigger Points)

New Homes

- Home is assigned to a lot (MRB created)

- OR home delivery scheduled

Rehabs

- Rehab is approved and scheduled

- OR vendor work requires utilities

Process by Phase

PHASE 1: Pre-Work Setup (Construction Lead)

1. Confirm Utility Requirements

Construction must:

- Identify utilities needed:

  - Electric

  - Water

  - Sewer / Septic

  - Gas (if applicable)

- Confirm providers

2. Determine Meter Status

- Existing meter: Activate or transfer

- No meter: Order new install

👉 If new meter needed:

- Construction owns coordination

- Escalate delays immediately

3. Submit Utility JotForm (Required)

Completed by Construction:

- Property + lot

- Utility providers

- Meter status

- Target activation date

👉 This triggers tracking with Gabe

PHASE 2: Account Setup (Construction Lead)

4. Open Accounts

Construction:

- Contacts utility providers

- Opens accounts in Parakeet name

- Confirms:

  - Account number

  - Activation/start date

  - Deposit requirements

5. Schedule Activation

- Utilities should be:

  - ON before vendor work begins (rehabs)

  - ON before or immediately after delivery (new homes)

PHASE 3: Verification (Construction + Ops)

6. Confirm Utilities Are Active

Construction verifies:

- Electric live

- Water running

- Sewer/septic functional

Operations:

- Confirms during walkthroughs

👉 No assumptions—must be physically verified

PHASE 4: Workflow Integration

Rehab Flow

- Utilities ON → Vendor work begins

- Vendor completes → Manager walkthrough

- Utilities remain ON for:

  - Punchlist

  - Cleaning

  - Showings

New Home Flow

- Utilities ON → Home delivered / set

- Utilities support:

  - Setup

  - Punchlist

  - Showings

  - Sale

PHASE 5: System Updates

7. Rent Manager Updates (Required)

Construction must:

- Enter:

  - Provider

  - Account number

  - Activation date

Gabe:

- Verifies via JotForm + tracking

PHASE 6: Handoff to Operations & Sales

8. Notify Teams

Construction confirms utilities are active and notifies:

- Operations → ready for walkthrough / maintenance

- Sales → ready for showings

If There Are Issues

Examples

- No meter

- Delayed activation

- Infrastructure not ready

Action

- Log in Rent Manager Issues

- Update JotForm

- Escalate immediately:

  - Regional

  - Construction leadership

Key Expectations

- Utilities must be proactive—not reactive

- No home sits without utilities due to lack of follow-up

- Utilities must be ON before:

  - Vendor work

  - Final walk

  - Showings

Failure to Execute

Leads to:

- Delays in rehab / setup

- Missed sales timelines

- Poor showing conditions

Bottom Line

Utilities are part of the construction completion process.
If the home is not powered, it is not ready.

👉 Construction owns getting them on.
👉 Operations verifies.
👉 Sales depends on it.